## LOGISTIK MASUK (hidden)
No. | NO. PON | NO. PON | NO. PON | NO. PON | NO. PON | NO. PON | NO. PON | NO. PON

## STATUS (hidden)
STATUS | MARKETING | AKSESORIS | Vendor
ON GOING | JON PUTRA
HOLD | WIRA KANAN
COMPLETED | CHAKIM
RFD | YUSUF

## DASHBOARD FINAL
2024-12-14
NO. PON | Type Struktur | Marking Struktur | Qty (Unit) | Status Pekerjaan | Progress (%) | Sum of Total Berat (Kg) | ISSUE'S
STKJ18 | Panel Bailey STOCK | KOMPONEN BAILEY | 1 | COMPLETED | 100% | 189231.53 | N/A
STKJ19 | Panel Bailey STOCK | KOMPONEN BAILEY | 1 | COMPLETED | 100% | 155984.84 | N/A
STKJ20 | Panel Bailey STOCK | KOMPONEN BAILEY | 1 | COMPLETED | 100% | 285981.34 | N/A
STKJ21 | Panel Bailey STOCK | KOMPONEN BAILEY | 1 | COMPLETED | 100% | 174798.16 | N/A
STKJ22 | Panel Bailey STOCK | KOMPONEN BAILEY | 1 | COMPLETED | 100% | 313247.54 | N/A
STKJ23 | Panel Bailey STOCK | KOMPONEN BAILEY | 1 | COMPLETED | 100% | 397430.23 | N/A
STKJ24 | Panel Bailey STOCK | KOMPONEN BAILEY | 1 | COMPLETED | 100% | 197176.7795 | N/A
STKJ25 | Panel Bailey STOCK | KOMPONEN BAILEY | 1 | COMPLETED | 100% | 338892.27 | N/A
STOCK2022 | Panel Bailey STOCK | KOMPONEN BAILEY | 1 | COMPLETED | 100% | 273475.7663 | N/A
W-370 | Truss Modullar | RB60-BU+LINKSET | 2 | COMPLETED | 100% | 0 | N/A
W-489A | PLATE LRB | BASEPLATE FOR LRB | 1 | COMPLETED | 100% | 79206.4578 | N/A
W-489B | PLATE LRB | BASEPLATE FOR LRB | 1 | COMPLETED | 100% | 48589.616 | N/A
W-493 | PIPE RACK | PIPE RACK | 1 | RFD | 100% | 14655.016 | Ready di WS Setu
W-494 | FENCING SHELTER & STAIRCASES | FENCING | 1 | RFD | 100% | 3450.457 | Ready packing di CGI
W-495A-02 | PLATE LRB | BASEPLATE FOR LRB | 1 | COMPLETED | 100% | 875.3339 | N/A
W-496-A | PLATE LRB | BASEPLATE FOR LRB | 1 | COMPLETED | 100% | 3090.48 | N/A
W-496-B | PLATE LRB | BASEPLATE FOR LRB | 1 | COMPLETED | 100% | 18126.9838 | N/A
W-498 | Jembatan Gantung | JG105 - PIPA | 1 | COMPLETED | 100% | 12451.612 | N/A
W-499 | Girder | AG30 | 1 | COMPLETED | 100% | 46075.954 | N/A
W-500 | Panel Bailey | 33M DSR2 - SS400 | 1 | COMPLETED | 100% | 33141.031 | N/A
W-501 | Girder | AG20 | 1 | COMPLETED | 100% | 24177.0809 | N/A
W-502 | Girder | AG8 | 1 | COMPLETED | 100% | 16367.0541 | N/A
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | 1 | COMPLETED | 100% | 66115.71 | N/A
W-504A | Panel Bailey | 12 SSR-EW | 2 | COMPLETED | 100% | 26998.236 | N/A
W-504B | Panel Bailey | 15 SSR-EW | 3 | COMPLETED | 100% | 50129.346 | N/A
W-504C | Panel Bailey | 21 SSR-EW | 1 | COMPLETED | 100% | 22417.19 | N/A
W-505 | Panel Bailey | KOMPONEN BAILEY | 1 | COMPLETED | 100% | 1453.8612 | N/A
W-506A | Panel Bailey | 24 DSR2-EW | 2 | RFD | 90% | 71754.1 | 1 unit sudah terkirim 1 unit Ready packing di CGI
W-506B | Panel Bailey | 21 DS-EW | 2 | RFD | 90% | 52532.916 | Ready packing di CGI
W-506C | Panel Bailey | 18 DSR1-EW | 1 | RFD | 90% | 25049.214 | Ready packing di CGI
W-506D | Panel Bailey | 18 DSR2-EW | 1 | COMPLETED | 100% | 27225.018 | N/A
W-506E | Panel Bailey | 33 DSR2H*-EW (U120) | 1 | COMPLETED | 100% | 51714.872 | N/A
W-507 | Panel Bailey | 30 DSR2-EW | 3 | COMPLETED | 100% | 133017.63 | N/A
W-511 | Girder | BG22 | 1 | COMPLETED | 100% | 29180.4485 | N/A
W-512A | Panel Bailey | 42 DSR2-EW (U120) | 1 | COMPLETED | 100% | 62875.614 | N/A
W-512B | Panel Bailey | 45 DSR2H**-EW (U120) | 2 | COMPLETED | 100% | 141070.488 | N/A
W-512C | BEAM TRESTLE | TRESTLE BEAM | 1 | COMPLETED | 100% | 4164.234 | N/A
W-513 | Panel Bailey | 30 DSR2-EW | 1 | COMPLETED | 100% | 44339.21 | N/A
W-514 | Girder | CG30 | 1 | COMPLETED | 100% | 32415.4597 | N/A
W-515 | Panel Bailey | KOMPONEN BAILEY | 1 | COMPLETED | 100% | 3482.36 | N/A
W-516A | Panel Bailey | 36 DSR2-EW | 1 | COMPLETED | 100% | 53793.21 | N/A
W-516B | Panel Bailey | 30 DSR2-EW | 2 | COMPLETED | 100% | 88678.42 | N/A
W-516C | Panel Bailey | 45 TSR2 - EW | 1 | COMPLETED | 100% | 81510.536 | N/A
W-516D | RAMP Panel Bailey | RAMP PANEL BAILEY | 6 | COMPLETED | 100% | 11561.544 | N/A
W-517 | Panel Bailey | 30 DSR2-EW | 1 | COMPLETED | 100% | 44339.21 | N/A
W-518A | Panel Bailey | 21 SSR-EW | 2 | RFD | 90% | 44834.38 | 1 UNIT RELEASE. 1 UNIT RFD%
W-518B | Panel Bailey | 24 SSR-EW | 1 | COMPLETED | 100% | 25436.974 | N/A
W-518C | Panel Bailey | 27 DSR2-EW | 1 | RFD | 90% | 40050.05 | Ready packing di CGI
W-519 | Panel Bailey | 39 DSR2H**-EW | 1 | COMPLETED | 100% | 62589.2273 | N/A
W-520A | Girder Spesial | GD14 | 1 | COMPLETED | 100% | 9075.5536 | N/A
W-520B | Girder Spesial | GD16 | 5 | COMPLETED | 100% | 54983.898 | N/A
W-520C | Girder Spesial | GD18 | 3 | COMPLETED | 100% | 38275.0878 | N/A
W-520D | Girder Spesial | GD20 | 1 | COMPLETED | 100% | 15456.9756 | N/A
W-521 | Girder | BG25 | 1 | COMPLETED | 100% | 34174.3084 | N/A
W-522 | Truss Modullar | KOMPONEN STRINGGER | 1 | COMPLETED | 100% | 11675.6 | N/A
W-523 | Girder | BG25 | 1 | COMPLETED | 100% | 29572.0964 | N/A
W-524 | WELDED BEAM | WB BEAM | 1 | COMPLETED | 100% | 3854.33 | N/A
W-525 | Girder | BG30 | 1 | COMPLETED | 100% | 64277.9259 | N/A
W-526 | Girder | CG30 | 1 | COMPLETED | 100% | 34214.7931 | N/A
W-527 | Girder | BG35 | 1 | COMPLETED | 100% | 68400.2952 | N/A
W-528 | Girder | BG20 | 1 | COMPLETED | 100% | 25519.3032 | N/A
W-529 | Truss Modullar | RB50 | 2 | COMPLETED | 100% | 191888.7568 | N/A
W-530 | Jembatan Gantung | JG154 | 1 | COMPLETED | 100% | 44161.22 | N/A
W-531 | Girder | CG15_6 Line | 1 | COMPLETED | 100% | 19480.0286 | N/A
W-532 | Girder | BG30 | 1 | COMPLETED | 100% | 39989.3442 | N/A
W-532A | ORNAMEN PIPA | GB30-ARCH | 1 | COMPLETED | 100% | 6708.215 | N/A
W-533 | Jembatan Gantung | JG120 | 1 | COMPLETED | 100% | 30913.5586 | N/A
W-534 | Girder | AG20 | 1 | COMPLETED | 100% | 25465.0419 | N/A
W-535 | Jembatan Gantung | JG80 | 1 | COMPLETED | 100% | 22831.6388 | N/A
W-536 | Girder | CG30 | 1 | COMPLETED | 100% | 34172.5531 | N/A
W-537 | Panel Bailey | 30 SSR-EW | 3 | COMPLETED | 100% | 94327.386 | N/A
W-538 | Truss Modullar | RB60 | 1 | COMPLETED | 100% | 142183.7838 | N/A
W-539 | SPECER MRT | SPECER MRT | 1 | COMPLETED | 100% | 5737.32 | N/A
W-540 | SUPPORT BEAM | SB35 | 1 | COMPLETED | 100% | 20784.694 | N/A
W-541 | Girder | CG12 | 1 | COMPLETED | 100% | 10589.4137 | N/A
W-542 | Jembatan Gantung | JG360_TAHAP I | 1 | ON GOING | 100% | 330142.696 | N/A
W-543 | Girder | GB30 | 1 | COMPLETED | 100% | 42160.0246 | N/A
W-544 | Panel Bailey | 9 SSR-EW | 2 | COMPLETED | 100% | 20651.148 | N/A
W-545 | Jembatan Gantung | JG150 | 1 | COMPLETED | 100% | 30198.0538 | N/A
W-546 | Panel Bailey | 39 DSR2H**-EW | 1 | COMPLETED | 100% | 61467.6273 | N/A
W-547 | Panel Bailey | 6 SSR-SW | 3 | COMPLETED | 100% | 21879.15 | N/A
W-548 | PLATE LRB | LRB | 1 | COMPLETED | 100% | 2307.1734 | N/A
W-549 | Truss Modullar | RB40 | 1 | COMPLETED | 100% | 72876.4092 | N/A
W-550 | Panel Bailey | 30 DSR2-EW | 1 | COMPLETED | 100% | 44339.21 | N/A
W-551 | Girder | AG40 | 1 | COMPLETED | 100% | 123722.8476 | N/A
W-552 | JPO | JPO-48 | 1 | COMPLETED | 100% | 23903.115 | N/A
W-553 | Panel Bailey | 12 SSR-EW | 3 | COMPLETED | 100% | 34890.852 | N/A
W-554 | STRUKTUR PERKUATAN | PERKUATAN | 1 | COMPLETED | 100% | 6951.4169 | N/A
W-555 | Jembatan Gantung | JG40_ASIMETRIS | 1 | COMPLETED | 100% | 16494.38 | N/A
W-556 | Girder | CG12 | 1 | COMPLETED | 100% | 8639.5305 | N/A
W-557 | Panel Bailey | Ex. England | 1 | COMPLETED | 100% | 103.3201 | N/A
W-558 | Truss Modullar | RB30 | 1 | COMPLETED | 100% | 52321.6543 | N/A
W-559 | Jembatan Gantung | JG100P | 1 | COMPLETED | 100% | 37054.8846 | N/A
W-560A | Jembatan Pendekat | SPAN 11.87 M | 2 | COMPLETED | 100% | 5502.3032 | N/A
W-560B | Jembatan Pendekat | SPAN 14.20 M | 1 | COMPLETED | 100% | 5255.8646 | N/A
W-560C | Jembatan Pendekat | SPAN 22.82 M | 1 | COMPLETED | 100% | 15732.922 | N/A
W-561 | TOWER | TWR-H36 | 1 | COMPLETED | 100% | 12082.8918 | N/A
W-562 | Panel Bailey | 24 DSR2-EW | 1 | COMPLETED | 100% | 36276.538 | N/A
W-563 | Girder | CG12 | 1 | COMPLETED | 100% | 8728.8064 | N/A
W-564 | Truss Modullar | RB50 | 1 | COMPLETED | 100% | 104003.1182 | N/A
W-565 | Panel Bailey | 36 DSR2-EW | 1 | COMPLETED | 100% | 53793.21 | N/A
W-565A | RAMP Panel Bailey | RAMP PANEL BAILEY | 2 | COMPLETED | 100% | 3795.92 | N/A
W-566 | Girder | AG18.8 | 1 | COMPLETED | 100% | 42795.4413 | N/A
W-567 | STRUKTUR ATAP | ATAP ASRAMA HAJI | 1 | COMPLETED | 100% | 15052.733 | N/A
W-568A | Panel Bailey | 18 SSR - EW (LANTAI KAYU) | 1 | COMPLETED | 100% | 14531.93 | N/A
W-568B | Panel Bailey | 24 SSR - EW (LANTAI KAYU) | 1 | COMPLETED | 100% | 18952.19 | N/A
W-569 | Truss Modullar | RB40 | 1 | COMPLETED | 100% | 67567.7924 | N/A
W-570 | Truss Modullar | RB30 | 1 | COMPLETED | 100% | 52321.6543 | N/A
W-571 | Panel Bailey | 30 DSR2-EW | 1 | COMPLETED | 100% | 44339.21 | N/A
W-572 | Panel Bailey | 21 SSR-EW | 1 | COMPLETED | 100% | 22682.47 | N/A
W-573 | Truss Modullar | RB40 | 1 | COMPLETED | 100% | 72876.4092 | N/A
W-574 | Truss Modullar | RC45+15 | 1 | COMPLETED | 100% | 45602.9137 | N/A
W-575 | Girder | C43 | 1 | COMPLETED | 100% | 13623.514 | N/A
W-576A | Panel Bailey | 18 SSR - EW | 1 | COMPLETED | 100% | 19372.446 | N/A
W-576B | Panel Bailey | 12 SSR-EW | 1 | COMPLETED | 100% | 11637.868 | N/A
W-577 | Girder | AG20 | 1 | COMPLETED | 100% | 24177.0809 | N/A
W-578 | KING POST | KP | 1 | ON GOING | 10% | 451165.015 | FINISH MATERIAL GRADE SS400
W-579 | Panel Bailey | 30 DSR2-EW | 2 | COMPLETED | 100% | 90725.14 | N/A
W-579A | Panel Bailey | 36 DSR2-EW | 2 | COMPLETED | 100% | 107586.42 | N/A
W-580 | Panel Bailey | 39 DSR2H**-EW | 2 | COMPLETED | 100% | 122935.2546 | KEKURANGAN WCRH
W-581 | Komponen Jembatan | WB BEAM | 1 | COMPLETED | 100% | 26360.78
W-582 | Komponen Jembatan | WB BEAM | 1 | COMPLETED | 100% | 2216.0074
W-585 | Jembatan Gantung | Komponen JG152 | 1 | COMPLETED | 100% | 57494
Grand Total | [5 empty] | 7503159.4498 | N/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AReady di WS SetuReady packing di CGIN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/A1 unit sudah terkirim 1 unit Ready packing di CGIReady packing di CGIReady packing di CGIN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/A1 UNIT RELEASE. 1 UNIT RFD%N/AReady packing di CGIN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AN/AFINISH MATERIAL GRADE SS400N/AN/AKEKURANGAN WCRH
`
REKAP OUTSTANDING PEKERJAAN 2023
1. W493 & 494 => sebagian material sudah terpakai
2. W506 => Unit Jembatan masih di CGI bentang 1x24 DSR2-EW,
2X21 DS-EW, & 1X18DS-EW, Est. 113,459.18 Kg
3. W518 => Unit Jembatan masih di CGI bentang 1x21 SSR-EW,
Est. 62,467.24 Kg
4. W579 & W580 => Outstanding pengiriman material Komponen WCRH2 = 21 Pcs
& 1xRamp Panel Bailey , Est. 8,149.82 Kg
5. W578 => Pekerjaan masih berjalan dalam proses fabrikasi,
DASHBOARD STATUS PEKERJAAN PT. WGJ
LIST PEKERJAAN PT. WIRATAMA GLOBALINDO JAYA TAHUN 2023
PROJECT SUMMARIES
PERSENTASE TERHADAP STATUS PEKERJAAN
PERSENTASE TERHADAP STATUS PEKERJAAN
SUMMARIES
SUMMARIES
7,503,159.45
14 Dec 2024

## PIVOT
PIVOT 1
Row Labels | Sum of Total Berat (Kg) | Row Labels | Count of Total Berat (Kg)
BEAM TRESTLE | 4164.234 | COMPLETED | 92.68%
FENCING SHELTER & STAIRCASES | 3450.457 | ON GOING | 1.626%
Girder | 797918.3461 | RFD | 5.691%
Girder Spesial | 117791.5151 | Grand Total | 100%
Jembatan Gantung | 581742.0438
Jembatan Pendekat | 26491.0898
JPO | 23903.115
KING POST | 451165.015
Komponen Jembatan | 28576.7874
ORNAMEN PIPA | 6708.215
Panel Bailey | 2075040.1735 | Row Labels | Sum of Total Berat (Kg)
Panel Bailey STOCK | 2326218.4557 | ATADIWIRA KANAN | 16.5%
PIPE RACK | 14655.016 | CHAKIM | 1.996%
PLATE LRB | 152196.0449 | FIKRI ARAFAH | 6.089%
RAMP Panel Bailey | 15357.464 | JON PUTRA | 31.71%
SPECER MRT | 5737.32 | N/A | 31%
STRUKTUR ATAP | 15052.733 | YUSUF | 12.69%
STRUKTUR PERKUATAN | 6951.4169 | Grand Total | 100%
SUPPORT BEAM | 20784.694
TOWER | 12082.8918 | Marketing | Marking Struktur | Qty (Unit) | Sum of Total Berat (Kg)
Truss Modullar | 813318.0919 | ATADIWIRA KANAN |  |  | 1238358.6069
WELDED BEAM | 3854.33 | CHAKIM |  |  | 149741.1793
Grand Total | 7503159.4498 | FIKRI ARAFAH |  |  | 456902.335
|  | JON PUTRA | 12 SSR-EW | 1 | 11637.868
|  | JON PUTRA | 12 SSR-EW | 2 | 26998.236
|  | JON PUTRA | 12 SSR-EW | 3 | 34890.852
|  | JON PUTRA | 15 SSR-EW | 3 | 50129.346
Row Labels | Sum of Total Berat (Kg) | JON PUTRA | 18 DSR1-EW | 1 | 25049.214
COMPLETED | 6469525.6058 | JON PUTRA | 18 DSR2-EW | 1 | 27225.018
ON GOING | 781307.711 | JON PUTRA | 18 SSR - EW | 1 | 19372.446
RFD | 252326.133 | JON PUTRA | 18 SSR - EW (LANTAI KAYU) | 1 | 14531.93
Grand Total | 7503159.4498 | JON PUTRA | 21 DS-EW | 2 | 52532.916
|  | JON PUTRA | 21 SSR-EW | 1 | 22417.19
|  | JON PUTRA | 21 SSR-EW | 2 | 44834.38
|  | JON PUTRA | 24 DSR2-EW | 1 | 36276.538
|  | JON PUTRA | 24 DSR2-EW | 2 | 71754.1
|  | JON PUTRA | 24 SSR - EW (LANTAI KAYU) | 1 | 18952.19
|  | JON PUTRA | 24 SSR-EW | 1 | 25436.974
|  | JON PUTRA | 27 DSR2-EW | 1 | 40050.05
|  | JON PUTRA | 30 DSR2-EW | 1 | 133017.63
|  | JON PUTRA | 30 DSR2-EW | 3 | 133017.63
|  | JON PUTRA | 33 DSR2H*-EW (U120) | 1 | 51714.872
|  | JON PUTRA | 36 DSR2-EW | 1 | 53793.21
|  | JON PUTRA | 39 DSR2H**-EW | 1 | 62589.2273
|  | JON PUTRA | 42 DSR2-EW (U120) | 1 | 62875.614
|  | JON PUTRA | 42 DSR2-EW + TRESTLE | 1 | 66115.71
|  | JON PUTRA | 45 DSR2H**-EW (U120) | 2 | 141070.488
|  | JON PUTRA | 6 SSR-SW | 3 | 21879.15
|  | JON PUTRA | 9 SSR-EW | 2 | 20651.148
|  | JON PUTRA | AG30 | 1 | 46075.954
|  | JON PUTRA | AG8 | 1 | 16367.0541
|  | JON PUTRA | ATAP ASRAMA HAJI | 1 | 15052.733
|  | JON PUTRA | BG20 | 1 | 25519.3032
|  | JON PUTRA | BG22 | 1 | 29180.4485
35877.05 |  | JON PUTRA | BG25 | 1 | 29572.0964
113459.18 |  | JON PUTRA | BG30 | 1 | 64277.9259
|  | JON PUTRA | BG35 | 1 | 68400.2952
|  | JON PUTRA | C43 | 1 | 13623.514
|  | JON PUTRA | CG15_6 Line | 1 | 19480.0286
113459.18 |  | JON PUTRA | CG30 | 1 | 32415.4597
|  | JON PUTRA | GB30 | 1 | 42160.0246
22417.19 |  | JON PUTRA | GD14 | 1 | 9075.5536
62467.24 |  | JON PUTRA | GD16 | 5 | 54983.898
|  | JON PUTRA | GD18 | 3 | 38275.0878
62467.24 |  | JON PUTRA | GD20 | 1 | 15456.9756
|  | JON PUTRA | JG100P | 1 | 37054.8846
3794 | 4355.82 | JON PUTRA | JG105 - PIPA | 1 | 12451.612
8149.82 |  | JON PUTRA | JG154 | 1 | 44161.22
8149.82 |  | JON PUTRA | JG40_ASIMETRIS | 1 | 16494.38
|  | JON PUTRA | KOMPONEN STRINGGER | 1 | 11675.6
|  | JON PUTRA | PERKUATAN | 1 | 6951.4169
|  | JON PUTRA | RAMP PANEL BAILEY | 2 | 3795.92
|  | JON PUTRA | RB30 | 1 | 104643.3086
|  | JON PUTRA | RB40 | 1 | 140444.2015
|  | JON PUTRA | RB50 | 1 | 104003.1182
|  | JON PUTRA | RC45+15 | 1 | 45602.9137
|  | JON PUTRA | SB35 | 1 | 20784.694
|  | JON PUTRA | SPAN 11.87 M | 2 | 5502.3032
|  | JON PUTRA | SPAN 14.20 M | 1 | 5255.8646
|  | JON PUTRA | SPAN 22.82 M | 1 | 15732.922
|  | JON PUTRA | TRESTLE BEAM | 1 | 4164.234
|  | JON PUTRA | TWR-H36 | 1 | 12082.8918
|  | N/A | KOMPONEN BAILEY | 1 | 2326218.4557
|  | YUSUF | 30 DSR2-EW | 1 | 44339.21
|  | YUSUF | 30 DSR2-EW | 2 | 179403.56
|  | YUSUF | 36 DSR2-EW | 1 | 53793.21
|  | YUSUF | 36 DSR2-EW | 2 | 107586.42
|  | YUSUF | 39 DSR2H**-EW | 1 | 61467.6273
|  | YUSUF | 39 DSR2H**-EW | 2 | 122935.2546
|  | YUSUF | 45 TSR2 - EW | 1 | 81510.536
|  | YUSUF | AG40 | 1 | 123722.8476
|  | YUSUF | JPO-48 | 1 | 23903.115
|  | YUSUF | RAMP PANEL BAILEY | 6 | 11561.544
|  | YUSUF | RB60 | 1 | 142183.7838

## DATA MASTER
NO. PON | Type Struktur | Qty (Unit) | Marking Struktur | Deskripsi Pekerjaan | Client | Daerah | Total Berat (Kg) | Status | Marketing | Progress | Issue | SUPPLY LIST | Date PON | Date Finish | Column1 | Date Aktual Finish | Finish Fabrikasi | Date Aktual Delivery to Site | REMINDER | Keterangan | TAHUN
STKJ18 | Panel Bailey STOCK | 1 | KOMPONEN BAILEY | STOCK | N/A | N/A | 189231.53 | COMPLETED | N/A | 100% | N/A |  | 2023-02-06 | 2023-03-29 |  | 0 | 2023-03-29 | 0 | On schedule | COMPLETED | 2023
STKJ19 | Panel Bailey STOCK | 1 | KOMPONEN BAILEY | STOCK | N/A | N/A | 155984.84 | COMPLETED | N/A | 100% | N/A |  |  |  |  | 0 | 2024-12-14 | -45640 | Terlambat | COMPLETED | 2023
STKJ20 | Panel Bailey STOCK | 1 | KOMPONEN BAILEY | STOCK | N/A | N/A | 285981.34 | COMPLETED | N/A | 100% | N/A |  |  |  |  | 0 | 2024-12-14 | -45640 | Terlambat | COMPLETED | 2023
STKJ21 | Panel Bailey STOCK | 1 | KOMPONEN BAILEY | STOCK | N/A | N/A | 174798.16 | COMPLETED | N/A | 100% | N/A |  |  |  |  | 0 | 2024-12-14 | -45640 | Terlambat | COMPLETED | 2023
STKJ22 | Panel Bailey STOCK | 1 | KOMPONEN BAILEY | STOCK | N/A | N/A | 313247.54 | COMPLETED | N/A | 100% | N/A |  |  |  |  | 0 | 2024-12-14 | -45640 | Terlambat | COMPLETED | 2023
STKJ23 | Panel Bailey STOCK | 1 | KOMPONEN BAILEY | STOCK | N/A | N/A | 397430.23 | COMPLETED | N/A | 100% | N/A |  |  |  |  | 0 | 2024-12-14 | -45640 | Terlambat | COMPLETED | 2023
STKJ24 | Panel Bailey STOCK | 1 | KOMPONEN BAILEY | STOCK | N/A | N/A | 197176.7795 | COMPLETED | N/A | 100% | N/A |  |  |  |  | 0 | 2024-12-14 | -45640 | Terlambat | COMPLETED | 2023
STKJ25 | Panel Bailey STOCK | 1 | KOMPONEN BAILEY | STOCK | N/A | N/A | 338892.27 | COMPLETED | N/A | 100% | N/A | [6 empty] | 0 | On schedule | COMPLETED | 2023
STOCK2022 | Panel Bailey STOCK | 1 | KOMPONEN BAILEY | STOCK | N/A |  | 273475.7663 | COMPLETED | N/A | 100% | N/A | [6 empty] | 0 | On schedule | COMPLETED | 2023
W-370 | Truss Modullar | 2 | RB60-BU+LINKSET | Pembangunan Jembatan Lemo Seberang – Desa Lemo, Kab. Barito Utara, Kalimantan Tengah | PT. MITRA BARITO LUMBUNG ENERGI | BARITO UTARA | 0 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  |  |  |  | 2023-07-21 | 2023-07-31 | -45138 | Terlambat | COMPLETED | 2021
W-489A | PLATE LRB | 1 | BASEPLATE FOR LRB | SHIM PLATE TEBAL 3MM | PT. FREYSSINET TOTAL TECHNOLOGY | #VALUE! | 79206.4578 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-01-05 | 2023-02-03 | 29 | 0 | 2023-04-15 | -71 | Terlambat | COMPLETED | 2023
W-489B | PLATE LRB | 1 | BASEPLATE FOR LRB | YOGYA BAWEN/ 909 | PT. FREYSSINET TOTAL TECHNOLOGY | #VALUE! | 48589.616 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-01-12 | 2023-02-03 | 22 | 0 | 2023-04-15 | -71 | Terlambat | COMPLETED | 2023
W-493 | PIPE RACK | 1 | PIPE RACK | PIPE RACK | PT. PETROSEA TBK (PTRO - NHM SERVICE) | #VALUE! | 14655.016 | RFD | ATADIWIRA KANAN | 100% | Ready di WS Setu |  | 2022-12-02 | 2023-12-23 | 386 | 2023-02-27 | 2024-12-14 | -357 | Terlambat | WAKTU | 2023
W-494 | FENCING SHELTER & STAIRCASES | 1 | FENCING | FENCING SHELTER & STAIRCASES | PT. PETROSEA TBK (PTRO - NHM SERVICE) | #VALUE! | 3450.457 | RFD | ATADIWIRA KANAN | 100% | Ready packing di CGI |  | 2022-12-02 | 2022-12-16 | 14 | 2023-02-27 | 2024-12-14 | -729 | Terlambat | WAKTU | 2023
W-495A-02 | PLATE LRB | 1 | BASEPLATE FOR LRB | JEMBATAN PANCOKANG/ 944 | PT. FREYSSINET TOTAL TECHNOLOGY | #VALUE! | 875.3339 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-02-07 | 2023-02-17 | 10 | 0 | 2023-02-25 | -8 | Terlambat | COMPLETED | 2023
W-496-A | PLATE LRB | 1 | BASEPLATE FOR LRB | MAKASSAR NEW PORT/ 928 | PT. FREYSSINET TOTAL TECHNOLOGY | #VALUE! | 3090.48 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-02-13 | 2023-02-27 | 14 | 0 | 2023-03-21 | -22 | Terlambat | COMPLETED | 2023
W-496-B | PLATE LRB | 1 | BASEPLATE FOR LRB | MAKASSAR NEW PORT/ 928 | PT. FREYSSINET TOTAL TECHNOLOGY | #VALUE! | 18126.9838 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-03-16 | 2023-04-06 | 21 | 0 | 2023-06-06 | -61 | Terlambat | COMPLETED | 2023
W-498 | Jembatan Gantung | 1 | JG105 - PIPA | Optimalisasi SPAM Kec. Dumbo Raya PDAM Kota Gorontalo | PT. DHARMA KARYA DHIKA ALAMBHANA | #VALUE! | 12451.612 | COMPLETED | JON PUTRA | 100% | N/A | 16951.4593 | 2023-01-31 | 2023-03-20 | 48 | 0 | 2023-03-17 | 3 | FALSE | COMPLETED | 2023
W-499 | Girder | 1 | AG30 | Pembangunan Jalan Jembatan Sidangoli | CV. YEMIMA KARYA UTAMA | #VALUE! | 46075.954 | COMPLETED | JON PUTRA | 100% | N/A | 51607.7474 | 2023-01-10 | 2023-02-28 | 49 | 2023-02-07 | 2023-06-20 | -112 | Terlambat | COMPLETED | 2023
W-500 | Panel Bailey | 1 | 33M DSR2 - SS400 | JEMBATAN PANEL BAJA 33 METER DI SUNGAU MAWANG ESTATE (SMWE) | PT. SAWIT KAPUAS KENCANA | #VALUE! | 33141.031 | COMPLETED | ATADIWIRA KANAN | 100% | N/A | 37486.1148 | 2023-01-11 | 2023-03-01 | 49 | 2023-03-29 | 2023-05-24 | -84 | Terlambat | COMPLETED | 2023
W-501 | Girder | 1 | AG20 | PEMBANGUNAN JALAN MALINAU - LONG SEMAMU | PT. BUDI BAKTI - DUTA MEGA, KSO | #VALUE! | 24177.0809 | COMPLETED | CHAKIM | 100% | N/A | 25351.7212 | 2023-01-13 | 2023-02-12 | 30 | 2023-02-08 | 2023-03-14 | -30 | Terlambat | COMPLETED | 2023
W-502 | Girder | 1 | AG8 | Preservasi Jalan Asam Baru - Sp. Bangkal - Bts. Kota Sampit | PT. BAWAN PERMAI GROUP | #VALUE! | 16367.0541 | COMPLETED | JON PUTRA | 100% | N/A | 17671.9921 | 2023-02-03 | 2023-03-16 | 41 | 2023-03-01 | 2023-03-24 | -8 | Terlambat | COMPLETED | 2023
W-503 | Panel Bailey | 1 | 42 DSR2-EW + TRESTLE | KONSTRUKSI JEMBATAN BAILEY 42DSR GORONTALO | PT. HARMONIS PERKASAINDAH POHUWATO | #VALUE! | 66115.71 | COMPLETED | JON PUTRA | 100% | N/A | 75141.9912 | 2023-02-02 | 2023-03-04 | 30 | 2023-03-07 | 2023-03-30 | -26 | Terlambat | COMPLETED | 2023
W-504A | Panel Bailey | 2 | 12 SSR-EW | Pembangunan Jalan dan Jembatan Ruas Saketa – Dehepodo (MY) | PT. HIJRAH NUSATAMA | #VALUE! | 26998.236 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-02-09 | 2023-03-26 | 45 | 2023-03-20 | 2023-03-28 | -2 | Terlambat | COMPLETED | 2023
W-504B | Panel Bailey | 3 | 15 SSR-EW | Pembangunan Jalan dan Jembatan Ruas Saketa – Dehepodo (MY) | PT. HIJRAH NUSATAMA | #VALUE! | 50129.346 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-02-09 | 2023-03-26 | 45 | 2023-03-24 | 2023-03-28 | -2 | Terlambat | COMPLETED | 2023
W-504C | Panel Bailey | 1 | 21 SSR-EW | Pembangunan Jalan dan Jembatan Ruas Saketa – Dehepodo (MY) | PT. HIJRAH NUSATAMA | #VALUE! | 22417.19 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-02-09 | 2023-03-26 | 45 | 2023-03-07 | 2023-03-28 | -2 | Terlambat | COMPLETED | 2023
W-505 | Panel Bailey | 1 | KOMPONEN BAILEY | KOMPONEN BAILEY KAB.BOGOR | DINAS PUPR KAB. BOGOR | #VALUE! | 1453.8612 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | ASAP | ASAP | #VALUE! | 0 | 2023-02-06 | #VALUE! | #VALUE! | COMPLETED | 2023
W-506A | Panel Bailey | 2 | 24 DSR2-EW | Pembangunan Jalan dan Jembatan Ruas Gane Luar - Rangaranga (MY) | PT. ALBARKA ABDUL AZIZ | #VALUE! | 71754.1 | RFD | JON PUTRA | 90% | 1 unit sudah terkirim 1 unit Ready packing di CGI |  | 2023-04-03 | 2023-05-22 | 49 | 2023-05-09 | 2023-06-08 | -17 | Terlambat | WAKTU | 2023
W-506B | Panel Bailey | 2 | 21 DS-EW | Pembangunan Jalan dan Jembatan Ruas Gane Luar - Rangaranga (MY) | PT. ALBARKA ABDUL AZIZ | #VALUE! | 52532.916 | RFD | JON PUTRA | 90% | Ready packing di CGI |  | 2023-04-03 | 2023-05-22 | 49 | 2023-07-10 | 2024-12-14 | -572 | Terlambat | WAKTU | 2023
W-506C | Panel Bailey | 1 | 18 DSR1-EW | Pembangunan Jalan dan Jembatan Ruas Gane Luar - Rangaranga (MY) | PT. ALBARKA ABDUL AZIZ | #VALUE! | 25049.214 | RFD | JON PUTRA | 90% | Ready packing di CGI |  | 2023-04-03 | 2023-05-22 | 49 | 2023-05-16 | 2024-12-14 | -572 | Terlambat | WAKTU | 2023
W-506D | Panel Bailey | 1 | 18 DSR2-EW | Pembangunan Jalan dan Jembatan Ruas Gane Luar - Rangaranga (MY) | PT. ALBARKA ABDUL AZIZ | #VALUE! | 27225.018 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-04-03 | 2023-05-22 | 49 | 2023-04-28 | 2023-06-10 | -19 | Terlambat | COMPLETED | 2023
W-506E | Panel Bailey | 1 | 33 DSR2H*-EW (U120) | Pembangunan Jalan dan Jembatan Ruas Gane Luar - Rangaranga (MY) | PT. ALBARKA ABDUL AZIZ | #VALUE! | 51714.872 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-04-03 | 2023-05-22 | 49 | 2023-05-22 | 2023-06-07 | -16 | Terlambat | COMPLETED | 2023
W-507 | Panel Bailey | 3 | 30 DSR2-EW | Pengadaan Jembatan Ruas Jalan Tering - Ujoh Bilang - Long Bagun - Long Pahangai | DINAS PEKERJAAN UMUM, PENATAAN RUANG DAN PERUMAHAN RAKYAT PROVINSI KALIMANTAN TIMUR | #VALUE! | 133017.63 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-02-15 | 2023-03-30 | 43 | 2023-02-22 | 2023-04-13 | -14 | Terlambat | COMPLETED | 2023
W-511 | Girder | 1 | BG22 | Pembangunan Jembatan Sungai Mesat Indah Kota Lubuklinggau | CV. RAYHAN ADITYA | #VALUE! | 29180.4485 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-05-17 | 2023-07-03 | 47 | 2023-06-10 | 2023-08-10 | -38 | Terlambat | COMPLETED | 2023
W-512A | Panel Bailey | 1 | 42 DSR2-EW (U120) | Paket Pekerjaan Pembangunan Jembatan Sei. Paluq – Mahakam Hulu | PT. JALADARA SUMBER LESTARI | #VALUE! | 62875.614 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-03-21 | 2023-04-30 | 40 | 2023-04-07 | 2023-05-27 | -27 | Terlambat | COMPLETED | 2023
W-512B | Panel Bailey | 2 | 45 DSR2H**-EW (U120) | Paket Pekerjaan Pembangunan Jembatan Sei. Paluq – Mahakam Hulu | PT. JALADARA SUMBER LESTARI | #VALUE! | 141070.488 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-03-21 | 2023-04-30 | 40 | 2023-06-13 | 2023-07-04 | -65 | Terlambat | COMPLETED | 2023
W-512C | BEAM TRESTLE | 1 | TRESTLE BEAM | Paket Pekerjaan Pembangunan Jembatan Sei. Paluq – Mahakam Hulu | PT. JALADARA SUMBER LESTARI | #VALUE! | 4164.234 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-03-21 | 2023-04-30 | 40 | 0 | 2023-07-04 | -65 | Terlambat | COMPLETED | 2023
W-513 | Panel Bailey | 1 | 30 DSR2-EW | Pengadaan Jembatan Rangka Baja Panel Darurat | Dinas Pekerjaan Umum, Penataan Ruang, Perumahan dan Kawasan Permukiman Provinsi Gorontalo | #VALUE! | 44339.21 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-04-14 | 2023-05-14 | 30 | 2023-04-29 | 2023-05-15 | -1 | Terlambat | COMPLETED | 2023
W-514 | Girder | 1 | CG30 | Pembangunan Jembatan Muara Danau | CV. BROTHER’S MONTY | #VALUE! | 32415.4597 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-04-10 | 2023-05-10 | 30 | 2023-04-12 | 2023-04-13 | 27 | FALSE | COMPLETED | 2023
W-515 | Panel Bailey | 1 | KOMPONEN BAILEY | Lanjutan Pembangunan Jembatan Ranto Panyang | DINAS PEKERJAAN UMUM DAN PENATAAN RUANG ACEH JAYA | #VALUE! | 3482.36 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-04-27 | 2023-05-21 | 24 | 0 | 2024-12-14 | -573 | Terlambat | COMPLETED | 2023
W-516A | Panel Bailey | 1 | 36 DSR2-EW | Pengadaan Panel Bailey JATIM | DINAS PUPR PROV. JATIM | #VALUE! | 53793.21 | COMPLETED | YUSUF | 100% | N/A |  | 2023-04-10 | 2023-05-10 | 30 | 2023-05-26 | 2024-12-14 | -584 | Terlambat | COMPLETED | 2023
W-516B | Panel Bailey | 2 | 30 DSR2-EW | Pengadaan Panel Bailey JATIM | DINAS PUPR PROV. JATIM | #VALUE! | 88678.42 | COMPLETED | YUSUF | 100% | N/A |  | 2023-04-10 | 2023-05-10 | 30 | 2023-05-31 | 2024-12-14 | -584 | Terlambat | COMPLETED | 2023
W-516C | Panel Bailey | 1 | 45 TSR2 - EW | Pengadaan Panel Bailey JATIM | DINAS PUPR PROV. JATIM | #VALUE! | 81510.536 | COMPLETED | YUSUF | 100% | N/A |  | 2023-04-10 | 2023-05-10 | 30 | 2023-07-27 | 2024-12-14 | -584 | Terlambat | COMPLETED | 2023
W-516D | RAMP Panel Bailey | 6 | RAMP PANEL BAILEY | Pengadaan Panel Bailey JATIM | DINAS PUPR PROV. JATIM | #VALUE! | 11561.544 | COMPLETED | YUSUF | 100% | N/A |  | 2023-04-10 | 2023-05-10 | 30 | 2023-07-27 | 2024-12-14 | -584 | Terlambat | COMPLETED | 2023
W-517 | Panel Bailey | 1 | 30 DSR2-EW | Pengadaan Panel Bailey JATIM | DINAS PUPR PROV. JATIM | #VALUE! | 44339.21 | COMPLETED | YUSUF | 100% | N/A |  | 2023-05-25 | 2023-07-05 | 41 | 2023-07-06 | 2024-12-14 | -528 | Terlambat | COMPLETED | 2023
W-518A | Panel Bailey | 2 | 21 SSR-EW | Pembangunan Jalan dan Jembatan Ruas Wai Ina - Malbufa (MY) | PT. PUTRA ANANDA | #VALUE! | 44834.38 | RFD | JON PUTRA | 90% | 1 UNIT RELEASE. 1 UNIT RFD% |  | 2023-05-25 | 2023-07-11 | 47 | 2023-06-15 | 2024-12-14 | -522 | Terlambat | WAKTU | 2023
W-518B | Panel Bailey | 1 | 24 SSR-EW | Pembangunan Jalan dan Jembatan Ruas Wai Ina - Malbufa (MY) | PT. PUTRA ANANDA | #VALUE! | 25436.974 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-05-25 | 2023-07-11 | 47 | 2023-06-26 | 2024-12-14 | -522 | Terlambat | COMPLETED | 2023
W-518C | Panel Bailey | 1 | 27 DSR2-EW | Pembangunan Jalan dan Jembatan Ruas Wai Ina - Malbufa (MY) | PT. PUTRA ANANDA | #VALUE! | 40050.05 | RFD | JON PUTRA | 90% | Ready packing di CGI |  | 2023-05-25 | 2023-07-11 | 47 | 2023-07-01 | 2024-12-14 | -522 | Terlambat | WAKTU | 2023
W-519 | Panel Bailey | 1 | 39 DSR2H**-EW | Paket Pembangunan Jalan dan Jembatan Ruas Ibu Kedi (MY) | PT. Hapsari Nusantara Gemilang | #VALUE! | 62589.2273 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-08-09 | 2023-08-10 | 1 | 2023-08-24 | 2024-12-14 | -492 | Terlambat | COMPLETED | 2023
W-520A | Girder Spesial | 1 | GD14 | GIRDER KARYAMAS | GIRDER KARYAMAS | #VALUE! | 9075.5536 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-05-26 | 2023-08-11 | 77 | 2023-08-10 | 2024-12-14 | -491 | Terlambat | COMPLETED | 2023
W-520B | Girder Spesial | 5 | GD16 | GIRDER KARYAMAS | GIRDER KARYAMAS | #VALUE! | 54983.898 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-05-26 | 2023-08-11 | 77 | 2023-08-10 | 2024-12-14 | -491 | Terlambat | COMPLETED | 2023
W-520C | Girder Spesial | 3 | GD18 | GIRDER KARYAMAS | GIRDER KARYAMAS | #VALUE! | 38275.0878 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-05-26 | 2023-08-11 | 77 | 2023-08-10 | 2024-12-14 | -491 | Terlambat | COMPLETED | 2023
W-520D | Girder Spesial | 1 | GD20 | GIRDER KARYAMAS | GIRDER KARYAMAS | #VALUE! | 15456.9756 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-05-26 | 2023-08-11 | 77 | 2023-08-10 | 2024-12-14 | -491 | Terlambat | COMPLETED | 2023
W-521 | Girder | 1 | BG25 | Pembangunan Jembatan Jl. Antara Desa Putri Sembilan, Kecamatan Rupat Utara | CV. PERMATA LINGGO JAYA | #VALUE! | 34174.3084 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-06-06 | 2023-07-23 | 47 | 2023-07-14 | 2024-12-14 | -510 | Terlambat | COMPLETED | 2023
W-522 | Truss Modullar | 1 | KOMPONEN STRINGGER | PROYEK MANADO | TBA | #VALUE! | 11675.6 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-06-08 | 2023-07-10 | 32 | 2023-07-06 | 2024-12-14 | -523 | Terlambat | COMPLETED | 2023
W-523 | Girder | 1 | BG25 | PEMBAGUNAN JALAN DAN JEMBATAN RUAS WASILE-LABI-LABI (MY) | PT. PANCONA KATARABUMI | #VALUE! | 29572.0964 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-06-09 | 2023-07-26 | 47 | 2023-07-18 | 2024-12-14 | -507 | Terlambat | COMPLETED | 2023
W-524 | WELDED BEAM | 1 | WB BEAM | XXXX | CV. SETU KANAKA | XXX | 3854.33 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-06-07 | 2023-06-22 | 15 | 0 | 2024-12-14 | -541 | Terlambat | COMPLETED | 2023
W-525 | Girder | 1 | BG30 | Pembangunan Jembatan Mersam, Kab. Batanghari | CV. CITRA DWI PRATAMA | #VALUE! | 64277.9259 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-06-09 | 2023-07-29 | 50 | 2023-08-14 | 2024-12-14 | -504 | Terlambat | COMPLETED | 2023
W-526 | Girder | 1 | CG30 | PEMBAGUNAN REKONSTRUKSI JEMBATAN PINJAUAN KECAMATAN SUNGAI LIMAU | CV. KARYA MENTAWAI | #VALUE! | 34214.7931 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-06-12 | 2023-07-29 | 47 | 2023-08-11 | 2024-12-14 | -504 | Terlambat | COMPLETED | 2023
W-527 | Girder | 1 | BG35 | Penggantian Jembatan Sungai Pering (K.105), Kecamatan BTS Ulu | CV. DAYANG | #VALUE! | 68400.2952 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-06-14 | 2023-08-03 | 50 | 2023-07-29 | 2024-12-14 | -499 | Terlambat | COMPLETED | 2023
W-528 | Girder | 1 | BG20 | Penggantian Jembatan Air Pelai, Kecamatan Muara Lakitan | CV. DAYANG | #VALUE! | 25519.3032 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-06-14 | 2023-08-10 | 57 | 2023-08-16 | 2024-12-14 | -492 | Terlambat | COMPLETED | 2023
W-529 | Truss Modullar | 2 | RB50 | Pembangunan Jembatan Batang Jujuan CS (Lanjutan), Kab. Solok Selatan | PT. KEMUNING YONA PRATAMA | #VALUE! | 191888.7568 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-06-19 | 2023-08-28 | 70 | 2023-08-23 | 2024-12-14 | -474 | Terlambat | COMPLETED | 2023
W-530 | Jembatan Gantung | 1 | JG154 | Pembangunan Jembatan Gantung Multifungsi Sungai Musi Desa Pelawe | CV. DAYANG | MUSI RAWAS | 44161.22 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-08-02 | 2023-09-17 | 46 | 0 | 2024-12-14 | -454 | Terlambat | COMPLETED | 2023
W-531 | Girder | 1 | CG15_6 Line | Preservasi Jalan Dalam Kota Balikpapan | PT. NUSA BHAKTI ABADI | #VALUE! | 19480.0286 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-06-19 | 2023-10-27 | 130 | 2023-08-02 | 2024-12-14 | -414 | Terlambat | COMPLETED | 2023
W-532 | Girder | 1 | BG30 | Pembangunan Jembatan Badong Ruas Jalan Kamolan - Klopoduwur Kec. Blora/ Banjarejo | CV. GRAHA SENTOSA | #VALUE! | 39989.3442 | COMPLETED | CHAKIM | 100% | N/A |  | 2023-06-26 | 2023-08-09 | 44 | 26/008/23 | 2024-12-14 | -493 | Terlambat | COMPLETED | 2023
W-532A | ORNAMEN PIPA | 1 | GB30-ARCH | Pembangunan Jembatan Badong Ruas Jalan Kamolan - Klopoduwur Kec. Blora/ Banjarejo | CV. GRAHA SENTOSA | #VALUE! | 6708.215 | COMPLETED | CHAKIM | 100% | N/A |  | 2023-06-26 | 2023-08-26 | 61 | 0 | 2024-12-14 | -476 | Terlambat | COMPLETED | 2023
W-533 | Jembatan Gantung | 1 | JG120 | LANJUTAN JEMBATAN GANTUNG KALUKUBULA (STRUKTUR ATAS JEMBATAN), | CV. MULIA RAYA | #VALUE! | 30913.5586 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 26/07/2023 | 2023-06-09 | -47 | 0 | 2024-12-14 | -554 | Terlambat | COMPLETED | 2023
W-534 | Girder | 1 | AG20 | PENGGANTIAN JEMBATAN BOILAN II | CV. MULIA RAYA | #VALUE! | 25465.0419 | COMPLETED | CHAKIM | 100% | N/A |  | 26/07/2023 | 2023-06-09 | -47 | 2023-09-04 | 2024-12-14 | -554 | Terlambat | COMPLETED | 2023
W-535 | Jembatan Gantung | 1 | JG80 | Pembangunan Jembatan Gantung Desa Gandring | CV. BATARA WALET | #VALUE! | 22831.6388 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-02-08 | 23/09/2023 | 227 | 0 | 2024-12-14 | -448 | Terlambat | COMPLETED | 2023
W-536 | Girder | 1 | CG30 | Pembangunan Jembatan Ba’basaratu | CV. FAJAR ASIA | #VALUE! | 34172.5531 | COMPLETED | CHAKIM | 100% | N/A |  | 2023-07-13 | 2023-08-26 | 44 | 2023-08-26 | 2024-12-14 | -476 | Terlambat | COMPLETED | 2023
W-537 | Panel Bailey | 3 | 30 SSR-EW | PEMBANGUNAN JEMBATAN SUKAMAJU (PENGADAAN RANGKA BAILEY) | DINAS BINA MARGA DAN PENATAAN RUANG PROVINSI SULAWESI TENGAH | #VALUE! | 94327.386 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-07-06 | 2023-08-09 | 34 | 2023-08-04 | 2024-12-14 | -493 | Terlambat | COMPLETED | 2023
W-538 | Truss Modullar | 1 | RB60 | Pembangunan Jembatan Cikanyayan | CV. A G E M | #VALUE! | 142183.7838 | COMPLETED | YUSUF | 100% | N/A |  | 21/07/2023 | 2023-09-09 | 50 | 0 | 2024-12-14 | -462 | Terlambat | COMPLETED | 2023
W-539 | SPECER MRT | 1 | SPECER MRT | SPACER - MRT MONAS | PT. NIPPON STEEL TRADING INDONESIA | #VALUE! | 5737.32 | COMPLETED | FIKRI ARAFAH | 100% | N/A |  | 2023-07-10 | 2023-07-26 | 16 | 0 | 2024-12-14 | -507 | Terlambat | COMPLETED | 2023
W-540 | SUPPORT BEAM | 1 | SB35 | REHABILITASI JEMBATAN RUAS BTS KOTA NABIRE-WANGGAR | CV. NAHASE PUTRA | NABIRE | 20784.694 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-07-12 | 2023-08-16 | 35 | 2023-09-01 | 2024-12-14 | -486 | Terlambat | COMPLETED | 2023
W-541 | Girder | 1 | CG12 | Pembangunan Jembatan Jalan Sentra Cabe Hiyung, Kab. Tapin, Kalimantan Selatan | CV. AMANAH RAYA | KALIMANTAN SELATAN | 10589.4137 | COMPLETED | CHAKIM | 100% | N/A |  | 18/07/2023 | 31/08/2023 | 44 | 2023-08-30 | 2024-12-14 | -471 | Terlambat | COMPLETED | 2023
W-542 | Jembatan Gantung | 1 | JG360_TAHAP I | Pembangunan Jembatan Gantung Sikan – Tumpung Laung, Kabupaten Barito Utara, Kalimantan Tengah (TAHAP 1) | PT. AGRABUDI KARYAMARGA | KALIMANTAN TENGAH | 330142.696 | ON GOING | ATADIWIRA KANAN | 100% | N/A |  | 18/07/2023 | 2023-08-09 | 22 |  |  | 45147 | Sesuai Schedule | PRIORITAS | 2023
W-543 | Girder | 1 | GB30 | Paket Penggantian Jembatan Buti Ruas (Tabulo-Karangetan) | CV. AYU JAYA | #VALUE! | 42160.0246 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-08-11 | 2023-09-24 | 44 | 0 | 2024-12-14 | -447 | Terlambat | COMPLETED | 2023
W-544 | Panel Bailey | 2 | 9 SSR-EW | Paket Pembangunan Jalan dan Jembatan Ruas Malifut – Ngoali -Tolabit, Kab. Halmahera Utara | PT. Eltis Anugerah Sejati | MALUKU UTARA | 20651.148 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-08-18 | 2023-09-01 | 14 | 2023-08-30 | 2024-12-14 | -470 | Terlambat | COMPLETED | 2023
W-545 | Jembatan Gantung | 1 | JG150 | PENANGANAN JEMBATAN KALIREGOYO | PT DWI MULYO LESTARI | REGOYO | 30198.0538 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-04-08 | 2023-06-09 | 62 | 0 | 2024-12-14 | -554 | Terlambat | COMPLETED | 2023
W-546 | Panel Bailey | 1 | 39 DSR2H**-EW | PPK PENANGANAN DARURAT KERUSAKAN JALAN DAN JEMBATAN DINAS PEKERJAAN UMUMBINA MARGA PROV. JAWA TIMUR | CV. Dwi Tunggal Sejati | REGOYO | 61467.6273 | COMPLETED | YUSUF | 100% | N/A |  | 2023-08-13 | 2023-08-14 | 1 | 0 | 2024-12-14 | -488 | Terlambat | COMPLETED | 2023
W-547 | Panel Bailey | 3 | 6 SSR-SW | Paket Pembangunan Jembatan Bailey Wai Kaloa II Ruas SP. Lintas Seram - Kaloa | CV. CAHAYA PRATAMA | MALUKU TENGAH | 21879.15 | COMPLETED | JON PUTRA | 100% | N/A | [6 empty] | 0 | On schedule | COMPLETED | 2023
W-548 | PLATE LRB | 1 | LRB | LRB PLATES - BSD | PT. FREYSSINET TOTAL TECHNOLOGY | BSD | 2307.1734 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-08-21 | 2023-09-04 | 14 | 0 | 2024-12-14 | -467 | Terlambat | COMPLETED | 2023
W-549 | Truss Modullar | 1 | RB40 | Belanja Modal Rehabilitasi/ Rekonstruksi Pascabencana Jembatan Kususinofa | CV. NANILY SEJATI | MALUKU UTARA | 72876.4092 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-01-08 | 16/08/2023 | 220 | 0 | 2024-12-14 | -486 | Terlambat | COMPLETED | 2023
W-550 | Panel Bailey | 1 | 30 DSR2-EW | Paket Pembangunan Jalan Ruas Jalan Kaporo – Capalulu | PT. Duta Tunggal Jaya | MALUKU UTARA | 44339.21 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-08-02 | 2023-08-03 | 1 | 2023-08-02 | 2024-12-14 | -499 | Terlambat | COMPLETED | 2023
W-551 | Girder | 1 | AG40 | Pembangunan Jembatan Sungai Merah Kecamatan Mook Manaar Bulatn | PT. PERANCIS NUR | KUTAI BARAT | 123722.8476 | COMPLETED | YUSUF | 100% | N/A | 128101.5324 | 2023-08-07 | 2023-09-22 | 46 | 0 | 2024-12-14 | -449 | Terlambat | COMPLETED | 2023
W-552 | JPO | 1 | JPO-48 | pembangunan Jembatan Jatimulya | CV. DAHLIA INDAH | #VALUE! | 23903.115 | COMPLETED | YUSUF | 100% | N/A | 25783.0386 | 2023-04-08 | 24/09/2023 | 169 | 0 | 2024-12-14 | -447 | Terlambat | COMPLETED | 2023
W-553 | Panel Bailey | 3 | 12 SSR-EW | PAKET BELANJA MODAL ALAT BANTU LAINNYA | DINAS PUPR KAB. BOJONEGORO | BOJONEGORO | 34890.852 | COMPLETED | JON PUTRA | 100% | N/A | 38928.5064 | 2023-08-10 | 2023-08-22 | 12 | 2023-08-12 | 2024-12-14 | -480 | Terlambat | COMPLETED | 2023
W-554 | STRUKTUR PERKUATAN | 1 | PERKUATAN | PERKUATAN JEMBATAN LEUWIRANJI | DINAS PUPR KAB BOGOR | KABUPATEN BOGOR | 6951.4169 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-08-07 | 2023-08-31 | 24 | 0 | 2024-12-14 | -471 | Terlambat | COMPLETED | 2023
W-555 | Jembatan Gantung | 1 | JG40_ASIMETRIS | Pembangunan Jembatan Angsana | CV. ALVIZ PRATAMA | SERANG | 16494.38 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-09-18 | 2023-10-27 | 39 |  |  | 45226 | Sesuai Schedule | COMPLETED | 2023
W-556 | Girder | 1 | CG12 | Paket Perbaikan Jembatan Desa Budi Mulya, Kab. Tapin, Kalimantan Selatan | CV. AMANAH RAYA | KALIMANTAN SELATAN | 8639.5305 | COMPLETED | CHAKIM | 100% | N/A | 11984.77 | 2023-08-25 | 2023-09-24 | 30 | 0 | 2024-12-14 | -447 | Terlambat | COMPLETED | 2023
W-557 | Panel Bailey | 1 | Ex. England | KOMPONEN BAILEY EX - ENGLAND | KEMENTERIAN PEKERJAAN UMUM DAN PERUMAHAN RAKYAT PELAKSANAAN JALAN NASIONAL WILAYAH I PROVINSI SUMBAR | sumatera barat | 103.3201 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-08-15 | 2023-08-31 | 16 | 0 | 2024-12-14 | -471 | Terlambat | COMPLETED | 2023
W-558 | Truss Modullar | 1 | RB30 | Paket Pembangunan Jembatan Pada Ruas Kheli - Sp. Wulur Tahap II | CV. CAHAYA KEHIDUPAN SEJAHTERA | MALUKU BARAT | 52321.6543 | COMPLETED | JON PUTRA | 100% | N/A | 56067.6137 | 2023-08-18 | 2023-10-04 | 47 | 0 | 2024-12-14 | -437 | Terlambat | COMPLETED | 2023
W-559 | Jembatan Gantung | 1 | JG100P | Pembangunan Jembatan Gantung Jila 80 M | PT. LAMBU RAYA UTAMA | PAPUA | 37054.8846 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-09-25 | 2023-10-27 | 32 |  |  | 45226 | Sesuai Schedule | COMPLETED | 2023
W-560A | Jembatan Pendekat | 2 | SPAN 11.87 M | Paket Pembangunan Jembatan Gantung Kelampai | CV. PANEN CIPTA MANGGALA | KALIMNATAN BARAT | 5502.3032 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-10-20 | 2023-11-30 | 41 |  |  | 45260 | Sesuai Schedule | COMPLETED | 2023
W-560B | Jembatan Pendekat | 1 | SPAN 14.20 M | Paket Pembangunan Jembatan Gantung Kelampai | CV. PANEN CIPTA MANGGALA | KALIMNATAN BARAT | 5255.8646 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-10-20 | 2023-11-30 | 41 |  |  | 45260 | Sesuai Schedule | COMPLETED | 2023
W-560C | Jembatan Pendekat | 1 | SPAN 22.82 M | Paket Pembangunan Jembatan Gantung Kelampai | CV. PANEN CIPTA MANGGALA | KALIMNATAN BARAT | 15732.922 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-10-20 | 2023-11-30 | 41 |  |  | 45260 | Sesuai Schedule | COMPLETED | 2023
W-561 | TOWER | 1 | TWR-H36 | TOWER H36 - TRIPOLE KETAPANG | PT. ANTARIKSA INTI | KALIMANTAN BARAT | 12082.8918 | COMPLETED | JON PUTRA | 100% | N/A | 12906.8725 | 2023-08-23 | 2023-08-29 | 6 | 0 | 2024-12-14 | -473 | Terlambat | COMPLETED | 2023
W-562 | Panel Bailey | 1 | 24 DSR2-EW | Paket Peningkatan Jalan Arbais - Webro - Waim - Karfasia (3,80 Km) | CV PUTRA ADIWIPI | PAPUA | 36276.538 | COMPLETED | JON PUTRA | 100% | N/A | 39918.6962 | 2023-08-28 | 2023-09-24 | 27 | 2023-09-04 | 2024-12-14 | -447 | Terlambat | COMPLETED | 2023
W-563 | Girder | 1 | CG12 | Paket Pembangunan Jembatan Buah Seri Kec. Blangjerango, Kab Gayo Lues | CV. PRIMA KONSTRUKSI | ACEH JAYA | 8728.8064 | COMPLETED | ATADIWIRA KANAN | 100% | N/A | 10190.9487 | 2023-09-13 | 2023-10-22 | 39 | 2023-09-13 | 2023-10-20 | 2 | FALSE | COMPLETED | 2023
W-564 | Truss Modullar | 1 | RB50 | Pembangunan Bangunan Atas Jembatan Rangka Baja Lubuk Belimbing I – Lubuk Belimbing II, Kecamatan Sindang Beliti Ilir (BM2) | CV. FINSA BERSAUDARA | BENGKULU | 104003.1182 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-09-25 | 2023-11-07 | 43 |  |  | 45237 | Sesuai Schedule | COMPLETED | 2023
W-565 | Panel Bailey | 1 | 36 DSR2-EW | Pengadaan Jembatan Darurat Bailey | DINAS PERUMAHAN DAN PERMUKIMAN KABUPATEN JOMBANG | JOMBANG | 53793.21 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-09-13 | 2023-09-30 | 17 |  |  | 45199 | Sesuai Schedule | COMPLETED | 2023
W-565A | RAMP Panel Bailey | 2 | RAMP PANEL BAILEY | Pengadaan Jembatan Darurat Bailey | DINAS PERUMAHAN DAN PERMUKIMAN KABUPATEN JOMBANG | JOMBANG | 3795.92 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-09-13 | 2023-09-30 | 17 |  |  | 45199 | Sesuai Schedule | COMPLETED | 2023
W-566 | Girder | 1 | AG18.8 | Penggantian Jembatan Sei. Apung | CV. DELIMA | SUMATERA UTARA | 42795.4413 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-09-19 | 2023-10-28 | 39 |  |  | 45227 | Sesuai Schedule | COMPLETED | 2023
W-567 | STRUKTUR ATAP | 1 | ATAP ASRAMA HAJI | Pembangunan Gedung Asrama dan Aula pada Asrama Haji Transit Ternate | PT. ALBARKA ABDUL AZIZ | TERNATE | 15052.733 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-09-19 | 2023-11-11 | 53 |  |  | 45241 | Sesuai Schedule | COMPLETED | 2023
W-568A | Panel Bailey | 1 | 18 SSR - EW (LANTAI KAYU) | Paket Pembangunan Jembatan Bailey | PT. BERKAT SAMMY GUINERA | PAPUA | 14531.93 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-09-27 | 2023-10-17 | 20 |  |  | 45216 | Sesuai Schedule | COMPLETED | 2023
W-568B | Panel Bailey | 1 | 24 SSR - EW (LANTAI KAYU) | Paket Pembangunan Jembatan Bailey | PT. BERKAT SAMMY GUINERA | PAPUA | 18952.19 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-09-27 | 2023-10-17 | 20 |  |  | 45216 | Sesuai Schedule | COMPLETED | 2023
W-569 | Truss Modullar | 1 | RB40 | Paket Pembangunan Jembatan Kumur - Bebar Tahap II | CV. CAKRAWALA INDAH | MALUKU BARAT DAYA | 67567.7924 | COMPLETED | JON PUTRA | 100% | N/A | 73411.09 | 2023-10-02 | 2023-11-09 | 38 |  |  | 45239 | Sesuai Schedule | COMPLETED | 2023
W-570 | Truss Modullar | 1 | RB30 | Pembangunan Jembatan Dalka Tahap II | CV. CONSTRUEREN OVERTROEVEN | MALUKU BARAT DAYA | 52321.6543 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-10-02 | 2023-11-09 | 38 |  |  | 45239 | Sesuai Schedule | COMPLETED | 2023
W-571 | Panel Bailey | 1 | 30 DSR2-EW | Pengadaan Alat Besar Jembatan Bailey | DINAS PEKERJAAN UMUM DAN PENATAAN RUANG KAB. MUSI BANYUASIN | MUSI BANYUASIN | 44339.21 | COMPLETED | JON PUTRA | 100% | N/A | [6 empty] | 0 | On schedule | COMPLETED | 2023
W-572 | Panel Bailey | 1 | 21 SSR-EW | Paket Peningkatan Ruas Jalan Dormena - Ormu | PT. INAI BONBO | PAPUA | 22682.47 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-10-18 | 2023-10-25 | 7 |  |  | 45224 | Sesuai Schedule | COMPLETED | 2023
W-573 | Truss Modullar | 1 | RB40 | Paket Pekerjaan PENGGANTIAN JEMBATAN SAGITSI, CS pada PELAKSANAAN JALAN NASIONAL WILAYAH I PROVINSI SUMBAR | AMAR - SEJAHTERA KSO | #VALUE! | 72876.4092 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-03-20 | 2023-04-04 | 15 | 2023-10-24 | 2023-12-03 | -243 | Terlambat | COMPLETED | 2023
W-574 | Truss Modullar | 1 | RC45+15 | Penggantian Jembatan Gantung | PT. Karya Anugrah Sejati | DEPOK | 45602.9137 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-11-07 | 2023-12-08 |  |  |  | 45268 | Sesuai Schedule | COMPLETED | 2023
W-575 | Girder | 1 | C43 | Penggantian Jembatan Kp. Parung Serab | CV. AGUNG JAYA PERSADA | DEPOK | 13623.514 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-11-01 | 2023-12-11 |  |  |  | 45271 | Sesuai Schedule | COMPLETED | 2023
W-576A | Panel Bailey | 1 | 18 SSR - EW | Pembangunan Jalan dan Jembatan Ruas Maba - Sagea (MY) | PT. SEDERHANA JAYA ABADI | MALUKU UTARA | 19372.446 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-11-01 | 2023-11-10 |  |  |  | 45240 | Sesuai Schedule | COMPLETED | 2023
W-576B | Panel Bailey | 1 | 12 SSR-EW | Pembangunan Jalan dan Jembatan Ruas Maba - Sagea (MY) | PT. SEDERHANA JAYA ABADI | MALUKU UTARA | 11637.868 | COMPLETED | JON PUTRA | 100% | N/A |  | 2023-11-01 | 2023-11-10 |  |  |  | 45240 | Sesuai Schedule | COMPLETED | 2023
W-577 | Girder | 1 | AG20 | PENGGANTIAN JEMBATAN AKSES GOA BATU - TAPAK RAJA, KABUPATEN PENAJAM, PASER UTARA KALIMANTAN TIMUR | PT. HERANANDA SURYA PRATAMA | KALTIM | 24177.0809 | COMPLETED | ATADIWIRA KANAN | 100% | N/A |  | 2023-11-08 | 2023-12-06 |  |  |  | 45266 | Sesuai Schedule | COMPLETED | 2023
W-578 | KING POST | 1 | KP | PROJECT MRT CP202 (Sawah Besar) | PT. NIPPON STEEL TRADING INDONESIA | #VALUE! | 451165.015 | ON GOING | FIKRI ARAFAH | 10% | FINISH MATERIAL GRADE SS400 | [6 empty] | 0 | On schedule | PRIORITAS | 2023
W-579 | Panel Bailey | 2 | 30 DSR2-EW | Pengadaan Jembatan Rangka Baja Panel Darurat | DINAS PEKERJAAN UMUM BINA MARGA PROPINSI JAWA TIMUR | #VALUE! | 90725.14 | COMPLETED | YUSUF | 100% | N/A |  | 2023-11-14 | 2023-11-30 |  |  |  | 45260 | Sesuai Schedule | COMPLETED | 2023
W-579A | Panel Bailey | 2 | 36 DSR2-EW | Pengadaan Jembatan Rangka Baja Panel Darurat | DINAS PEKERJAAN UMUM BINA MARGA PROPINSI JAWA TIMUR | #VALUE! | 107586.42 | COMPLETED | YUSUF | 100% | N/A | [6 empty] | 0 | On schedule | COMPLETED | 2023
W-580 | Panel Bailey | 2 | 39 DSR2H**-EW | Pengadaan Jembatan Rangka Baja Panel Darurat | DINAS PEKERJAAN UMUM BINA MARGA PROPINSI JAWA TIMUR | #VALUE! | 122935.2546 | COMPLETED | YUSUF | 100% | KEKURANGAN WCRH |  | 2023-11-14 | 2023-11-30 |  |  |  | 45260 | Sesuai Schedule | COMPLETED | 2023
W-581 | Komponen Jembatan | 1 | WB BEAM | N/A | CV. MAKKURTUK DONGAN | SUMATERA UTARA | 26360.78 | COMPLETED | ATADIWIRA KANAN | 100% | [7 empty] | 0 | On schedule | COMPLETED | 2023
W-582 | Komponen Jembatan | 1 | WB BEAM | N/A | PT. VITA ENGINEER CONTRACTOR | PAPUA | 2216.0074 | COMPLETED | ATADIWIRA KANAN | 100% | [7 empty] | 0 | On schedule | COMPLETED | 2023
W-585 | Jembatan Gantung | 1 | Komponen JG152 | Kegiatan Pembangunan Jembatan Gantung Lae Renun, Kabupaten Dairi, Provinsi Sumatera Utara | CV. MANDALA KARYA | SUMATERA UTARA | 57494 | COMPLETED | ATADIWIRA KANAN | 100% | [7 empty] | 0 | On schedule | COMPLETED | 2023
7503159.4498
7653222.6388
805.6%
[15 empty] | -29 | -29
-22
-386
-14
-10
-14
-21
-48
[8 empty] | 2529.31 | [6 empty] | -49
|  |  | W-489A | [11 empty] | -49
|  |  | W-489B | [11 empty] | -30
|  |  | W-493 | [11 empty] | -41
|  |  | W-494 | [11 empty] | -30
|  |  | W-495A-02 | [11 empty] | -45
|  |  | W-496-A | [11 empty] | -45
|  |  | W-496-B | [11 empty] | -45
|  |  | W-498 | [11 empty] | #VALUE!
|  |  | W-499 | [11 empty] | -49
|  |  | W-500 | [11 empty] | -49
|  |  | W-501 | [11 empty] | -49
|  |  | W-502 | [11 empty] | -49
|  |  | W-503 | [11 empty] | -49
|  |  | W-504A | [11 empty] | -43
|  |  | W-504B | [11 empty] | -15
|  |  | W-504C | [11 empty] | -47
|  |  | W-505 | [11 empty] | -40
|  |  | W-506A | [11 empty] | -40
|  |  | W-506B | [11 empty] | -40
|  |  | W-506C | [11 empty] | -30
|  |  | W-506D | [11 empty] | -30
|  |  | W-506E | [11 empty] | -24
|  |  | W-507 | [11 empty] | -30
|  |  | W-509 | [11 empty] | -30
|  |  | W-511 | [11 empty] | -30
|  |  | W-512A | [11 empty] | -30
|  |  | W-512B | [11 empty] | -41
|  |  | W-512C | [11 empty] | -47
|  |  | W-513 | [11 empty] | -47
|  |  | W-514 | [11 empty] | -47
|  |  | W-515 | [11 empty] | -1
|  |  | W-516A | [11 empty] | -77
|  |  | W-516B | [11 empty] | -77
|  |  | W-516C | [11 empty] | -77
|  |  | W-516D | [11 empty] | -77
|  |  | W-517 | [11 empty] | -47
|  |  | W-518A | [11 empty] | -32
|  |  | W-518B | [11 empty] | -47
|  |  | W-518C | [11 empty] | -15
|  |  | W-519 | [11 empty] | -50
|  |  | W-520A | [11 empty] | -47
|  |  | W-520B | [11 empty] | -50
|  |  | W-520C | [11 empty] | -57
|  |  | W-520D | [11 empty] | -70
|  |  | W-521 | [11 empty] | -46
|  |  | W-522 | [11 empty] | -130
|  |  | W-523 | [11 empty] | -44
|  |  | W-524 | [11 empty] | -61
|  |  | W-525 | [11 empty] | 47
|  |  | W-526 | [11 empty] | 47
|  |  | W-527 | [11 empty] | -227
|  |  | W-528 | [11 empty] | -44
|  |  | W-529 | [11 empty] | -34
|  |  | W-530 | [11 empty] | -50
|  |  | W-531 | [11 empty] | -16
|  |  | W-532 | [11 empty] | -35
|  |  | W-532A | [11 empty] | -44
|  |  | W-533 | [11 empty] | -22
|  |  | W-534 | [11 empty] | -22
|  |  | W-535 | [11 empty] | -22
|  |  | W-536 | [11 empty] | -44
|  |  | W-537 | [11 empty] | -14
|  |  | W-538 | [11 empty] | -62
|  |  | W-539 | [11 empty] | -1
|  |  | W-540 | [11 empty] | -14
|  |  | W-541 | [11 empty] | -220
|  |  | W-542#1 | [11 empty] | -1
|  |  | W-542#2 | [11 empty] | -46
|  |  | W-542#3 | [11 empty] | -169
|  |  | W-543 | [11 empty] | -12
|  |  | W-544 | [11 empty] | -24
|  |  | W-545 | [11 empty] | -39
|  |  | W-546 | [11 empty] | -30
|  |  | W-548 | [11 empty] | -16
|  |  | W-549 | [11 empty] | #VALUE!
|  |  | W-550 | [11 empty] | -32
|  |  | W-551 | [11 empty] | -6
|  |  | W-552 | [11 empty] | -27
|  |  | W-553 | [11 empty] | -39
|  |  | W-554 | [11 empty] | -43
|  |  | W-555 | [11 empty] | -17
|  |  | W-556 | [11 empty] | -17
|  |  | W-557 | [11 empty] | -39
|  |  | W-558 | [11 empty] | -53
|  |  | W-559 | [11 empty] | -20
|  |  | W-561 | [11 empty] | -20
|  |  | W-562 | [11 empty] | -38
|  |  | W-563 | [11 empty] | -38
W-564
W-565
W-565A
W-566
W-567
W-568A
W-568B
W-569
W-570

## DATA FABRIKASI
No.PON | Vendor | Type Struktur | Marking Struktur | Berat Fabrikasi | Date Release SD | Date Start PON | Date Finish PON | Qty | SUM Total | Date Finish Aktual | Progress (%) | ISSUE | STATUS | Keterangan
STKJ18 | DHJ | Panel Bailey STOCK | KOMPONEN BAILEY | 189231.53 | 2023-02-06 | 2023-02-06 | 2023-03-29 | 1 | 189231.53
STKJ19 | DHJ | Panel Bailey STOCK | KOMPONEN BAILEY | 155984.84 | STKJ19 |  |  | 1 | 155984.84
STKJ20 | DHJ | Panel Bailey STOCK | KOMPONEN BAILEY | 285981.34 | STKJ20 |  |  | 1 | 285981.34
STKJ21 | DHJ | Panel Bailey STOCK | KOMPONEN BAILEY | 174798.16 | STKJ21 | 2023-04-18 |  | 1 | 174798.16
STKJ22 | DHJ | Panel Bailey STOCK | KOMPONEN BAILEY | 313247.54 | STKJ22 |  |  | 1 | 313247.54
STKJ23 | DHJ | Panel Bailey STOCK | KOMPONEN BAILEY | 397430.23 | 2023-07-12 |  |  | 1 | 397430.23
STKJ24 | DHJ | Panel Bailey STOCK | KOMPONEN BAILEY | 197176.7795 |  |  |  | 1 | 197176.7795
STOCK2022 | DHJ | Panel Bailey STOCK | KOMPONEN BAILEY | 268007.3663 |  |  | 2022-01-16 | 1 | 268007.3663
W-489A | DHJ | PLATE LRB | BASEPLATE FOR LRB | 79206.4578 |  |  |  | 1 | 79206.4578
W-489B | DHJ | PLATE LRB | BASEPLATE FOR LRB | 48589.616 |  |  |  | 1 | 48589.616
W-493 | DHJ | PIPE RACK | PIPE RACK | 14268.66 | 2023-01-13 | 2022-12-02 | 2023-12-23 | 1 | 14268.66
W-494 | DHJ | FENCING SHELTER & STAIRCASES | FENCING | 3450.457 |  |  |  | 1 | 3450.457
W-495A-02 | DHJ | PLATE LRB | BASEPLATE FOR LRB | 875.3339 | 2023-02-10 | 2023-02-07 | 2023-02-17 | 1 | 875.3339 |  |  |  |  | LRB1-PCK & LRB2-PCK
W-496-A | DHJ | PLATE LRB | BASEPLATE FOR LRB | 3090.48 | 2023-02-16 | 2023-02-13 | 2023-02-27 | 1 | 3090.48
W-496-B | DHJ | PLATE LRB | BASEPLATE FOR LRB | 18126.9838 | 2023-03-20 | 2023-03-16 | 2023-04-06 | 1 | 18126.9838
W-498 | DHJ | Jembatan Gantung | JG105 - PIPA | 11634.56 | 2023-02-07 | 2023-01-31 | 2023-03-20 | 1 | 11634.56
W-498 | DHJ | Jembatan Gantung | JG105 - PIPA | 106.32 | 2023-02-13 | 2023-01-31 | 2023-03-20 | 1 | 106.32 |  |  |  |  | Wire lock di supply oleh DHJ
W-499 | DHJ | Girder | AG30 | 45241.61 | 2023-01-13 | 2023-01-10 | 2023-02-21 | 1 | 45241.61 | 2023-02-07
W-500 | DHJ | Panel Bailey | 33M DSR2 - SS400 | 32746.12 | 2023-01-31 | 2023-01-11 | 2023-02-22 | 1 | 32746.12
W-501 | DHJ | Girder | AG20 | 22273.2 | 2023-01-16 | 2023-01-13 | 2023-02-07 | 1 | 22273.2
W-502 | DHJ | Girder | AG8 | 16166.62 | 2023-02-03 | 2023-02-03 | 2023-03-16 | 1 | 16166.62
W-503 | DHJ | Panel Bailey | 42 DSR2-EW + TRESTLE | 59752.43 | STKJ18 | STKJ18 | STKJ18 | 1 | 59752.43 |  |  |  |  | PANEL BAILEY 1X42 DSR2-EW (*HH*)
W-503 | DHJ | Panel Bailey | 42 DSR2-EW + TRESTLE | 4838.64 | 2023-02-09 | 2023-02-02 | 2023-03-04 | 1 | 4838.64 |  |  |  |  | Struktur Trestle
W-504A | DHJ | Panel Bailey | 12 SSR-EW | 13076.63 | STKJ18 | 2023-02-09 | 2023-03-26 | 2 | 26153.26
W-504B | DHJ | Panel Bailey | 15 SSR-EW | 16041.14 | STKJ18 | 2023-02-09 | 2023-03-26 | 3 | 48123.42
W-504C | DHJ | Panel Bailey | 21 SSR-EW | 21970.16 | STKJ18 | 2023-02-09 | 2023-03-26 | 1 | 21970.16
W-505 | DHJ | Panel Bailey | KOMPONEN BAILEY | 1406.4612 | STKJ18 | STKJ18 | STKJ18 | 1 | 1406.4612
W-506A | DHJ | Panel Bailey | 24 DSR2-EW | 34967.53 | STKJ20 | 2023-04-03 | 2023-05-22 | 2 | 69935.06
W-506B | DHJ | Panel Bailey | 21 DS-EW | 25837.54 | STKJ20 | 2023-04-03 | 2023-05-22 | 2 | 51675.08
W-506C | DHJ | Panel Bailey | 18 DSR1-EW | 24530.89 | STKJ20 | 2023-04-03 | 2023-05-22 | 1 | 24530.89
W-506D | DHJ | Panel Bailey | 18 DSR2-EW | 26673.07 | STKJ20 | 2023-04-03 | 2023-05-22 | 1 | 26673.07
W-506E | DHJ | Panel Bailey | 33 DSR2H*-EW (U120) | 50562.14 | STKJ20 | 2023-04-03 | 2023-05-22 | 1 | 50562.14
W-507 | DHJ | Panel Bailey | 30 DSR2-EW | 43261.99 | STKJ18 | STKJ18 | STKJ18 | 3 | 129785.97
W-511 | DHJ | Girder | BG22 | 27132.52 | 2023-05-19 | 2023-05-17 | 2023-07-03 | 1 | 27132.52
W-512A | DHJ | Panel Bailey | 42 DSR2-EW (U120) | 61912.55 | STKJ20 | 2023-03-21 | 2023-04-30 | 1 | 61912.55
W-512B | DHJ | Panel Bailey | 45 DSR2H**-EW (U120) | 68880.26 | STKJ20 | 2023-03-21 | 2023-04-30 | 2 | 137760.52
W-512C | DHJ | BEAM TRESTLE | TRESTLE BEAM | 3859.92 | 2023-04-05 | 2023-04-03 | 2023-05-22 | 1 | 3859.92 |  |  |  |  | Struktur Trestle
W-513 | DHJ | Panel Bailey | 30 DSR2-EW | 43261.99 | STKJ20 | 2023-04-14 | 2023-05-14 | 1 | 43261.99
W-514 | DHJ | Girder | CG30 | 30865.46 | 2023-04-11 | 2023-04-10 | 2023-05-10 | 1 | 30865.46 |  |  |  |  | Fabrikasi mengganti proyek W499 yang terpakai
W-515 | DHJ | Panel Bailey | KOMPONEN BAILEY | 3482.36 |  |  |  | 1 | 3482.36
W-516A | DHJ | Panel Bailey | 36 DSR2-EW | 52580.93 | STKJ21 |  |  | 1 | 52580.93
W-516B | DHJ | Panel Bailey | 30 DSR2-EW | 43261.99 | STKJ22 |  |  | 2 | 86523.98
W-516C | DHJ | Panel Bailey | 45 TSR2 - EW | 79238.13 | STKJ22 |  |  | 1 | 79238.13
W-516D | DHJ | RAMP Panel Bailey | RAMP PANEL BAILEY | 1897.96 |  | 2023-05-25 | 2023-07-05 | 6 | 11387.76
W-517 | DHJ | Panel Bailey | 30 DSR2-EW | 43261.99 | STKJ22 | 2023-05-25 | 2023-07-05 | 1 | 43261.99
W-518A | DHJ | Panel Bailey | 21 SSR-EW | 21970.16 | STKJ22 | 2023-05-25 | 2023-07-11 | 2 | 43940.32
W-518B | DHJ | Panel Bailey | 24 SSR-EW | 24934.67 | STKJ22 | 2023-05-25 | 2023-07-11 | 1 | 24934.67
W-518C | DHJ | Panel Bailey | 27 DSR2-EW | 39114.76 | STKJ22 | 2023-05-25 | 2023-07-11 | 1 | 39114.76
W-519 | DHJ | Panel Bailey | 39 DSR2H**-EW | 60185.5033 |  |  |  | 1 | 60185.5033
W-520A | DHJ | Girder Spesial | GD14 | 8841.46 | 2023-06-13 | 2023-06-02 | 2023-07-22 | 1 | 8841.46
W-520B | DHJ | Girder Spesial | GD16 | 10736.49 | 2023-06-13 | 2023-06-02 | 2023-07-22 | 5 | 53682.45
W-520C | DHJ | Girder Spesial | GD18 | 12394.98 | 2023-06-13 | 2023-06-02 | 2023-07-22 | 3 | 37184.94
W-520D | DHJ | Girder Spesial | GD20 | 15105.2 | 2023-06-13 | 2023-06-02 | 2023-07-22 | 1 | 15105.2
W-521 | DHJ | Girder | BG25 | 31786.84 | 2023-07-06 | 2023-06-06 | 2023-07-23 | 1 | 31786.84
W-522 | DHJ | Truss Modullar | KOMPONEN STRINGGER | 11675.6 |  |  |  | 1 | 11675.6
W-523 | DHJ | Girder | BG25 | 27691.33 | 2023-06-12 | 2023-06-09 | 2023-07-26 | 1 | 27691.33
W-524 | DHJ | WELDED BEAM | WB BEAM | 3854.33 |  | 2023-06-07 | 2023-06-22 | 1 | 3854.33
W-525 | DHJ | Girder | BG30 | 61592.52 |  | 2023-06-09 | 2023-07-29 | 1 | 61592.52
W-526 | DHJ | Girder | CG30 | 32109.32 | 2023-06-13 | 2023-06-12 | 2023-07-29 | 1 | 32109.32
W-527 | DHJ | Girder | BG35 | 63831.92 | 2023-06-20 | 2023-06-14 | 2023-08-03 | 1 | 63831.92
W-528 | DHJ | Girder | BG20 | 23612.12 | 2023-06-20 | 2023-06-14 | 2023-08-10 | 1 | 23612.12
W-529 | DHJ | Truss Modullar | RB50 | 89080.45 | 2023-06-23 | 2023-06-19 | 2023-08-28 | 2 | 178160.9
W-530 | DHJ | Jembatan Gantung | JG154 | 37760.5 | 2023-08-16 |  |  | 1 | 37760.5 |  |  |  |  | HANGER
W-530 | DHJ | Jembatan Gantung | JG154 | 969.76 |  |  |  | 1 | 969.76
W-530 | DHJ | Jembatan Gantung | JG154 | 4953.68 |  |  |  | 1 | 4953.68 |  |  |  |  | ADDITIONAL IKATAN ANGIN
W-531 | DHJ | Girder | CG15_6 Line | 18751.4 | 2023-06-26 | 2023-06-26 | 2023-08-09 | 1 | 18751.4
W-532 | DHJ | Girder | BG30 | 38834.35 | 2023-06-26 |  |  | 1 | 38834.35 |  |  |  |  | Reff. W477
W-532A | DHJ | ORNAMEN PIPA | GB30-ARCH | 6578.71 |  |  |  | 1 | 6578.71
W-533 | DHJ | Jembatan Gantung | JG120 | 21968.33 | 2023-08-03 |  |  | 1 | 21968.33
W-534 | DHJ | Girder | AG20 | 24116.54 | 2023-07-26 | 2023-07-26 | 2023-09-02 | 1 | 24116.54 |  |  |  |  | Reff. W405
W-535 | DHJ | Jembatan Gantung | JG80 | 13211.78 | 2023-08-16 |  |  | 1 | 13211.78
W-536 | DHJ | Girder | CG30 | 32109.32 | 2023-06-13 | 2023-07-13 | 2023-08-26 | 1 | 32109.32
W-537 | DHJ | Panel Bailey | 30 SSR-EW | 30863.69 |  | 2023-07-06 | 2023-08-09 | 3 | 92591.07
W-538 | DHJ | Truss Modullar | RB60 | 132663.95 | 2023-07-26 | 2023-07-12 | 2023-08-16 | 1 | 132663.95
W-539 | DHJ | SPECER MRT | SPECER MRT | 4829.88 | 2023-07-12 | 2023-07-10 | 2023-07-26 | 1 | 4829.88
W-540 | DHJ | SUPPORT BEAM | SB35 | 20002.72 | 2023-07-12 | 2023-07-12 | 2023-08-16 | 1 | 20002.72
W-541 | DHJ | Girder | CG12 | 9767.04 | 2023-07-26 | 18/07/2023 | 31/08/2023 | 1 | 9767.04
W-542 | DHJ | Jembatan Gantung | JG360_TAHAP I | 191687.58 |  |  |  | 1 | 191687.58
W-542 | DHJ | Jembatan Gantung | JG360_TAHAP I | 118324.16 |  |  |  | 1 | 118324.16
W-543 | DHJ | Girder | GB30 | 39865.21 | 2023-08-18 |  |  | 1 | 39865.21
W-544 | DHJ | Panel Bailey | 9 SSR-EW | 10112.12 |  |  |  | 2 | 20224.24
W-545 | DHJ | Jembatan Gantung | JG150 | 24764.35 | 2023-08-07 | 2023-04-08 | 2023-06-09 | 1 | 24764.35
W-546 | DHJ | Panel Bailey | 39 DSR2H**-EW | 60185.5033 |  |  |  | 1 | 60185.5033
W-547 | DHJ | Panel Bailey | 6 SSR-SW | 7184.09 |  |  |  | 3 | 21552.27
W-548 | DHJ | PLATE LRB | LRB | 2307.1734 |  |  |  | 1 | 2307.1734
W-549 | DHJ | Truss Modullar | RB40 | 67681.34 |  | 2023-01-08 | 16/08/2023 | 1 | 67681.34
W-550 | DHJ | Panel Bailey | 30 DSR2-EW | 43261.99 |  |  |  | 1 | 43261.99
W-551 | DHJ | Girder | AG40 | 117156.9 | 2023-08-10 |  |  | 1 | 117156.9
W-552 | DHJ | JPO | JPO-48 | 23400.14 | 2023-08-11 |  |  | 1 | 23400.14
W-553 | DHJ | Panel Bailey | 12 SSR-EW | 11373.3 |  |  |  | 3 | 34119.9
W-554 | DHJ | STRUKTUR PERKUATAN | PERKUATAN | 6609.12 |  |  |  | 1 | 6609.12
W-555 | DHJ | Jembatan Gantung | JG40_ASIMETRIS | 14827.35 |  |  |  | 1 | 14827.35
W-556 | DHJ | Girder | CG12 | 7753.39 | 2023-08-26 |  |  | 1 | 7753.39
W-557 | DHJ | Panel Bailey | Ex. England | 44.744 | 2023-08-16 |  |  | 1 | 44.744
W-558 | DHJ | Truss Modullar | RB30 | 48505.58 |  |  |  | 1 | 48505.58
W-559 | DHJ | Jembatan Gantung | JG100P | 32191.3 |  |  |  | 1 | 32191.3
W-560A | DHJ | Jembatan Pendekat | SPAN 11.87 M | 2624.12 |  |  |  | 2 | 5248.24
W-560B | DHJ | Jembatan Pendekat | SPAN 14.20 M | 5095.58 |  |  |  | 1 | 5095.58
W-560C | DHJ | Jembatan Pendekat | SPAN 22.82 M | 15295.28 |  |  |  | 1 | 15295.28
W-561 | DHJ | TOWER | TWR-H36 | 11581.71 | 2023-08-31 |  |  | 1 | 11581.71
W-562 | DHJ | Panel Bailey | 24 DSR2-EW | 35413.93 |  | 2023-08-28 | 2023-09-24 | 1 | 35413.93
W-563 | DHJ | Girder | CG12 | 8364.5 |  |  |  | 1 | 8364.5
W-564 | DHJ | Truss Modullar | RB50 | 97069.91 |  |  |  | 1 | 97069.91
W-565 | DHJ | Panel Bailey | 36 DSR2-EW | 52580.93 |  |  |  | 1 | 52580.93
W-565A | DHJ | RAMP Panel Bailey | RAMP PANEL BAILEY | 1897.96 |  |  |  | 2 | 3795.92
W-566 | DHJ | Girder | AG18.8 | 39866.56 |  |  |  | 1 | 39866.56
W-567 | DHJ | STRUKTUR ATAP | ATAP ASRAMA HAJI | 14880.765 |  |  |  | 1 | 14880.765
W-568A | DHJ | Panel Bailey | 18 SSR - EW (LANTAI KAYU) | 10104.65 |  |  |  | 1 | 10104.65
W-568A | DHJ | Panel Bailey | 18 SSR - EW (LANTAI KAYU) | 4427.28 |  |  |  | 1 | 4427.28
W-568B | DHJ | Panel Bailey | 24 SSR - EW (LANTAI KAYU) | 13124.31 |  |  |  | 1 | 13124.31
W-568B | DHJ | Panel Bailey | 24 SSR - EW (LANTAI KAYU) | 5827.88 |  |  |  | 1 | 5827.88
W-569 | DHJ | Truss Modullar | RB40 | 62651.46 |  |  |  | 1 | 62651.46
W-570 | DHJ | Truss Modullar | RB30 | 48505.58 |  |  |  | 1 | 48505.58
W-571 | DHJ | Panel Bailey | 30 DSR2-EW | 43261.99 |  |  |  | 1 | 43261.99
W-572 | DHJ | Panel Bailey | 21 SSR-EW | 21970.16 |  |  |  | 1 | 21970.16
W-573 | DHJ | Truss Modullar | RB40 | 67681.34 | STJ12 | 2023-03-20 | 2023-04-04 | 1 | 67681.34 |  |  |  |  | TYPICAL DESIGN W-423
W-574 | DHJ | Truss Modullar | RC45+15 | 42283.52 |  |  |  | 1 | 42283.52
W-576A | DHJ | Panel Bailey | 18 SSR - EW | 19005.65 |  |  |  | 1 | 19005.65
W-576B | DHJ | Panel Bailey | 12 SSR-EW | 11373.3 |  |  |  | 1 | 11373.3
W-575 | DHJ | Girder | C43 | 12419.22 |  |  |  | 1 | 12419.22 |  |  |  |  | TYPICAL DESIGN W-501
W-577 | DHJ | Girder | AG20 | 22273.2 |  |  |  | 1 | 22273.2
STKJ25 | DHJ | Panel Bailey STOCK | KOMPONEN BAILEY | 338892.27 |  |  |  | 1 | 338892.27
W-578 | DHJ | KING POST | KP | 451165.015 |  |  |  | 1 | 451165.015
W-579 | DHJ | Panel Bailey | 30 DSR2-EW | 43261.99 |  |  |  | 2 | 86523.98
W-579A | DHJ | Panel Bailey | 36 DSR2-EW | 52580.93 |  |  |  | 2 | 105161.86
W-580 | DHJ | Panel Bailey | 39 DSR2H**-EW | 60185.5033 |  |  |  | 2 | 120371.0066
W-581 | DHJ | Komponen Jembatan | WB BEAM | 25922.4 |  |  |  | 1 | 25922.4
W-582 | DHJ | Komponen Jembatan | WB BEAM | 1561.2874 |  |  |  | 1 | 1561.2874
W-585 | DHJ | Jembatan Gantung | Komponen JG152 | 57494 |  |  |  | 1 | 57494
|  |  |  | 2320750.0557 |  |  |  |  | 2320750.0557
W-576 - PACKING
[8 empty] | 18 | 67872.22
[8 empty] | 12 | 42424.8
110297.02
|  |  |  | 67681.34 |  |  |  | 190.88
|  | W-489A-B | 127796.0738 | 42283.52 |  |  |  | 141.28

## Sheet1
CETAK & DESIGN CALENDAR 2024
Kalender Meja
Deskripsi Product
Dimensi
Spesifikasi Bahan
1 Set Kalender
Harga 1 Kalender Meja
Kalender Dinding
Deskripsi Product
Dimensi
Spesifikasi Bahan
1 Set Kalender
Harga 1 Kalender Meja
Note
* Jika Order dibawah 100 pcs up 20%
AS PIN | 48.6*213 |  | 3.1
Angkur Bearing | M20X420 |  | 1.08
AS PIN | 48.6*213 |  | 3.1
Angkur Bearing | M20X420 |  | 1.08
AS PIN | 48.6*213 |  | 3.1
Angkur Bearing | M20X420 |  | 1.08
AS PIN | 48.6*213 |  | 3.1
Angkur Bearing | M20X420 |  | 1.08
AS PIN | 48.6*213 |  | 3.1
Angkur Bearing | M20X420 |  | 1.08
AS PIN | 48.6*213 |  | 3.1
Angkur Bearing | M20X420 |  | 1.08
JEMBATAN PANEL BAILEY PON 2023
No.PON | Type Struktur | Marking Struktur | Qty | SUM Total
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | 1 | 59752.43
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | 1 | 4838.64
W-504A | Panel Bailey | 12 SSR-EW | 2 | 26153.26
W-504B | Panel Bailey | 15 SSR-EW | 3 | 48123.42
W-504C | Panel Bailey | 21 SSR-EW | 1 | 21970.16
W-505 | Panel Bailey | KOMPONEN BAILEY | 1 | 1406.4612
W-506A | Panel Bailey | 24 DSR2-EW | 2 | 69935.06
W-506B | Panel Bailey | 21 DS-EW | 2 | 51675.08
W-506C | Panel Bailey | 18 DSR1-EW | 1 | 24530.89
W-506D | Panel Bailey | 18 DSR2-EW | 1 | 26673.07
W-506E | Panel Bailey | 33 DSR2H*-EW (U120) | 1 | 50562.14
W-507 | Panel Bailey | 30 DSR2-EW | 3 | 129785.97
W-512A | Panel Bailey | 42 DSR2-EW (U120) | 1 | 61912.55
W-512B | Panel Bailey | 45 DSR2H**-EW (U120) | 2 | 137760.52
W-513 | Panel Bailey | 30 DSR2-EW | 1 | 43261.99
W-515 | Panel Bailey | KOMPONEN BAILEY | 1 | 3482.36
W-516A | Panel Bailey | 36 DSR2-EW | 1 | 52580.93
W-516B | Panel Bailey | 30 DSR2-EW | 2 | 86523.98
W-516C | Panel Bailey | 45 TSR2 - EW | 1 | 79238.13
W-517 | Panel Bailey | 30 DSR2-EW | 1 | 43261.99
W-518A | Panel Bailey | 21 SSR-EW | 2 | 43940.32
W-518B | Panel Bailey | 24 SSR-EW | 1 | 24934.67
W-518C | Panel Bailey | 27 DSR2-EW | 1 | 39114.76
W-519 | Panel Bailey | 39 DSR2H**-EW | 1 | 60185.5033
W-537 | Panel Bailey | 30 SSR-EW | 3 | 92591.07
W-544 | Panel Bailey | 9 SSR-EW | 2 | 20224.24
W-546 | Panel Bailey | 39 DSR2H**-EW | 1 | 60185.5033
W-547 | Panel Bailey | 6 SSR-SW | 3 | 21552.27
W-550 | Panel Bailey | 30 DSR2-EW | 1 | 43261.99
W-553 | Panel Bailey | 12 SSR-EW | 3 | 34119.9
W-557 | Panel Bailey | Ex. England | 1 | 44.744
W-562 | Panel Bailey | 24 DSR2-EW | 1 | 35413.93
W-565 | Panel Bailey | 36 DSR2-EW | 1 | 52580.93
W-568A | Panel Bailey | 18 SSR - EW (LANTAI KAYU) | 1 | 10104.65
W-568A | Panel Bailey | 18 SSR - EW (LANTAI KAYU) | 1 | 4427.28
W-568B | Panel Bailey | 24 SSR - EW (LANTAI KAYU) | 1 | 13124.31
W-568B | Panel Bailey | 24 SSR - EW (LANTAI KAYU) | 1 | 5827.88
W-571 | Panel Bailey | 30 DSR2-EW | 1 | 43261.99
W-572 | Panel Bailey | 21 SSR-EW | 1 | 21970.16
W-576A | Panel Bailey | 18 SSR - EW | 1 | 19005.65
W-576B | Panel Bailey | 12 SSR-EW | 1 | 11373.3
W-579 | Panel Bailey | 30 DSR2-EW | 2 | 86523.98
W-579A | Panel Bailey | 36 DSR2-EW | 2 | 105161.86
W-580 | Panel Bailey | 39 DSR2H**-EW | 2 | 120371.0066
|  |  |  | 1992730.9283 | KG
PRODUKSI PANEL BAILEY 2022
| STOCK2022 |  |  | 268007.3663
| STKJ18 |  |  | 189231.53
| STKJ19 |  |  | 155984.84
| STKJ20 |  |  | 285981.34
| STKJ21 |  |  | 174798.16
| STKJ22 |  |  | 313247.54
| STKJ23 |  |  | 397430.23
| STKJ24 |  |  | 197176.7795
| STKJ25 |  |  | 338892.27
|  |  |  | 2320750.0557 | KG
|  |  |  | 328019.1274 | KG

## ISSUE PROJECT (hidden)
No.PON | Type Struktur | Marking Struktur | Date Issue | ISSUE
W-501 | Girder | AG20 | 2023-01-19 | Penambahan Lubang Bondeck
W-500 | Panel Bailey | 33M DSR2 - SS400 | 2023-01-31 | Shop Drawing Baru Turun
W-498 | Jembatan Gantung | JG105 - PIPA | 2023-02-06 | Bentangan Berubah menjadi 105 Meter
W-505 | Panel Bailey | KOMPONEN BAILEY | 2023-02-05 | Dikirim ke Site
W-498 | Jembatan Gantung | JG105 - PIPA | 2023-02-10 | List Revisi ke2 menambahkan material fabrikasi yang awalnya di masining
W-498 | Jembatan Gantung | JG105 - PIPA | 2023-02-13 | Wirelock di fabrikasi oleh DHJ

## Data Aksesories
No.PON | Type Struktur | Marking Struktur | Vendor | No. PO | Purchase | Marking Aksesories | Dimensi/Ukuran | Panjang | Total (pcs) | Berat/pcs (Kg) | Total Berat Aksesories (Kg) | UNIT | TOTAL KESELURUHAN | Keterangan | Qty
STOCK2022 | Panel Bailey STOCK | KOMPONEN BAILEY |  |  | AS PIN | PIN1 | 48.6*213 |  | 1764 | 3.1 | 5468.4 | 1 | 1764
W-493 | PIPE RACK | PIPE RACK |  |  | Angkur Bearing | ANGKUR BOLT | AB-M22-300 | 300 | 168 | 0.85 | 142.8 | 1 | 168
W-498 | Jembatan Gantung | JG105 - PIPA | UNTEK |  | MUR M16 | JG105-NUT1 | NUT_M16 |  | 246 | 0.03 | 7.38 | 1 | 246
W-498 | Jembatan Gantung | JG105 - PIPA | UNTEK |  | AS PIN | JG105-PIN1 | D60 |  | 4 | 3.82 | 15.28 | 1 | 4
W-498 | Jembatan Gantung | JG105 - PIPA | UNTEK |  | AS PIN | JG105-PIN2 | D32 |  | 8 | 0.97 | 7.76 | 1 | 8
W-498 | Jembatan Gantung | JG105 - PIPA | UNTEK |  | AS D16 | JG105-RB3 | D16 |  | 82 | 1.42 | 116.44 | 1 | 82
W-498 | Jembatan Gantung | JG105 - PIPA | UNTEK |  | AS D38 | JG105-RB27 | ROD38 |  | 8 | 10.19 | 81.52 | 1 | 8
W-498 | Jembatan Gantung | JG105 - PIPA | UNTEK |  | RING PLATE BAJA | RING PLATE BAJA | ROD30 |  | 164 | 0.01 | 1.64 | 1 | 164
W-498 | Jembatan Gantung | JG105 - PIPA | UNTEK |  | AS ROLLER | JG105-RL1 | ROD50 |  | 4 | 2.28 | 9.12 | 1 | 4
W-498 | Jembatan Gantung | JG105 - PIPA | UNTEK |  | AS ROLLER | JG105-RL2 | D140 |  | 8 | 2.88 | 23.04 | 1 | 8
W-498 | Jembatan Gantung | JG105 - PIPA | UNTEK |  | MUR M38 | NUT-M38 | NUT_M38 |  | 24 | 0.33 | 7.92 | 1 | 24
W-498 | Jembatan Gantung | JG105 - PIPA | UNTEK |  | RING PLATE BAJA | RING PLATE BAJA 5MM | RING M38 |  | 2 | 0.025 | 0.05 | 1 | 2
W-498 | Jembatan Gantung | JG105 - PIPA | ENIFA INDO JAYA |  | PIN CLAMP HANGER | JG105-PIN24 | D24*85 |  | 82 | 0.44 | 36.08 | 1 | 82
W-499 | Girder | AG30 | KAKADA |  | Bearing | AG30-EB1 | Bearing 41*350*300 |  | 12 | 15.9113 | 190.9359 | 1 | 12
W-499 | Girder | AG30 | KAKADA |  | Bearing | AG30-EB2 | Bearing 20*200*170 |  | 4 | 3.9205 | 15.6821 | 1 | 4
W-499 | Girder | AG30 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 24 | 1.55 | 37.2 | 1 | 24
W-499 | Girder | AG30 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 128 | 0.21 | 26.88 | 1 | 128
W-499 | Girder | AG30 |  |  | Ubolt | U Bolt | U BOLT 2.1/2 "-M12 | 2-1/2" | 128 | 0.33 | 42.24 | 1 | 128
W-500 | Panel Bailey | 33M DSR2 - SS400 |  |  | AS PIN | PIN1 | PIN 60.8*213 | 213 | 48 | 4.77 | 228.96 | 1 | 48
W-500 | Panel Bailey | 33M DSR2 - SS400 |  |  | AS PIN | PIN2 + P15 | PIN 69*394 + PL16*40 |  | 4 | 11.69 | 46.76 | 1 | 4
W-501 | Girder | AG20 | KAKADA |  | Bearing | AG20-EB1 | Bearing 50*350*260 |  | 12 | 14.9933 | 179.9196 | 1 | 12
W-501 | Girder | AG20 | KAKADA |  | Bearing | AG20-EB2 | Bearing 20*200*150 |  | 4 | 3.4381 | 13.7523 | 1 | 4
W-501 | Girder | AG20 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 24 | 1.55 | 37.2 | 1 | 24
W-501 | Girder | AG20 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 88 | 0.21 | 18.48 | 1 | 88
W-501 | Girder | AG20 |  |  | Ubolt | U Bolt | U BOLT 2.1/2 "-M12 | 2-1/2" | 88 | 0.33 | 29.04 | 1 | 88
W-501 | Girder | AG20 |  |  | Bondeck | AG20-PD1 | PL0.75*1450 |  | 5 | 7.38 | 36.9 | 1 | 5
W-501 | Girder | AG20 |  |  | Bondeck | AG20-PD2 | PL0.75*1450 |  | 95 | 10.72 | 1018.4 | 1 | 95
W-501 | Girder | AG20 |  |  | Bondeck | AG20-PD3 | PL0.75*1450 |  | 5 | 7.38 | 36.9 | 1 | 5
W-502 | Girder | AG8 | KAKADA |  | Bearing | AG8-EB1 | Bearing 30*300*300 |  | 12 | 12.0922 | 145.1061 | 1 | 12
W-502 | Girder | AG8 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 40 | 0.21 | 8.4 | 1 | 40
W-502 | Girder | AG8 |  |  | Ubolt | U Bolt | U BOLT 2.1/2 "-M12 | 2-1/2" | 40 | 0.33 | 13.2 | 1 | 40
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | STOCK |  | AS PIN | PIN1 | 48.6*213 | 213 | 240 | 3.1 | 744 | 1 | 240
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | STOCK |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE |  |  | AS PIN | PIN2 + PIN3 | PIN80*317 |  | 4 | 12.5 | 50 | 1 | 4 | AS PIN SUPPORT TRESTLE
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | STOCK |  | Angkur Bearing | M20X420 | M20X420 | 420 | 24 | 1.08 | 25.92 | 1 | 24 | ANGKUR TRESTLE
W-504A | Panel Bailey | 12 SSR-EW | STOCK |  | AS PIN | PIN1 | 48.6*213 | 213 | 80 | 3.1 | 248 | 2 | 160
W-504A | Panel Bailey | 12 SSR-EW | STOCK |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 2 | 64
W-504B | Panel Bailey | 15 SSR-EW | STOCK |  | AS PIN | PIN1 | 48.6*213 | 213 | 144 | 3.1 | 446.4 | 3 | 432
W-504B | Panel Bailey | 15 SSR-EW | STOCK |  | Angkur Bearing | M20X420 | M20X420 | 420 | 48 | 1.08 | 51.84 | 3 | 144
W-504C | Panel Bailey | 21 SSR-EW | STOCK |  | AS PIN | PIN1 | 48.6*213 | 213 | 64 | 3.1 | 198.4 | 1 | 64
W-504C | Panel Bailey | 21 SSR-EW | STOCK |  | Angkur Bearing | M20X420 | M20X420 | 420 | 16 | 1.08 | 17.28 | 1 | 16 |  |  | 192
W-506A | Panel Bailey | 24 DSR2-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 144 | 3.1 | 446.4 | 2 | 288 |  | 288
W-506A | Panel Bailey | 24 DSR2-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 2 | 64 |  | 64
W-506B | Panel Bailey | 21 DS-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 64 | 3.1 | 198.4 | 2 | 128 |  | 128
W-506B | Panel Bailey | 21 DS-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 2 | 64 |  | 64
W-506C | Panel Bailey | 18 DSR1-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 84 | 3.1 | 260.4 | 1 | 84 |  | 168
W-506C | Panel Bailey | 18 DSR1-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32 |  | 64
W-506D | Panel Bailey | 18 DSR2-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 112 | 3.1 | 347.2 | 1 | 112 |  | 112
W-506D | Panel Bailey | 18 DSR2-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32 |  | 32
W-506E | Panel Bailey | 33 DSR2H*-EW (U120) |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 192 | 3.1 | 595.2 | 1 | 192 |  | 192
W-506E | Panel Bailey | 33 DSR2H*-EW (U120) |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32 |  | 32
W-507 | Panel Bailey | 30 DSR2-EW | STOCK |  | AS PIN | PIN1 | 48.6*213 | 213 | 192 | 3.1 | 595.2 | 3 | 576
W-507 | Panel Bailey | 30 DSR2-EW | STOCK |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 3 | 96
W-511 | Girder | BG22 | KAKADA |  | Bearing | BG22-EB1 | Bearing 50*300*250 |  | 10 | 14.4042 | 144.0422 | 1 | 10
W-511 | Girder | BG22 | KAKADA |  | Bearing | BG22-EB2 | Bearing 20*200*150 |  | 4 | 3.4381 | 13.7523 | 1 | 4
W-511 | Girder | BG22 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 20 | 1.55 | 31 | 1 | 20
W-511 | Girder | BG22 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 96 | 0.21 | 20.16 | 1 | 96
W-511 | Girder | BG22 |  |  | Bondeck | GB22-PD1 | PL1*1450 |  | 4 | 10.06 | 40.24 | 1 | 4
W-511 | Girder | BG22 |  |  | Bondeck | GB22-PD2 | PL1*1450 |  | 4 | 9.97 | 39.88 | 1 | 4
W-511 | Girder | BG22 |  |  | Bondeck | GB22-PD3 | PL1*1450 |  | 84 | 14.29 | 1200.36 | 1 | 84
W-511 | Girder | BG22 |  |  | Ubolt | U Bolt | U BOLT 2.1/2 "-M12 | 2-1/2" | 96 | 0.33 | 31.68 | 1 | 96
W-512A | Panel Bailey | 42 DSR2-EW (U120) |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 251 | 1.08 | 271.08 | 1 | 251 |  | 251
W-512A | Panel Bailey | 42 DSR2-EW (U120) |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32 |  | 32
W-512B | Panel Bailey | 45 DSR2H**-EW (U120) |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 283 | 3.1 | 877.3 | 2 | 566 |  | 566
W-512B | Panel Bailey | 45 DSR2H**-EW (U120) |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 2 | 64 |  | 64
W-512C | BEAM TRESTLE | TRESTLE BEAM |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 96 | 1.08 | 103.68 | 1 | 96 |  | 96
W-512C | BEAM TRESTLE | TRESTLE BEAM |  |  | AS PIN | PIN2 | PIN 60*317 |  | 24 | 6.91 | 165.84 | 1 | 24 |  | 24
W-512C | BEAM TRESTLE | TRESTLE BEAM |  |  | AS PIN | PIN3 | ROD76 |  | 12 | 0.19 | 2.28 | 1 | 12 |  | 12
W-512C | BEAM TRESTLE | TRESTLE BEAM |  |  | TEFLON | TF1 | TF10*250 |  | 24 | 0 | 0 | 1 | 24 |  | 24
W-513 | Panel Bailey | 30 DSR2-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 192 | 3.1 | 595.2 | 1 | 192 |  | 192
W-513 | Panel Bailey | 30 DSR2-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32 |  | 32
W-514 | Girder | CG30 |  |  | Bearing | AG30-EB1 | Bearing 41*350*300 |  | 8 | 15.9113 | 127.2906 | 1 | 8
W-514 | Girder | CG30 |  |  | Bearing | AG30-EB2 | Bearing 20*200*170 |  | 4 | 3.9205 | 15.6821 | 1 | 4
W-514 | Girder | CG30 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 16 | 1.55 | 24.8 | 1 | 16
W-514 | Girder | CG30 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 128 | 0.21 | 26.88 | 1 | 128
W-514 | Girder | CG30 |  |  | Bondeck | GC30-PD1 | PL0.75*1452 |  | 3 | 5.59 | 16.77 | 1 | 3
W-514 | Girder | CG30 |  |  | Bondeck | GC30-PD2 | PL0.75*1452 |  | 3 | 5.66 | 16.98 | 1 | 3
W-514 | Girder | CG30 |  |  | Bondeck | GC30-PD3 | PL0.75*1452 |  | 87 | 10.73 | 933.51 | 1 | 87
W-514 | Girder | CG30 |  |  | Ubolt | U Bolt | U BOLT 2.1/2 "-M12 | 2-1/2" | 128 | 0.33 | 42.24 | 1 | 128
W-516A | Panel Bailey | 36 DSR2-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 208 | 3.1 | 644.8 | 1 | 208
W-516A | Panel Bailey | 36 DSR2-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32
W-516B | Panel Bailey | 30 DSR2-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 192 | 3.1 | 595.2 | 2 | 384
W-516B | Panel Bailey | 30 DSR2-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 2 | 64
W-516C | Panel Bailey | 45 TSR2 - EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 256 | 3.1 | 793.6 | 1 | 256
W-516C | Panel Bailey | 45 TSR2 - EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32
W-516C | Panel Bailey | 45 TSR2 - EW |  |  | AS PIN | PIN2 | 48.6X220 |  | 128 | 3.15 | 403.2 | 1 | 128
W-517 | Panel Bailey | 30 DSR2-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 192 | 3.1 | 595.2 | 1 | 192
W-517 | Panel Bailey | 30 DSR2-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32
W-518A | Panel Bailey | 21 SSR-EW | STOCK |  | AS PIN | PIN1 | 48.6*213 | 213 | 64 | 3.1 | 198.4 | 2 | 128
W-518A | Panel Bailey | 21 SSR-EW | STOCK |  | Angkur Bearing | M20X420 | M20X420 | 420 | 16 | 1.08 | 17.28 | 2 | 32
W-518B | Panel Bailey | 24 SSR-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 72 | 3.1 | 223.2 | 1 | 72
W-518B | Panel Bailey | 24 SSR-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 16 | 1.08 | 17.28 | 1 | 16
W-518C | Panel Bailey | 27 DSR2-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 160 | 3.1 | 496 | 1 | 160
W-518C | Panel Bailey | 27 DSR2-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32
W-519 | Panel Bailey | 39 DSR2H**-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 174 | 3.1 | 539.4 | 1 | 174
W-519 | Panel Bailey | 39 DSR2H**-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32
W-519 | Panel Bailey | 39 DSR2H**-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 147 | 3.1 | 455.7 | 1 | 147
W-519 | Panel Bailey | 39 DSR2H**-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32
W-520A | Girder Spesial | GD14 |  |  | Bearing | GD14-EB1 | Bearing 30*300*400 |  | 4 | 16.2147 | 64.8586 | 1 | 4
W-520B | Girder Spesial | GD16 |  |  | Bearing | GD16-EB1 | Bearing 30*300*400 |  | 4 | 16.2147 | 64.8586 | 5 | 20
W-520C | Girder Spesial | GD18 |  |  | Bearing | GD18-EB1 | Bearing 30*300*400 |  | 4 | 16.2147 | 64.8586 | 3 | 12
W-520D | Girder Spesial | GD20 |  |  | Bearing | GD20-EB1 | Bearing 30*300*400 |  | 4 | 16.2147 | 64.8586 | 1 | 4
W-521 | Girder | BG25 |  |  | Bearing | BG25-EB1 | Bearing 50*350*300 |  | 10 | 17.3496 | 173.4961 | 1 | 10
W-521 | Girder | BG25 |  |  | Bearing | BG25-EB2 | Bearing 20*200*150 |  | 4 | 3.4381 | 13.7523 | 1 | 4
W-521 | Girder | BG25 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 20 | 1.55 | 31 | 1 | 20
W-521 | Girder | BG25 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 112 | 0.21 | 23.52 | 1 | 112
W-521 | Girder | BG25 |  |  | Bondeck | GB25-PD1 | PL1*1450 |  | 96 | 14.29 | 1371.84 | 1 | 96
W-521 | Girder | BG25 |  |  | Bondeck | GB25-PD2 | PL1*1450 |  | 4 | 10.01 | 40.04 | 1 | 4
W-521 | Girder | BG25 |  |  | Bondeck | GB25-PD3 | PL1*1450 |  | 4 | 10.11 | 40.44 | 1 | 4
W-521 | Girder | BG25 |  |  | Ubolt | U Bolt | U BOLT 2.1/2 "-M12 | 2-1/2" | 112 | 0.33 | 36.96 | 1 | 112
W-523 | Girder | BG25 |  |  | Bearing | BG25-EB1 | Bearing 50*350*300 |  | 10 | 17.3496 | 173.4961 | 1 | 10
W-523 | Girder | BG25 |  |  | Bearing | BG25-EB2 | Bearing 20*200*150 |  | 4 | 3.4381 | 13.7523 | 1 | 4
W-523 | Girder | BG25 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 20 | 1.55 | 31 | 1 | 20
W-523 | Girder | BG25 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 112 | 0.21 | 23.52 | 1 | 112
W-523 | Girder | BG25 |  |  | Bondeck | GB25-PD1 | PL1*1450 |  | 4 | 8.08 | 32.32 | 1 | 4
W-523 | Girder | BG25 |  |  | Bondeck | GB25-PD2 | PL1*1450 |  | 4 | 8.01 | 32.04 | 1 | 4
W-523 | Girder | BG25 |  |  | Bondeck | GB25-PD3 | PL1*1450 |  | 32 | 10.76 | 344.32 | 1 | 32
W-523 | Girder | BG25 |  |  | Bondeck | GB25-PD4 | PL1*1450 |  | 64 | 11.22 | 718.08 | 1 | 64
W-523 | Girder | BG25 |  |  | Ubolt | U Bolt | U BOLT 2.1/2 "-M12 | 2-1/2" | 112 | 0.33 | 36.96 | 1 | 112
W-525 | Girder | BG30 |  |  | Bearing | BG30-EB1 | Bearing 41*350*310 |  | 10 | 16.4525 | 164.5246 | 1 | 10
W-525 | Girder | BG30 |  |  | Bearing | BG30-EB2 | Bearing 20*200*150 |  | 4 | 3.4381 | 13.7523 | 1 | 4
W-525 | Girder | BG30 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 20 | 1.55 | 31 | 1 | 20
W-525 | Girder | BG30 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 120 | 0.21 | 25.2 | 1 | 120
W-526 | Girder | CG30 |  |  | Bearing | CG30-EB1 | Bearing 41*350*330 |  | 8 | 17.5347 | 140.2778 | 1 | 8
W-526 | Girder | CG30 |  |  | Bearing | CG30-EB2 | Bearing 20*200*150 |  | 4 | 3.4381 | 13.7523 | 1 | 4
W-526 | Girder | CG30 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 16 | 1.55 | 24.8 | 1 | 16
W-526 | Girder | CG30 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 120 | 0.21 | 25.2 | 1 | 120
W-526 | Girder | CG30 |  |  | Bondeck | GC30-PD1 | PL1*1450 |  | 3 | 10.11 | 30.33 | 1 | 3
W-526 | Girder | CG30 |  |  | Bondeck | GC30-PD3 | PL1*1450 |  | 3 | 10.01 | 30.03 | 1 | 3
W-526 | Girder | CG30 |  |  | Bondeck | GC30-PD4 | PL1*1450 |  | 87 | 14.29 | 1243.23 | 1 | 87
W-526 | Girder | CG30 |  |  | Ubolt | U Bolt | U BOLT 2.1/2 "-M12 | 2-1/2" | 128 | 0.33 | 42.24 | 1 | 128
W-527 | Girder | BG35 |  |  | Bearing | BG35-EB1 | Bearing 45*350*330 |  | 10 | 18.2379 | 182.3789 | 1 | 10
W-527 | Girder | BG35 |  |  | Bearing | BG35-EB2 | Bearing 20*200*150 |  | 4 | 3.4381 | 13.7523 | 1 | 4
W-527 | Girder | BG35 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 20 | 1.55 | 31 | 1 | 20
W-527 | Girder | BG35 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 154 | 0.21 | 32.34 | 1 | 154
W-527 | Girder | BG35 |  |  | Bondeck | GB35-PD1 | PL1*1450 |  | 4 | 10.11 | 40.44 | 1 | 4
W-527 | Girder | BG35 |  |  | Bondeck | GB35-PD2 | PL1*1450 |  | 136 | 14.29 | 1943.44 | 1 | 136
W-527 | Girder | BG35 |  |  | Bondeck | GB35-PD3 | PL1*1450 |  | 4 | 10.11 | 40.44 | 1 | 4
W-527 | Girder | BG35 |  |  | Ubolt | U Bolt | U BOLT 2.1/2 "-M12 | 2-1/2" | 154 | 0.33 | 50.82 | 1 | 154
W-528 | Girder | BG20 |  |  | Bearing | BG20-EB1 | Bearing 45*350*330 |  | 10 | 18.2379 | 182.3789 | 1 | 10
W-528 | Girder | BG20 |  |  | Bearing | BG20-EB2 | Bearing 20*200*150 |  | 4 | 3.4381 | 13.7523 | 1 | 4
W-528 | Girder | BG20 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 20 | 1.55 | 31 | 1 | 20
W-528 | Girder | BG20 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 88 | 0.21 | 18.48 | 1 | 88
W-528 | Girder | BG20 |  |  | Bondeck | GB20-PD1 | PL1*1255.6 |  | 76 | 14.29 | 1086.04 | 1 | 76
W-528 | Girder | BG20 |  |  | Bondeck | GB20-PD2 | PL1*880.6 |  | 4 | 10.02 | 40.08 | 1 | 4
W-528 | Girder | BG20 |  |  | Bondeck | GB20-PD3 | PL1*872.4 |  | 4 | 9.93 | 39.72 | 1 | 4
W-528 | Girder | BG20 |  |  | Ubolt | U Bolt | U BOLT 2.1/2 "-M12 | 2-1/2" | 88 | 0.33 | 29.04 | 1 | 88
W-529 | Truss Modullar | RB50 |  |  | Bearing | RB50-EB1 | Bearing 68*500*500 |  | 4 | 48.6643 | 194.6572 | 2 | 8
W-529 | Truss Modullar | RB50 |  |  | Bearing | RB50-EB2 | Bearing 45*300*300 |  | 4 | 14.1469 | 56.5875 | 2 | 8
W-529 | Truss Modullar | RB50 |  |  | Bearing | RB50-EB3 | Bearing 41*200*200 |  | 4 | 5.9227 | 23.6908 | 2 | 8
W-529 | Truss Modullar | RB50 |  |  | Angkur Bearing | AB-M32-1000 | M32X1000 | 1000 | 4 | 6.03 | 24.12 | 2 | 8
W-529 | Truss Modullar | RB50 |  |  | Bondeck | RB50-PD1 | PL1*1182 |  | 60 | 11.65 | 699 | 2 | 120 | Ex. W-483
W-529 | Truss Modullar | RB50 |  |  | Bondeck | RB50-PD2 | PL1*1030 |  | 120 | 10.15 | 1218 | 2 | 240 | Ex. W-483
W-529 | Truss Modullar | RB50 |  |  | Bondeck | RB50-PD3 | PL1*1030 |  | 80 | 9.3 | 744 | 2 | 160 | Ex. W-483
W-529 | Truss Modullar | RB50 |  |  | Bondeck | RB50-PD4 | PL1*1182 |  | 40 | 10.67 | 426.8 | 2 | 80 | Ex. W-483
W-530 | Jembatan Gantung | JG154 |  |  | HANGER | MH154-HG2 | ROD20 | 1090 | 152 | 3.14 | 477.28 | 1 | 152
W-531 | Girder | CG15_6 Line |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 48 | 1.55 | 74.4 | 1 | 48
W-531 | Girder | CG15_6 Line |  |  | Bearing | CG15-EB1 | Bearing 50*350*260 |  | 12 | 14.9933 | 179.9196 | 1 | 12
W-532 | Girder | BG30 |  |  | Bearing | BG30-EB1 | Bearing 50*350*310 |  | 10 | 17.9387 | 179.3869 | 1 | 10
W-532 | Girder | BG30 |  |  | Bearing | BG30-EB2 | Bearing 20*200*150 |  | 4 | 3.4381 | 13.7523 | 1 | 4
W-532 | Girder | BG30 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 20 | 1.55 | 31 | 1 | 20
W-532 | Girder | BG30 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 120 | 0.21 | 25.2 | 1 | 120
W-532 | Girder | BG30 |  |  | Ubolt | U Bolt | U BOLT 2.1/2 "-M12 | 2-1/2" | 120 | 0.33 | 39.6 | 1 | 120
W-532A | ORNAMEN PIPA | GB30-ARCH |  |  | Angkur Bearing | ANCHOR BOLT | M20X420 | 420 | 32 | 1.55 | 49.6 | 1 | 32
W-533 | Jembatan Gantung | JG120 | UNTEK |  | As Drat | GT120-AD1 | ROD55 |  | 8 | 47.02 | 376.16 | 1 | 8 | 2322192.0652
W-533 | Jembatan Gantung | JG120 | UNTEK |  | ASROLLER | GT120-ARC1 | ROD20 |  | 16 | 0.44 | 7.04 | 1 | 16
W-533 | Jembatan Gantung | JG120 | UNTEK |  | AS RODA | GT120-AT1 | ROD22 |  | 8 | 1.11 | 8.88 | 1 | 8
W-533 | Jembatan Gantung | JG120 | UNTEK |  | HANGER | GT120-HG1 | D19 |  | 118 | 4.149 | 489.582 | 1 | 118
W-533 | Jembatan Gantung | JG120 | UNTEK |  | AS PIN | GT120-PIN1 | D58 |  | 8 | 4.04 | 32.32 | 1 | 8
W-533 | Jembatan Gantung | JG120 | UNTEK |  | AS PIN | GT120-PIN2 | D82 |  | 4 | 7.9 | 31.6 | 1 | 4
W-533 | Jembatan Gantung | JG120 | UNTEK |  | Bolt PIN | GT120-PIN24 | D24 |  | 118 | 0.56 | 66.08 | 1 | 118
W-533 | Jembatan Gantung | JG120 | UNTEK |  | BLOCK RESIN | GT120-STW1 | PL140*220 |  | 4 | 75.12 | 300.48 | 1 | 4
W-533 | Jembatan Gantung | JG120 | UNTEK |  | ASROLLER | GT120-RD1 | D180 |  | 4 | 11.82 | 47.28 | 1 | 4
W-533 | Jembatan Gantung | JG120 | UNTEK |  | AS RODA | GT120-RL1 | ROD77 |  | 4 | 6.5 | 26 | 1 | 4
W-533 | Jembatan Gantung | JG120 | UNTEK |  | Bearing | GT120-EB1 | PL45*300 |  | 4 | 14.1469 | 56.5875 | 1 | 4
W-533 | Jembatan Gantung | JG120 | INDOSPLICE |  | Wire Rope | GT120-KBU1 | D57 |  | 2 | 3541.9696 | 7083.9391 | 1 | 2
W-533 | Jembatan Gantung | JG120 | INDOSPLICE |  | Wire Rope | GT120-KIA1 | D16 |  | 1 | 58.86 | 58.86 | 1 | 1
W-533 | Jembatan Gantung | JG120 | INDOSPLICE |  | Wire Rope | GT120-KIA2 | D16 |  | 3 | 3.45 | 10.35 | 1 | 3
W-533 | Jembatan Gantung | JG120 | INDOSPLICE |  | Wire Rope | GT120-KIA3 | D16 |  | 3 | 13.61 | 40.83 | 1 | 3
W-533 | Jembatan Gantung | JG120 | INDOSPLICE |  | Wire Rope | GT120-KIA4 | D16 |  | 3 | 10.19 | 30.57 | 1 | 3
W-533 | Jembatan Gantung | JG120 | INDOSPLICE |  | Wire Rope | GT120-KIA5 | D16 |  | 3 | 6.87 | 20.61 | 1 | 3
W-533 | Jembatan Gantung | JG120 | INDOSPLICE |  | Wire Rope | GT120-KIA6 | D16 |  | 1 | 74.72 | 74.72 | 1 | 1
W-533 | Jembatan Gantung | JG120 | INDOSPLICE |  | Wire Rope | GT120-KIA7 | D16 |  | 1 | 3.6 | 3.6 | 1 | 1
W-533 | Jembatan Gantung | JG120 | INDOSPLICE |  | Wire Rope | GT120-KIA8 | D16 |  | 1 | 14.32 | 14.32 | 1 | 1
W-533 | Jembatan Gantung | JG120 | INDOSPLICE |  | Wire Rope | GT120-KIA9 | D16 |  | 1 | 10.6 | 10.6 | 1 | 1
W-533 | Jembatan Gantung | JG120 | INDOSPLICE |  | Wire Rope | GT120-KIA10 | D16 |  | 1 | 7.18 | 7.18 | 1 | 1
W-533 | Jembatan Gantung | JG120 | INDOSPLICE |  | Wire Rope | GT120-KIA11 | D16 |  | 2 | 58.48 | 116.96 | 1 | 2
W-533 | Jembatan Gantung | JG120 | UNTEK |  | TURNBUCKLE | TB-M20 | PL6*12 |  | 4 | 1.53 | 6.12 | 1 | 4
W-533 | Jembatan Gantung | JG120 |  |  | THIMBLES | THIMBLE-M16 | U24*15*1.5 |  | 16 | 0.14 | 2.24 | 1 | 16
W-533 | Jembatan Gantung | JG120 |  |  | Buldogrip | M16 | M16 |  | 36 | 0.62 | 22.32 | 1 | 36
W-534 | Girder | AG20 |  |  | Bondeck | GA20-PD1 | PL0.75*1460 |  | 95 | 10.79 | 1025.05 | 1 | 95
W-534 | Girder | AG20 |  |  | Bondeck | GA20-PD3 | PL0.75*1460 |  | 5 | 7.45 | 37.25 | 1 | 5
W-534 | Girder | AG20 |  |  | Bondeck | GA20-PD4 | PL0.75*1460 |  | 5 | 7.37 | 36.85 | 1 | 5
W-534 | Girder | AG20 |  |  | Bearing | GA20-EB1 | Bearing 50*350*260 |  | 12 | 14.9933 | 179.9196 | 1 | 12
W-534 | Girder | AG20 |  |  | Bearing | GA20-EB2 | Bearing 20*200*150 |  | 4 | 3.4381 | 13.7523 | 1 | 4
W-534 | Girder | AG20 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 24 | 1.55 | 37.2 | 1 | 24
W-534 | Girder | AG20 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 88 | 0.21 | 18.48 | 1 | 88
W-535 | Jembatan Gantung | JG80 | UNTEK |  | Angkur Pylon | GT80-ABP1 | ROD30 |  | 48 | 7.34 | 352.32 | 1 | 48
W-535 | Jembatan Gantung | JG80 | UNTEK |  | As Drat | GT80-AD1 | ROD50 |  | 16 | 32.0509 | 512.8138 | 1 | 16
W-535 | Jembatan Gantung | JG80 | UNTEK |  | HANGER | GT80-HG21 | D19 |  | 78 | 4.05 | 315.9 | 1 | 78
W-535 | Jembatan Gantung | JG80 | UNTEK |  | AS PIN | GT80-PIN2 | D50 |  | 16 | 2.05 | 32.8 | 1 | 16
W-535 | Jembatan Gantung | JG80 | UNTEK |  | Bolt PIN | GT80-PIN24 | D24 |  | 78 | 0.585 | 45.63 | 1 | 78
W-535 | Jembatan Gantung | JG80 | UNTEK |  | SADDLE | GT80-SD1 | PL20*392 |  | 4 | 103.1 | 412.4 | 1 | 4
W-535 | Jembatan Gantung | JG80 | UNTEK |  | BLOCK RESIN | GT80-STW1 | PL130*200 |  | 8 | 56.56 | 452.48 | 1 | 8
W-535 | Jembatan Gantung | JG80 | INDOSPLICE |  | Wire Rope | GT80-KBU1 | D52 | 150000 | 4 | 1785 | 7140 | 1 | 4
W-536 | Girder | CG30 |  |  | Bearing | CG30-EB1 | Bearing 41*350*330 |  | 8 | 17.5347 | 140.2778 | 1 | 8
W-536 | Girder | CG30 |  |  | Bearing | CG30-EB2 | Bearing 20*200*150 |  | 4 | 3.4381 | 13.7523 | 1 | 4
W-536 | Girder | CG30 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 16 | 1.55 | 24.8 | 1 | 16
W-536 | Girder | CG30 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 120 | 0.21 | 25.2 | 1 | 120
W-536 | Girder | CG30 |  |  | Bondeck | GC30-PD1 | PL1*1450 |  | 3 | 10.11 | 30.33 | 1 | 3
W-536 | Girder | CG30 |  |  | Bondeck | GC30-PD3 | PL1*1450 |  | 3 | 10.01 | 30.03 | 1 | 3
W-536 | Girder | CG30 |  |  | Bondeck | GC30-PD4 | PL1*1450 |  | 87 | 14.29 | 1243.23 | 1 | 87
W-537 | Panel Bailey | 30 SSR-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 88 | 3.1 | 272.8 | 3 | 264
W-537 | Panel Bailey | 30 SSR-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 16 | 1.55 | 24.8 | 3 | 48
W-538 | Truss Modullar | RB60 |  |  | Angkur Bearing | ANCHOR BOLT | M32X1000 | 1000 | 4 | 6.03 | 24.12 | 1 | 4
W-538 | Truss Modullar | RB60 |  |  | Bondeck | RB60-PD1 | PL1*1111.5 |  | 72 | 10.96 | 789.12 | 1 | 72
W-538 | Truss Modullar | RB60 |  |  | Bondeck | RB60-PD2 | PL1*1081 |  | 144 | 10.66 | 1535.04 | 1 | 144
W-538 | Truss Modullar | RB60 |  |  | Bondeck | RB60-PD3 | PL1*1111.5 |  | 48 | 10.17 | 488.16 | 1 | 48
W-538 | Truss Modullar | RB60 |  |  | Bondeck | RB60-PD4 | PL1*1081 |  | 96 | 9.89 | 949.44 | 1 | 96
W-538 | Truss Modullar | RB60 |  |  | Bearing | RB60-EB1 | PL68*525*525 |  | 4 | 53.7012 | 214.805 | 1 | 4
W-538 | Truss Modullar | RB60 |  |  | Bearing | RB60-EB2 | PL45*350*350 |  | 4 | 19.3628 | 77.4511 | 1 | 4
W-538 | Truss Modullar | RB60 |  |  | Bearing | RB60-EB3 | PL41*250 |  | 4 | 5.9227 | 23.6908 | 1 | 4
W-539 | SPECER MRT | SPECER MRT |  |  | LONG BOLT | LONG BOLT | M24X1160 |  | 144 | 4.12 | 593.28 | 1 | 144
W-539 | SPECER MRT | SPECER MRT |  |  | Angkur Bearing | ANCHOR BOLT | M24X650 | 650 | 136 | 2.31 | 314.16 | 1 | 136
W-540 | SUPPORT BEAM | SB35 |  |  | Angkur Bearing | ANCHOR BOLT | M20X500 | 500 | 12 | 1.65 | 19.8 | 1 | 12
W-541 | Girder | CG12 |  |  | Bondeck | GC12-PD1 | PL0.75*1255.6 |  | 33 | 10.94 | 361.02 | 1 | 33
W-541 | Girder | CG12 |  |  | Bondeck | GC12-PD2 | PL0.75*1270.2 |  | 3 | 7.74 | 23.22 | 1 | 3
W-541 | Girder | CG12 |  |  | Bondeck | GC12-PD3 | PL0.75*1270.2 |  | 3 | 7.74 | 23.22 | 1 | 3
W-541 | Girder | CG12 |  |  | Bondeck | GC12-EB1 | Bearing 50*300*250 |  | 8 | 12.3139 | 98.5115 | 1 | 8
W-541 | Girder | CG12 |  |  | Bondeck | GC12-EB2 | Bearing 20*200*150 |  | 4 | 3.4381 | 13.7523 | 1 | 4
W-541 | Girder | CG12 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 16 | 1.55 | 24.8 | 1 | 16
W-541 | Girder | CG12 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 56 | 0.21 | 11.76 | 1 | 56
W-541 | Girder | CG12 |  |  | Ubolt | U Bolt | U BOLT 2.1/2 "-M12 | 2-1/2" | 56 | 0.33 | 18.48 | 1 | 56
W-542 | Jembatan Gantung | JG360_TAHAP I |  |  | Angkur Pylon | ANCHOR BOLT PYLON | M40X1781 | 1781 | 128 | 17.06 | 2183.68 | 1 | 128
W-542 | Jembatan Gantung | JG360_TAHAP I |  |  | ASROLLER | JG360-P79 | ROD270 |  | 12 | 208.2 | 2498.4 | 1 | 12
W-542 | Jembatan Gantung | JG360_TAHAP I |  |  | AS RODA | JG360-RD1 | ROD671 |  | 12 | 539.73 | 6476.76 | 1 | 12
W-542 | Jembatan Gantung | JG360_TAHAP I |  |  | AS PIN | JG360-PIN1 | D58 | 150 | 28 | 3.44 | 96.32 | 1 | 28
W-542 | Jembatan Gantung | JG360_TAHAP I |  |  | AS PIN | JG360-PIN2 | D58 | 150 | 28 | 3.44 | 96.32 | 1 | 28
W-542 | Jembatan Gantung | JG360_TAHAP I |  |  | AS PIN | JG360-PIN3 | D100 | 160 | 14 | 10.49 | 146.86 | 1 | 14
W-542 | Jembatan Gantung | JG360_TAHAP I |  |  | AS PIN | JG360-PIN4 | D100 | 160 | 14 | 10.49 | 146.86 | 1 | 14
W-542 | Jembatan Gantung | JG360_TAHAP I |  |  | BLOCK RESIN | JG360-WL1 | PL120*250 | 250 | 28 | 71.01 | 1988.28 | 1 | 28
W-543 | Girder | GB30 |  |  | Bearing | BG30-EB1 | Bearing 41*350*330 |  | 10 | 17.5347 | 175.3473 | 1 | 10
W-543 | Girder | GB30 |  |  | Bearing | BG30-EB2 | Bearing 20*200*150 |  | 4 | 3.4381 | 13.7523 | 1 | 4
W-543 | Girder | GB30 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 20 | 1.55 | 31 | 1 | 20
W-543 | Girder | GB30 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 128 | 0.21 | 26.88 | 1 | 128
W-543 | Girder | GB30 |  |  | Ubolt | U Bolt | U BOLT 2.1/2 "-M12 | 2-1/2" | 128 | 0.33 | 42.24 | 1 | 128
W-543 | Girder | GB30 |  |  | Bondeck | GB30-PD1 | PL0.8*1256.1 | 1440 | 116 | 10.64 | 1234.24 | 1 | 116
W-543 | Girder | GB30 |  |  | Bondeck | GB30-PD2 | PL0.8*886.7 | 1440 | 8 | 7.52 | 60.16 | 1 | 8
W-544 | Panel Bailey | 9 SSR-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 32 | 3.1 | 99.2 | 2 | 64
W-544 | Panel Bailey | 9 SSR-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 16 | 1.08 | 17.28 | 2 | 32
W-545 | Jembatan Gantung | JG150 | UNTEK |  | HANGER | RGH-HG1 | M22X940 |  | 148 | 4.22 | 624.56 | 1 | 148
W-545 | Jembatan Gantung | JG150 | UNTEK |  | Angkur Bearing | RGR-AR1 | ROD20 | 700 | 8 | 1.75 | 14 | 1 | 8
W-545 | Jembatan Gantung | JG150 | UNTEK |  | Bearing | RGR-EB1 | PL23*250 |  | 4 | 2.88 | 11.52 | 1 | 4
W-545 | Jembatan Gantung | JG150 | UNTEK |  | Bearing | RGR-EB2 | PL25*160 |  | 4 | 1.24 | 4.96 | 1 | 4
W-545 | Jembatan Gantung | JG150 | UNTEK |  | Bolt PIN | RGH-PIN24 | D24 |  | 148 | 0.56 | 82.88 | 1 | 148
W-545 | Jembatan Gantung | JG150 | INDOSPLICE |  | Wire Rope | RGI-WIA1 | D22 |  | 1 | 394.485 | 394.485 | 1 | 1
W-545 | Jembatan Gantung | JG150 | INDOSPLICE |  | Wire Rope | RGI-WIA2 | D22 |  | 1 | 287.266 | 287.266 | 1 | 1
W-545 | Jembatan Gantung | JG150 | INDOSPLICE |  | Wire Rope | RGI-WIA3 | D16 |  | 1 | 265.6168 | 265.6168 | 1 | 1
W-545 | Jembatan Gantung | JG150 | UNTEK |  | Boldogrip | BGRIP-M16 | PL13*16 |  | 132 | 0.1 | 13.2 | 1 | 132
W-545 | Jembatan Gantung | JG150 | UNTEK |  | Boldogrip | BGRIP-M22 | D22 |  | 16 | 0.56 | 8.96 | 1 | 16
W-545 | Jembatan Gantung | JG150 | UNTEK |  | TURNBUCKLE | RGI-WM20 | D20 |  | 16 | 10.6 | 169.6 | 1 | 16
W-545 | Jembatan Gantung | JG150 | UNTEK |  | TURNBUCKLE | RGI-WM38 | D38 |  | 16 | 83.84 | 1341.44 | 1 | 16
W-545 | Jembatan Gantung | JG150 | UNTEK |  | thimbles | THIMBLE-M16 | U24*15*2 |  | 44 | 0.25 | 11 | 1 | 44
W-545 | Jembatan Gantung | JG150 | UNTEK |  | thimbles | THIMBLE-M22 | U40*30*2 |  | 2 | 0.61 | 1.22 | 1 | 2
W-546 | Panel Bailey | 39 DSR2H**-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 174 | 3.1 | 539.4 | 1 | 174
W-546 | Panel Bailey | 39 DSR2H**-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32
W-547 | Panel Bailey | 6 SSR-SW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 24 | 3.1 | 74.4 | 3 | 72
W-547 | Panel Bailey | 6 SSR-SW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 3 | 96
W-549 | Truss Modullar | RB40 |  |  | Bearing | RB40-EB1 | PL68*450*450 |  | 4 | 45.46 | 181.8398 | 1 | 4
W-549 | Truss Modullar | RB40 |  |  | Bearing | RB40-EB2 | PL45*300*300 |  | 4 | 14.1469 | 56.5875 | 1 | 4
W-549 | Truss Modullar | RB40 |  |  | Bearing | RB40-EB3 | PL20*200*200 |  | 4 | 4.6442 | 18.5768 | 1 | 4
W-549 | Truss Modullar | RB40 |  |  | Angkur Bearing | M32X850 | M32X850 | 850 | 4 | 5.12 | 20.48 | 1 | 4
W-549 | Truss Modullar | RB40 |  |  | Bondeck | RB40-PD1 | PL1*1124*1270 |  | 32 | 10.25 | 328 | 1 | 32
W-549 | Truss Modullar | RB40 |  |  | Bondeck | RB40-PD2 | PL1*1081*1270 |  | 64 | 9.86 | 631.04 | 1 | 64
W-549 | Truss Modullar | RB40 |  |  | Bondeck | RB40-PD3 | PL1*1124*1256 |  | 48 | 11.08 | 531.84 | 1 | 48
W-549 | Truss Modullar | RB40 |  |  | Bondeck | RB40-PD4 | PL1*1081*1256 |  | 96 | 10.66 | 1023.36 | 1 | 96
W-550 | Panel Bailey | 30 DSR2-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 192 | 3.1 | 595.2 | 1 | 192
W-550 | Panel Bailey | 30 DSR2-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32
W-551 | Girder | AG40 |  |  | Bearing | G40-EB1 | PL60*460*460 |  | 12 | 38.5446 | 462.5353 | 1 | 12
W-551 | Girder | AG40 |  |  | Bearing | G40-EB2 | PL20*200*150 |  | 4 | 3.4381 | 13.7523 | 1 | 4
W-551 | Girder | AG40 |  |  | Angkur Bearing | M30X420 | M30X420 | 420 | 24 | 2.23 | 53.52 | 1 | 24
W-551 | Girder | AG40 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 168 | 0.21 | 35.28 | 1 | 168
W-551 | Girder | AG40 |  |  | Bondeck | G40-PD1 | PL0.75*1400*985 |  | 10 | 8.12 | 81.2 | 1 | 10
W-551 | Girder | AG40 |  |  | Bondeck | G40-PD2 | PL0.75*1400*1256 |  | 195 | 10.3484 | 2017.94 | 1 | 195
W-551 | Girder | AG40 |  |  | Ubolt | U Bolt | U BOLT 2.1/2 "-M12 | 2-1/2" | 168 | 0.33 | 55.44 | 1 | 168
W-552 | JPO | JPO-48 |  |  | Angkur Bearing | AB-M25-240 | ROD25 | 240 | 16 | 1.55 | 24.8 | 1 | 16
W-552 | JPO | JPO-48 |  |  | Bearing | G48-EB1 | PL50*300*250 | 300 | 8 | 12.31 | 98.48 | 1 | 8
W-553 | Panel Bailey | 12 SSR-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 40 | 3.1 | 124 | 3 | 120
W-553 | Panel Bailey | 12 SSR-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 16 | 1.08 | 17.28 | 3 | 48
W-554 | STRUKTUR PERKUATAN | PERKUATAN |  |  | Angkur Bearing | AB-M20-600 | ROD20 | 600 | 24 | 1.3321 | 31.97 | 1 | 24
W-554 | STRUKTUR PERKUATAN | PERKUATAN |  |  | Bearing | EB1 | PL50*300*300 |  | 3 | 14.8318 | 44.4953 | 1 | 3
W-554 | STRUKTUR PERKUATAN | PERKUATAN |  |  | Bearing | EB2 | PL50*450*450 |  | 6 | 33.7868 | 202.7206 | 1 | 6
W-555 | Jembatan Gantung | JG40_ASIMETRIS |  |  | Wire Rope | GT40-KBU1 | ROD38 | 55000 | 1 | 332.145 | 332.145 | 1 | 1
W-555 | Jembatan Gantung | JG40_ASIMETRIS |  |  | Wire Rope | GT40-KBU2 | ROD38 | 55000 | 1 | 332.145 | 332.145 | 1 | 1
W-555 | Jembatan Gantung | JG40_ASIMETRIS |  |  | Wire Rope | GT40-IA3 | ROD16 | 55000 | 1 | 58.85 | 58.85 | 1 | 1
W-555 | Jembatan Gantung | JG40_ASIMETRIS |  |  | Wire Rope | GT40-IA2 | ROD10 | 22000 | 1 | 9.196 | 9.196 | 1 | 1
W-555 | Jembatan Gantung | JG40_ASIMETRIS |  |  | Boldogrip | BGRIP-M16 | PL13*16 |  | 20 | 0.1 | 2 | 1 | 20
W-555 | Jembatan Gantung | JG40_ASIMETRIS |  |  | Boldogrip | BGRIP-M10 |  |  | 24 | 0.05 | 1.2 | 1 | 24
W-555 | Jembatan Gantung | JG40_ASIMETRIS |  |  | HANGER | GT40-HG21 | ROD40 | 1100 | 38 | 2.71 | 102.98 | 1 | 38
W-555 | Jembatan Gantung | JG40_ASIMETRIS |  |  | AS PIN | GT40-PIN1 | D80 | 165 | 2 | 7 | 14 | 1 | 2
W-555 | Jembatan Gantung | JG40_ASIMETRIS |  |  | AS PIN | GT40-PIN2 | D50 | 150 | 4 | 2.49 | 9.96 | 1 | 4
W-555 | Jembatan Gantung | JG40_ASIMETRIS |  |  | SADDLE | GT40-SD1 | PL16*276 | 516 | 2 | 49.67 | 99.34 | 1 | 2
W-555 | Jembatan Gantung | JG40_ASIMETRIS |  |  | BLOCK RESIN | GT40-STW1 | PL100*180 | 180 | 2 | 31.5 | 63 | 1 | 2
W-555 | Jembatan Gantung | JG40_ASIMETRIS |  |  | thimbles | GT40-THIMBLES | THIMBLES M16 |  | 2 | 0.23 | 0.46 | 1 | 2
W-555 | Jembatan Gantung | JG40_ASIMETRIS |  |  | As Drat | GT40-AD1 | ROD44 | 1385 | 4 | 26.68 | 106.72 | 1 | 4
W-555 | Jembatan Gantung | JG40_ASIMETRIS |  |  | Angkur Bearing | GT40-AB1 | ROD22 | 420 | 4 | 1.2 | 4.8 | 1 | 4
W-555 | Jembatan Gantung | JG40_ASIMETRIS |  |  | Angkur Kollom | GT40-AK1 | ROD22 | 873 | 20 | 2.54 | 50.8 | 1 | 20
W-555 | Jembatan Gantung | JG40_ASIMETRIS |  |  | Angkur Kollom | GT40-AK2 | ROD22 | 373 | 12 | 1.11 | 13.32 | 1 | 12
W-555 | Jembatan Gantung | JG40_ASIMETRIS |  |  | Angkur Pylon | GT40-AP1 | ROD24 | 872 | 48 | 3.02 | 144.96 | 1 | 48
W-556 | Girder | CG12 |  |  | Bearing | CG12-EB1 | Bearing 50*250*300 |  | 8 | 14.8318 | 118.6542 | 1 | 8
W-556 | Girder | CG12 |  |  | Bearing | CG12-EB2 | Bearing 20*200*150 |  | 4 | 3.4381 | 13.7523 | 1 | 4
W-556 | Girder | CG12 |  |  | Bondeck | GC12-PD1 | PL0.8*1256.1 | 1480 | 33 | 10.94 | 361.02 | 1 | 33
W-556 | Girder | CG12 |  |  | Bondeck | GC12-PD2 | PL0.8*875.8 | 1480 | 6 | 7.63 | 45.78 | 1 | 6
W-556 | Girder | CG12 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 56 | 1.55 | 86.8 | 1 | 56
W-556 | Girder | CG12 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 16 | 0.21 | 3.36 | 1 | 16
W-556 | Girder | CG12 |  |  | Ubolt | U Bolt | U BOLT 2.1/2 "-M12 | 2-1/2" | 56 | 0.33 | 18.48 | 1 | 56
W-557 | Panel Bailey | Ex. England |  |  | AS PIN | WBEB-03A | RB46.8*290 |  | 2 | 3.6441 | 7.2883 | 1 | 2
W-557 | Panel Bailey | Ex. England |  |  | AS PIN | WBP-001A | RB46.8*200 |  | 19 | 2.6994 | 51.2879 | 1 | 19
W-558 | Truss Modullar | RB30 |  |  | Bearing | RB30-EB1 | Bearing 68*525 | 525 | 4 | 53.7012 | 214.805 | 1 | 4
W-558 | Truss Modullar | RB30 |  |  | Bearing | RB30-EB2 | Bearing 45*300 | 300 | 4 | 16.5506 | 66.2022 | 1 | 4
W-558 | Truss Modullar | RB30 |  |  | Bearing | RB30-EB3 | Bearing 41*250 | 250 | 4 | 9.3675 | 37.4701 | 1 | 4
W-558 | Truss Modullar | RB30 |  |  | Bondeck | RB30-PD1 | PL1*1111.5 | 1256 | 36 | 10.96 | 394.56 | 1 | 36
W-558 | Truss Modullar | RB30 |  |  | Bondeck | RB30-PD2 | PL1*1081 | 1256 | 72 | 10.66 | 767.52 | 1 | 72
W-558 | Truss Modullar | RB30 |  |  | Bondeck | RB30-PD3 | PL1*1111.5 | 1270 | 24 | 10.17 | 244.08 | 1 | 24
W-558 | Truss Modullar | RB30 |  |  | Bondeck | RB30-PD4 | PL1*1081 | 1270 | 48 | 9.89 | 474.72 | 1 | 48
W-558 | Truss Modullar | RB30 |  |  | Angkur Bearing | AB-M32-1000 | M32X1000 | 1000 | 4 | 6.03 | 24.12 | 1 | 4
W-559 | Jembatan Gantung | JG100P |  |  | Angkur Bearing | JG80P-AB1 | ROD24 | 918 | 64 | 3.17 | 202.88 | 1 | 64
W-559 | Jembatan Gantung | JG100P |  |  | Angkur Pylon | JG80P-AB2 | ROD19 | 372 | 8 | 0.77 | 6.16 | 1 | 8
W-559 | Jembatan Gantung | JG100P |  |  | As Drat | JG80P-AD1 | ROD44 | 1400 | 8 | 29.5 | 236 | 1 | 8
W-559 | Jembatan Gantung | JG100P |  |  | HANGER | JG80P-HG21 | D19 | 1350 | 78 | 3.65 | 284.7 | 1 | 78
W-559 | Jembatan Gantung | JG100P |  |  | AS PIN | JG80P-PIN1 | D80 | 165 | 4 | 7 | 28 | 1 | 4
W-559 | Jembatan Gantung | JG100P |  |  | AS PIN | JG80P-PIN2 | D40 | 150 | 8 | 1.71 | 13.68 | 1 | 8
W-559 | Jembatan Gantung | JG100P |  |  | AS ROLLER | JG80P-AS1 | ROD77 | 185 | 4 | 6.5 | 26 | 1 | 4
W-559 | Jembatan Gantung | JG100P |  |  | RODA ROLLER | JG80P-RD1 | D180 | 104 | 4 | 13.44 | 53.76 | 1 | 4
W-559 | Jembatan Gantung | JG100P |  |  | BLOCK RESIN | JG80P-STW1 | PL100*180 | 180 | 4 | 31.13 | 124.52 | 1 | 4
W-559 | Jembatan Gantung | JG100P |  |  | PIN CLAMP HANGER | PIN24 | D24 | 110 | 78 | 1.131 | 88.218 | 1 | 78
W-559 | Jembatan Gantung | JG100P |  |  | Buldogrip | BULDOGRIP-M5 |  |  | 60 | 0.03 | 1.8 | 1 | 60
W-559 | Jembatan Gantung | JG100P |  |  | Buldogrip | BULDOGRIP-M10 |  |  | 20 | 0.09 | 1.8 | 1 | 20
W-559 | Jembatan Gantung | JG100P |  |  | Wire Rope | JG80-IA1 | D16 |  | 1 | 250.5 | 250.5 | 1 | 1
W-559 | Jembatan Gantung | JG100P |  |  | Wire Rope | JG80-IA2 | D10 |  | 4 | 2.17 | 8.68 | 1 | 4
W-559 | Jembatan Gantung | JG100P |  |  | Wire Rope | JG80-IA3 | D10 |  | 4 | 3.02 | 12.08 | 1 | 4
W-559 | Jembatan Gantung | JG100P |  |  | Wire Rope | JG80-IA4 | D10 |  | 4 | 3.99 | 15.96 | 1 | 4
W-559 | Jembatan Gantung | JG100P |  |  | Wire Rope | JG80-IA5 | D10 |  | 4 | 5.02 | 20.08 | 1 | 4
W-559 | Jembatan Gantung | JG100P |  |  | Wire Rope | JG80-IA6 | D10 |  | 4 | 6.08 | 24.32 | 1 | 4
W-559 | Jembatan Gantung | JG100P |  |  | Bearing | JG80P-EB1 | 45*280*350 |  | 4 | 13.1854 | 52.7416 | 1 | 4
W-559 | Jembatan Gantung | JG100P |  |  | Wire Rope | JG80P-KBU1 | D42 |  | 2 | 1002.864 | 2005.728 | 1 | 2
W-559 | Jembatan Gantung | JG100P |  |  | TURNBUCKLE | TB-M20 | 3/4" |  | 4 | 1.53 | 6.12 | 1 | 4
W-559 | Jembatan Gantung | JG100P |  |  | thimbles | THIMBLES-M20 | M20 |  | 4 | 0.44 | 1.76 | 1 | 4
W-559 | Jembatan Gantung | JG100P |  |  | Ubolt | U.BOLT_1.1/4 "- M10 | M10 |  | 492 | 0.09 | 44.28 | 1 | 492
W-560A | Jembatan Pendekat | SPAN 11.87 M |  |  | Angkur Bearing | M16X899 | M16X899 | 900 | 24 | 1.28 | 30.72 | 2 | 48
W-560A | Jembatan Pendekat | SPAN 11.87 M |  |  | Bearing | JP11-EB1 | Bearing 45*250*275 | 275 | 6 | 10.7456 | 64.4736 | 2 | 12
W-560B | Jembatan Pendekat | SPAN 14.20 M |  |  | Angkur Bearing | M16X899 | M16X899 | 900 | 24 | 1.08 | 25.92 | 1 | 24
W-560B | Jembatan Pendekat | SPAN 14.20 M |  |  | Bearing | JP-EB1 | Bearing 45*250*275 | 275 | 6 | 10.7456 | 64.4736 | 1 | 6
W-560C | Jembatan Pendekat | SPAN 22.82 M |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 24 | 1.55 | 37.2 | 1 | 24
W-560C | Jembatan Pendekat | SPAN 22.82 M |  |  | Bearing | JP22-EB1 | Bearing 45*250*280 | 280 | 6 | 10.95 | 65.7 | 1 | 6
W-561 | TOWER | TWR-H36 |  |  | Angkur Bearing | M38X1119 | M38X1119 | 1119 | 24 | 10.233 | 245.5928 | 1 | 24
W-562 | Panel Bailey | 24 DSR2-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 144 | 3.1 | 446.4 | 1 | 144
W-562 | Panel Bailey | 24 DSR2-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32
W-563 | Girder | CG12 |  |  | Bearing | GC12-EB1 | Bearing 50*300 | 250 | 4 | 14.8318 | 59.3271 | 1 | 4
W-563 | Girder | CG12 |  |  | Bearing | GC12-EB2 | Bearing 20*200 | 150 | 4 | 3.4381 | 13.7523 | 1 | 4
W-563 | Girder | CG12 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 8 | 1.55 | 12.4 | 1 | 8
W-563 | Girder | CG12 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 56 | 0.21 | 11.76 | 1 | 56
W-563 | Girder | CG12 |  |  | Ubolt | Ubolt | U BOLT 2.1/2 "-M12 | 2-1/2" | 56 | 0.33 | 18.48 | 1 | 56
W-564 | Truss Modullar | RB50 |  |  | Bearing | RB50-EB1 | Bearing 68*500 | 500 | 4 | 48.6643 | 194.6572 | 1 | 4
W-564 | Truss Modullar | RB50 |  |  | Bearing | RB50-EB2 | Bearing 45*300 | 300 | 4 | 14.1469 | 56.5875 | 1 | 4
W-564 | Truss Modullar | RB50 |  |  | Bearing | RB50-EB3 | Bearing 41*200 | 250 | 4 | 7.3699 | 29.4796 | 1 | 4
W-564 | Truss Modullar | RB50 |  |  | Angkur Bearing | AB-M32-1000 | M32X1000 | 1000 | 4 | 6.03 | 24.12 | 1 | 4
W-564 | Truss Modullar | RB50 |  |  | Bondeck | RB50-PD1 | PL1*1182 | 1256 | 60 | 11.65 | 699 | 1 | 60
W-564 | Truss Modullar | RB50 |  |  | Bondeck | RB50-PD2 | PL1*1030 | 1256 | 120 | 10.15 | 1218 | 1 | 120
W-564 | Truss Modullar | RB50 |  |  | Bondeck | RB50-PD3 | PL1*1030 | 1270 | 48 | 9.3 | 446.4 | 1 | 48
W-564 | Truss Modullar | RB50 |  |  | Bondeck | RB50-PD4 | PL1*1182 | 1270 | 24 | 10.67 | 256.08 | 1 | 24
W-564 | Truss Modullar | RB50 |  |  | Bondeck | RB50-PD5 | PL1*1030 | 1270 | 32 | 8.45 | 270.4 | 1 | 32
W-564 | Truss Modullar | RB50 |  |  | Bondeck | RB50-PD6 | PL1*1182 | 1270 | 16 | 9.7 | 155.2 | 1 | 16
W-565 | Panel Bailey | 36 DSR2-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 208 | 3.1 | 644.8 | 1 | 208
W-565 | Panel Bailey | 36 DSR2-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32
W-566 | Girder | AG18.8 |  |  | Bearing | GA18-EB1 | Bearing 50*350 | 260 | 14 | 14.9933 | 209.9062 | 1 | 14
W-566 | Girder | AG18.8 |  |  | Bearing | GA18-EB2 | Bearing 20*200 | 150 | 4 | 3.9205 | 15.6821 | 1 | 4
W-566 | Girder | AG18.8 |  |  | Bondeck | GA18-PD1 | PL1*1050 |  | 102 | 10.35 | 1055.7 | 1 | 102
W-566 | Girder | AG18.8 |  |  | Bondeck | GA18-PD2 | PL1*1050 |  | 12 | 9.35 | 112.2 | 1 | 12
W-566 | Girder | AG18.8 |  |  | Angkur Railing | AB-M16-185 | M16X185 | 185 | 80 | 0.21 | 16.8 | 1 | 80
W-566 | Girder | AG18.8 |  |  | Angkur Bearing | AB-M25-420 | M25X420 | 420 | 28 | 1.55 | 43.4 | 1 | 28
W-569 | Truss Modullar | RB40 |  |  | Angkur Bearing | AB-M32-850 | M32X850 | 850 | 4 | 5.12 | 20.48 | 1 | 4
W-569 | Truss Modullar | RB40 |  |  | Bearing | RB40-EB1 | Bearing 68*450 | 450 | 4 | 39.3345 | 157.3378 | 1 | 4
W-569 | Truss Modullar | RB40 |  |  | Bearing | RB40-EB2 | Bearing 45*300 | 350 | 4 | 16.5506 | 66.2022 | 1 | 4
W-569 | Truss Modullar | RB40 |  |  | Bearing | RB40-EB3 | Bearing 41*200 | 250 | 4 | 11.2866 | 45.1463 | 1 | 4
W-569 | Truss Modullar | RB40 |  |  | Bondeck | RB40-PD1 | PL1*1124 | 1270 | 24 | 10.25 | 246 | 1 | 24
W-569 | Truss Modullar | RB40 |  |  | Bondeck | RB40-PD2 | PL1*1081 | 1270 | 48 | 9.86 | 473.28 | 1 | 48
W-569 | Truss Modullar | RB40 |  |  | Bondeck | RB40-PD3 | PL1*1124 | 1256 | 52 | 11.08 | 576.16 | 1 | 52
W-569 | Truss Modullar | RB40 |  |  | Bondeck | RB40-PD4 | PL1*1081 | 1256 | 104 | 10.66 | 1108.64 | 1 | 104
W-570 | Truss Modullar | RB30 |  |  | Bearing | RB30-EB1 | Bearing 68*525 | 525 | 4 | 53.7012 | 214.805 | 1 | 4
W-570 | Truss Modullar | RB30 |  |  | Bearing | RB30-EB2 | Bearing 45*300 | 300 | 4 | 16.5506 | 66.2022 | 1 | 4
W-570 | Truss Modullar | RB30 |  |  | Bearing | RB30-EB3 | Bearing 41*250 | 250 | 4 | 9.3675 | 37.4701 | 1 | 4
W-570 | Truss Modullar | RB30 |  |  | Bondeck | RB30-PD1 | PL1*1111.5 | 1256 | 36 | 10.96 | 394.56 | 1 | 36
W-570 | Truss Modullar | RB30 |  |  | Bondeck | RB30-PD2 | PL1*1081 | 1256 | 72 | 10.66 | 767.52 | 1 | 72
W-570 | Truss Modullar | RB30 |  |  | Bondeck | RB30-PD3 | PL1*1111.5 | 1270 | 24 | 10.17 | 244.08 | 1 | 24
W-570 | Truss Modullar | RB30 |  |  | Bondeck | RB30-PD4 | PL1*1081 | 1270 | 48 | 9.89 | 474.72 | 1 | 48
W-570 | Truss Modullar | RB30 |  |  | Angkur Bearing | AB-M32-1000 | M32X1000 | 1000 | 4 | 6.03 | 24.12 | 1 | 4
W-571 | Panel Bailey | 30 DSR2-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 192 | 3.1 | 595.2 | 1 | 192
W-571 | Panel Bailey | 30 DSR2-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32
W-572 | Panel Bailey | 21 SSR-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 144 | 3.1 | 446.4 | 1 | 144
W-572 | Panel Bailey | 21 SSR-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 1 | 32
W-573 | Truss Modullar | RB40 |  |  | Bearing | RB40-EB1 | PL68*450*450 |  | 4 | 45.46 | 181.8398 | 1 | 4
W-573 | Truss Modullar | RB40 |  |  | Bearing | RB40-EB2 | PL45*300*300 |  | 4 | 14.1469 | 56.5875 | 1 | 4
W-573 | Truss Modullar | RB40 |  |  | Bearing | RB40-EB3 | PL20*200*200 |  | 4 | 4.6442 | 18.5768 | 1 | 4
W-573 | Truss Modullar | RB40 |  |  | Angkur Bearing | M32X850 | M32X850 | 850 | 4 | 5.12 | 20.48 | 1 | 4
W-573 | Truss Modullar | RB40 |  |  | Bondeck | RB40-PD1 | PL1*1124*1270 |  | 32 | 10.25 | 328 | 1 | 32
W-573 | Truss Modullar | RB40 |  |  | Bondeck | RB40-PD2 | PL1*1081*1270 |  | 64 | 9.86 | 631.04 | 1 | 64
W-573 | Truss Modullar | RB40 |  |  | Bondeck | RB40-PD3 | PL1*1124*1256 |  | 48 | 11.08 | 531.84 | 1 | 48
W-573 | Truss Modullar | RB40 |  |  | Bondeck | RB40-PD4 | PL1*1081*1256 |  | 96 | 10.66 | 1023.36 | 1 | 96
W-576A | Panel Bailey | 18 SSR - EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 56 | 3.1 | 173.6 | 1 | 56
W-576A | Panel Bailey | 18 SSR - EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 16 | 1.08 | 17.28 | 1 | 16
W-576B | Panel Bailey | 12 SSR-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 40 | 3.1 | 124 | 1 | 40
W-576B | Panel Bailey | 12 SSR-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 16 | 1.08 | 17.28 | 1 | 16
W-574 | Truss Modullar | RC45+15 |  |  | Angkur Bearing | AB-M24-420 | AB-M24-420 | 420 | 8 | 1.42 | 11.36 | 1 | 8
W-574 | Truss Modullar | RC45+15 |  |  | Angkur Bearing | AB-M30-850 | AB-M30-850 | 850 | 2 | 3.97 | 7.94 | 1 | 2
W-574 | Truss Modullar | RC45+15 |  |  | Angkur Bearing | AB-M40-850 | AB-M40-850 | 850 | 2 | 8.78 | 17.56 | 1 | 2
W-574 | Truss Modullar | RC45+15 |  |  | Bearing | RC60-EB1 | PL51*450 | 450 | 4 | 34.095 | 136.3799 | 1 | 4
W-574 | Truss Modullar | RC45+15 |  |  | Bearing | RC60-EB2 | PL 45*250 | 250 | 4 | 9.748 | 38.9921 | 1 | 4
W-574 | Truss Modullar | RC45+15 |  |  | Bearing | RC60-EB3 | PL41*250 | 250 | 6 | 9.3675 | 56.2051 | 1 | 6
W-574 | Truss Modullar | RC45+15 |  |  | Bearing | RC60-EB4 | PL51*400 | 400 | 2 | 26.8569 | 53.7137 | 1 | 2
W-574 | Truss Modullar | RC45+15 |  |  | Wire Rope | RC60-KT1 | D20 | 47761 | 2 | 111.79 | 223.58 | 1 | 2
W-574 | Truss Modullar | RC45+15 |  |  | Wire Rope | RC60-KT2 | D20 | 29355 | 2 | 70.23 | 140.46 | 1 | 2
W-574 | Truss Modullar | RC45+15 |  |  | Wire Rope | RC60-KT3 | D20 | 9765 | 2 | 28.74 | 57.48 | 1 | 2
W-574 | Truss Modullar | RC45+15 |  |  | Wire Rope | RC60-KT4 | D20 | 13968 | 2 | 31.01 | 62.02 | 1 | 2
W-574 | Truss Modullar | RC45+15 |  |  | Wire Rope | RC60-KT5 | D20 | 28946 | 2 | 64.27 | 128.54 | 1 | 2
W-574 | Truss Modullar | RC45+15 |  |  | Bondeck | RC60-PD1 | PL0.75*545 | 668 | 4 | 2.14 | 8.56 | 1 | 4
W-574 | Truss Modullar | RC45+15 |  |  | Bondeck | RC60-PD2 | PL0.75*545 | 672 | 4 | 2.16 | 8.64 | 1 | 4
W-574 | Truss Modullar | RC45+15 |  |  | Bondeck | RC60-PD3 | PL0.75*545 | 1256 | 8 | 4.03 | 32.24 | 1 | 8
W-574 | Truss Modullar | RC45+15 |  |  | Bondeck | RC60-PD4 | PL0.75*1130 | 1256 | 8 | 8.35 | 66.8 | 1 | 8
W-574 | Truss Modullar | RC45+15 |  |  | Bondeck | RC60-PD5 | PL0.75*1230 | 1256 | 64 | 9.09 | 581.76 | 1 | 64
W-574 | Truss Modullar | RC45+15 |  |  | Bondeck | RC60-PD6 | PL0.75*1130 | 1000 | 4 | 6.65 | 26.6 | 1 | 4
W-574 | Truss Modullar | RC45+15 |  |  | Bondeck | RC60-PD7 | PL0.75*1130 | 1008 | 4 | 6.7 | 26.8 | 1 | 4
W-574 | Truss Modullar | RC45+15 |  |  | Bondeck | RC60-PD8 | PL0.75*1230 | 1000 | 32 | 7.24 | 231.68 | 1 | 32
W-574 | Truss Modullar | RC45+15 |  |  | Bondeck | RC60-PD9 | PL0.75*1230 | 1008 | 32 | 7.3 | 233.6 | 1 | 32
W-575 | Girder | C43 |  |  | Angkur Bearing | AB-M20-500 | ROD20 | 500 | 40 | 1.11 | 44.4 | 1 | 40
W-575 | Girder | C43 |  |  | Bearing | GC43-EB1 | PL50*220 | 220 | 8 | 10.2236 | 81.7891 | 1 | 8
W-575 | Girder | C43 |  |  | Bearing | GC43-EB2 | PL20*200 | 150 | 4 | 3.4381 | 13.7523 | 1 | 4
W-575 | Girder | C43 |  |  | Wire Rope | GC43-HG1 | D12 | 2689 | 4 | 1.51 | 6.04 | 1 | 4
W-575 | Girder | C43 |  |  | Wire Rope | GC43-HG2 | D12 | 2086 | 4 | 1.17 | 4.68 | 1 | 4
W-575 | Girder | C43 |  |  | Wire Rope | GC43-HG3 | D12 | 1791 | 4 | 1.17 | 4.68 | 1 | 4
W-575 | Girder | C43 |  |  | Wire Rope | GC43-HG4 | D12 | 3616 | 4 | 2.0281 | 8.1126 | 1 | 4
W-575 | Girder | C43 |  |  | Wire Rope | GC43-PD1 | PL0.75*1390 | 294 | 1 | 2.4 | 2.4 | 1 | 1
W-575 | Girder | C43 |  |  | Wire Rope | GC43-PD2 | PL0.75*1390 | 1256 | 43 | 10.27 | 441.61 | 1 | 43
W-575 | Girder | C43 |  |  | Wire Rope | GC43-PD3 | PL0.75*1390 | 962 | 1 | 7.87 | 7.87 | 1 | 1
W-575 | Girder | C43 |  |  | Wire Rope | KU1 | ROD38 | 28238 | 2 | 183.24 | 366.48 | 1 | 2
W-575 | Girder | C43 |  |  | Wire Rope | KU2 | ROD38 | 9338 | 4 | 55.62 | 222.48 | 1 | 4
W-577 | Girder | AG20 |  |  | Bearing | AG20-EB1 | Bearing 50*350*260 |  | 12 | 14.9933 | 179.9196 | 1 | 12
W-577 | Girder | AG20 |  |  | Bearing | AG20-EB2 | Bearing 20*200*150 |  | 4 | 3.4381 | 13.7523 | 1 | 4
W-577 | Girder | AG20 |  |  | Angkur Bearing | M25X420 | M25X420 | 420 | 24 | 1.55 | 37.2 | 1 | 24
W-577 | Girder | AG20 |  |  | Angkur Railing | M16X185 | M16X185 | 185 | 88 | 0.21 | 18.48 | 1 | 88
W-577 | Girder | AG20 |  |  | Ubolt | U Bolt | U BOLT 2.1/2 "-M12 | 2-1/2" | 88 | 0.33 | 29.04 | 1 | 88
W-577 | Girder | AG20 |  |  | Bondeck | AG20-PD1 | PL0.75*1450 |  | 5 | 7.38 | 36.9 | 1 | 5
W-577 | Girder | AG20 |  |  | Bondeck | AG20-PD2 | PL0.75*1450 |  | 95 | 10.72 | 1018.4 | 1 | 95
W-577 | Girder | AG20 |  |  | Bondeck | AG20-PD3 | PL0.75*1450 |  | 5 | 7.38 | 36.9 | 1 | 5
W-579 | Panel Bailey | 30 DSR2-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 192 | 7.38 | 1416.96 | 2 | 384
W-579 | Panel Bailey | 30 DSR2-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 7.38 | 236.16 | 2 | 64
W-579A | Panel Bailey | 36 DSR2-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 208 | 3.1 | 644.8 | 2 | 416
W-579A | Panel Bailey | 36 DSR2-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 2 | 64
W-580 | Panel Bailey | 39 DSR2H**-EW |  |  | AS PIN | PIN1 | 48.6*213 | 213 | 174 | 3.1 | 539.4 | 2 | 348
W-580 | Panel Bailey | 39 DSR2H**-EW |  |  | Angkur Bearing | M20X420 | M20X420 | 420 | 32 | 1.08 | 34.56 | 2 | 64
W-581 | Komponen Jembatan | WB BEAM |  |  | Angkur Bearing | M24X400 | M20X420 | 400 | 20 | 1.6 | 32 | 1 | 20
W-581 | Komponen Jembatan | WB BEAM |  |  | Bearing |  | Bearing 40*240 | 400 | 10 | 12.288 | 122.88 | 1 | 10
W-582 | Komponen Jembatan | WB BEAM |  |  | Bearing |  | Bearing 60*250 | 300 | 18 | 14.4 | 259.2 | 1 | 18
W-582 | Komponen Jembatan | WB BEAM |  |  | Bearing |  | Bearing 60*350 | 600 | 6 | 40.32 | 241.92 | 1 | 6
W-582 | Komponen Jembatan | WB BEAM |  |  | Bearing |  | Bearing 60*250 | 320 | 10 | 15.36 | 153.6 | 1 | 10
120914.0878
2441664.1435

## Data Baut Jembatan
No.PON | Type Struktur | Marking Struktur | Dimensi | Spesifikasi | Grade | Qty (Set) | Berat Satuan (Kg) | Total Berat Baut (Kg) | Vendor | TOTAL UNIT | Total Berat UNIT (KG) | Date Release | Keterangan | Status
W-493 | PIPE RACK | PIPE RACK | M16X55 | B/N/2WP - HDG (std) | 8.8 | 215 | 0.274 | 58.91 |  | 1 | 58.91
W-493 | PIPE RACK | PIPE RACK | M16X50 | B/N/2WP - HDG (std) | 8.8 | 196 | 0.254 | 49.784 |  | 1 | 49.784
W-493 | PIPE RACK | PIPE RACK | M16X45 | B/N/2WP - HDG (std) | 8.8 | 546 | 0.244 | 133.224 |  | 1 | 133.224
W-493 | PIPE RACK | PIPE RACK | M16X40 | B/N/2WP - HDG (std) | 8.8 | 7 | 0.234 | 1.638 |  | 1 | 1.638
W-498 | Jembatan Gantung | JG105 - PIPA | M24X65 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.592 | 10.064 |  | 1 | 10.064 | 2023-02-10
W-498 | Jembatan Gantung | JG105 - PIPA | M24X50 | B/N/2WP - HDG (std) | 8.8 | 5 | 0.552 | 2.76 |  | 1 | 2.76 | 2023-02-10
W-498 | Jembatan Gantung | JG105 - PIPA | M20X60 | B/N/2WP - HDG (std) | 8.8 | 248 | 0.274 | 67.952 |  | 1 | 67.952 | 2023-02-10
W-498 | Jembatan Gantung | JG105 - PIPA | M20X55 | B/N/2WP - HDG (std) | 8.8 | 264 | 0.264 | 69.696 |  | 1 | 69.696 | 2023-02-10
W-498 | Jembatan Gantung | JG105 - PIPA | M20X50 | B/N/2WP - HDG (std) | 8.8 | 244 | 0.254 | 61.976 |  | 1 | 61.976 | 2023-02-10
W-498 | Jembatan Gantung | JG105 - PIPA | M20X45 | B/N/2WP - HDG (std) | 8.8 | 132 | 0.244 | 32.208 |  | 1 | 32.208 | 2023-02-10
W-498 | Jembatan Gantung | JG105 - PIPA | M16X160 | B/N/2WP - HDG (std) | 8.8 | 101 | 0.319 | 32.219 |  | 1 | 32.219 | 2023-02-10
W-498 | Jembatan Gantung | JG105 - PIPA | M16X55 | B/N/2WP - HDG (std) | 8.8 | 42 | 0.154 | 6.468 |  | 1 | 6.468 | 2023-02-10
W-498 | Jembatan Gantung | JG105 - PIPA | M16X40 | B/N/2WP - HDG (std) | 8.8 | 425 | 0.129 | 54.825 |  | 1 | 54.825 | 2023-02-10
W-498 | Jembatan Gantung | JG105 - PIPA | M16X35 | B/N/2WP - HDG (std) | 8.8 | 99 | 0.129 | 12.771 |  | 1 | 12.771 | 2023-02-10
W-498 | Jembatan Gantung | JG105 - PIPA | M12X35 | B/N/2WP - HDG (std) | 8.8 | 50 | 0.063 | 3.15 |  | 1 | 3.15 | 2023-02-10
W-498 | Jembatan Gantung | JG105 - PIPA | M12X30 | B/N/2WP - HDG (std) | 8.8 | 792 | 0.063 | 49.896 |  | 1 | 49.896 | 2023-02-10
W-498 | Jembatan Gantung | JG105 - PIPA | M10X25 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.011 | 0.187 |  | 1 | 0.187 | 2023-02-10
W-498 | Jembatan Gantung | JG105 - PIPA | M6X20 | B/N/2WP - HDG (std) | 8.8 | 33 | 0.01 | 0.33 |  | 1 | 0.33 | 2023-02-10
W-499 | Girder | AG30 | M24X100 | B/N/2WP (F35) - HDG | 8.8 | 347 | 0.407 | 141.229 |  | 1 | 141.229 | 2023-01-13 |  | 100%
W-499 | Girder | AG30 | M24X90 | B/N/2WP (F35) - HDG | 8.8 | 248 | 0.387 | 95.976 |  | 1 | 95.976 | 2023-01-13 |  | 100%
W-499 | Girder | AG30 | M24X75 | B/N/2WP (F35) - HDG | 8.8 | 693 | 0.347 | 240.471 |  | 1 | 240.471 | 2023-01-13 |  | 100%
W-499 | Girder | AG30 | M20X60 | B/N/2WP (STD) - HDG | 8.8 | 17 | 0.154 | 2.618 |  | 1 | 2.618 | 2023-01-13 |  | 100%
W-499 | Girder | AG30 | M20X55 | B/N/2WP (STD) - HDG | 8.8 | 83 | 0.149 | 12.367 |  | 1 | 12.367 | 2023-01-13 |  | 100%
W-499 | Girder | AG30 | M20X50 | B/N/2WP (STD) - HDG | 8.8 | 206 | 0.136 | 28.016 |  | 1 | 28.016 | 2023-01-13 |  | 100%
W-499 | Girder | AG30 | M12X55 | B/N/2WP (STD) - HDG | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729 | 2023-01-13 |  | 100%
W-500 | Panel Bailey | 33M DSR2 - SS400 | M12X201 | B/N/2WP - HDG (std) | 4.6/8.8 | 33 | 0.185 | 6.105 |  | 1 | 6.105 | 2023-01-31 |  | 100%
W-500 | Panel Bailey | 33M DSR2 - SS400 | M12X181 | B/N/2WP - HDG (std) | 4.6/8.8 | 3 | 0.164 | 0.492 |  | 1 | 0.492 | 2023-01-31
W-500 | Panel Bailey | 33M DSR2 - SS400 | M12X174 | B/N/2WP - HDG (std) | 4.6/8.8 | 36 | 0.156 | 5.616 |  | 1 | 5.616 | 2023-01-31
W-500 | Panel Bailey | 33M DSR2 - SS400 | M12X130 | B/N/2WP - HDG (std) | 4.6/8.8 | 283 | 0.149 | 42.167 |  | 1 | 42.167 | 2023-01-31
W-500 | Panel Bailey | 33M DSR2 - SS400 | 1/2"X3" | B/N/2WP - HDG (F436) | A325 | 108 | 0.158 | 17.064 |  | 1 | 17.064 | 2023-01-31
W-500 | Panel Bailey | 33M DSR2 - SS400 | 5/8"X2" | B/N/2WP - HDG (F436) | A325 | 46 | 0.218 | 10.028 |  | 1 | 10.028 | 2023-01-31
W-500 | Panel Bailey | 33M DSR2 - SS400 | 1/2"X1-3/4" | B/N/2WP - HDG (F436) | A325 | 297 | 0.127 | 37.719 |  | 1 | 37.719 | 2023-01-31
W-501 | Girder | AG20 | M20X85 | B/N/2WP (F35) - HDG | 8.8 | 520 | 0.387 | 201.24 |  | 1 | 201.24 | 2023-01-16 |  | 100%
W-501 | Girder | AG20 | M20X75 | B/N/2WP (F35) - HDG | 8.8 | 186 | 0.367 | 68.262 |  | 1 | 68.262 | 2023-01-16 |  | 100%
W-501 | Girder | AG20 | M20X70 | B/N/2WP (F35) - HDG | 8.8 | 557 | 0.357 | 198.849 |  | 1 | 198.849 | 2023-01-16 |  | 100%
W-501 | Girder | AG20 | M16X50 | B/N/2WP (STD) - HDG | 8.8 | 17 | 0.149 | 2.533 |  | 1 | 2.533 | 2023-01-16 |  | 100%
W-501 | Girder | AG20 | M16X45 | B/N/2WP (STD) - HDG | 8.8 | 206 | 0.136 | 28.016 |  | 1 | 28.016 | 2023-01-16 |  | 100%
W-501 | Girder | AG20 | M12X55 | B/N/2WP (STD) - HDG | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729 | 2023-01-16 |  | 100%
W-501 | Girder | AG20 | M12X40 | B/N/2WP (STD) - HDG | 8.8 | 495 | 0.068 | 33.66 |  | 1 | 33.66 | 2023-01-19 | Penambahan Bondeck | 100%
W-502 | Girder | AG8 | M16X45 | B/N/2WP - HDG (std) | 8.8 | 248 | 0.136 | 33.728 |  | 1 | 33.728 | 2023-02-03
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | M24X130 | B/N/2WP - HDG (std) | 8.8 | 32 | 0.67 | 21.44 |  | 1 | 21.44 | 2023-02-03 | PANEL BAILEY 1X42 DSR2-EW
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 384 | 0.53 | 203.52 |  | 1 | 203.52 | 2023-02-03 | PANEL BAILEY 1X42 DSR2-EW
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 238 | 0.46 | 109.48 |  | 1 | 109.48 | 2023-02-03 | PANEL BAILEY 1X42 DSR2-EW
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 112 | 0.43 | 48.16 |  | 1 | 48.16 | 2023-02-03 | PANEL BAILEY 1X42 DSR2-EW
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 124 | 0.41 | 50.84 |  | 1 | 50.84 | 2023-02-03 | PANEL BAILEY 1X42 DSR2-EW
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 240 | 0.474 | 113.76 |  | 1 | 113.76 | 2023-02-03 | PANEL BAILEY 1X42 DSR2-EW
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.294 | 7.056 |  | 1 | 7.056 | 2023-02-03 | PANEL BAILEY 1X42 DSR2-EW
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 14 | 0.294 | 4.116 |  | 1 | 4.116 | 2023-02-03 | PANEL BAILEY 1X42 DSR2-EW
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 224 | 0.244 | 54.656 |  | 1 | 54.656 | 2023-02-03 | PANEL BAILEY 1X42 DSR2-EW
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.14 | 2.24 |  | 1 | 2.24 | 2023-02-03 | PANEL BAILEY 1X42 DSR2-EW
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 112 | 0.136 | 15.232 |  | 1 | 15.232 | 2023-02-03 | PANEL BAILEY 1X42 DSR2-EW
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | M24X65 | B/N/2WP - HDG (std) | 8.8 | 13 | 0.44 | 5.72 |  | 1 | 5.72 | 2023-02-09 | STRUKTUR TRESTLE
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | M20X55 | B/N/2WP - HDG (std) | 8.8 | 75 | 0.264 | 19.8 |  | 1 | 19.8 | 2023-02-09 | STRUKTUR TRESTLE
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | M20X50 | B/N/2WP - HDG (std) | 8.8 | 38 | 0.254 | 9.652 |  | 1 | 9.652 | 2023-02-09 | STRUKTUR TRESTLE
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | M10X40 | B/N/2WP - HDG (std) | 8.8 | 33 | 0.136 | 4.488 |  | 1 | 4.488 | 2023-02-09 | STRUKTUR TRESTLE
W-504A | Panel Bailey | 12 SSR-EW | M24 x 90 | B/N/2WP - HDG (std) | F10T | 64 | 0.79 | 50.56 |  | 2 | 101.12
W-504A | Panel Bailey | 12 SSR-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 4 | 0.46 | 1.84 |  | 2 | 3.68
W-504A | Panel Bailey | 12 SSR-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 32 | 0.43 | 13.76 |  | 2 | 27.52
W-504A | Panel Bailey | 12 SSR-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.41 | 9.84 |  | 2 | 19.68
W-504A | Panel Bailey | 12 SSR-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.474 | 37.92 |  | 2 | 75.84
W-504A | Panel Bailey | 12 SSR-EW | M20 x 90 | B/N/2WP - HDG (std) | 8.8 | 10 | 0.354 | 3.54 |  | 2 | 7.08
W-504A | Panel Bailey | 12 SSR-EW | M20 x 80 | B/N/2WP - HDG (std) | 8.8 | 10 | 0.334 | 3.34 |  | 2 | 6.68
W-504A | Panel Bailey | 12 SSR-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.294 | 4.704 |  | 2 | 9.408
W-504A | Panel Bailey | 12 SSR-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 4 | 0.294 | 1.176 |  | 2 | 2.352
W-504A | Panel Bailey | 12 SSR-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 32 | 0.244 | 7.808 |  | 2 | 15.616
W-504A | Panel Bailey | 12 SSR-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.136 | 1.088 |  | 2 | 2.176
W-504A | Panel Bailey | 12 SSR-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 32 | 0.136 | 4.352 |  | 2 | 8.704
W-504B | Panel Bailey | 15 SSR-EW | M24 x 90 | B/N/2WP - HDG (std) | F10T | 80 | 0.79 | 63.2 |  | 3 | 189.6
W-504B | Panel Bailey | 15 SSR-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 5 | 0.46 | 2.3 |  | 3 | 6.9
W-504B | Panel Bailey | 15 SSR-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 40 | 0.43 | 17.2 |  | 3 | 51.6
W-504B | Panel Bailey | 15 SSR-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 28 | 0.41 | 11.48 |  | 3 | 34.44
W-504B | Panel Bailey | 15 SSR-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 96 | 0.474 | 45.504 |  | 3 | 136.512
W-504B | Panel Bailey | 15 SSR-EW | M20 x 90 | B/N/2WP - HDG (std) | 8.8 | 12 | 0.354 | 4.248 |  | 3 | 12.744
W-504B | Panel Bailey | 15 SSR-EW | M20 x 80 | B/N/2WP - HDG (std) | 8.8 | 12 | 0.334 | 4.008 |  | 3 | 12.024
W-504B | Panel Bailey | 15 SSR-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.294 | 4.704 |  | 3 | 14.112
W-504B | Panel Bailey | 15 SSR-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 5 | 0.294 | 1.47 |  | 3 | 4.41
W-504B | Panel Bailey | 15 SSR-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 40 | 0.244 | 9.76 |  | 3 | 29.28
W-504B | Panel Bailey | 15 SSR-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.136 | 1.088 |  | 3 | 3.264
W-504B | Panel Bailey | 15 SSR-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 40 | 0.136 | 5.44 |  | 3 | 16.32
W-504C | Panel Bailey | 21 SSR-EW | M24 x 90 | B/N/2WP - HDG (std) | F10T | 112 | 0.79 | 88.48 |  | 1 | 88.48
W-504C | Panel Bailey | 21 SSR-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 7 | 0.46 | 3.22 |  | 1 | 3.22
W-504C | Panel Bailey | 21 SSR-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 56 | 0.43 | 24.08 |  | 1 | 24.08
W-504C | Panel Bailey | 21 SSR-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 36 | 0.41 | 14.76 |  | 1 | 14.76
W-504C | Panel Bailey | 21 SSR-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 128 | 0.474 | 60.672 |  | 1 | 60.672
W-504C | Panel Bailey | 21 SSR-EW | M20 x 90 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.354 | 5.664 |  | 1 | 5.664
W-504C | Panel Bailey | 21 SSR-EW | M20 x 80 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.334 | 5.344 |  | 1 | 5.344
W-504C | Panel Bailey | 21 SSR-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.294 | 4.704 |  | 1 | 4.704
W-504C | Panel Bailey | 21 SSR-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 7 | 0.294 | 2.058 |  | 1 | 2.058
W-504C | Panel Bailey | 21 SSR-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 56 | 0.244 | 13.664 |  | 1 | 13.664
W-504C | Panel Bailey | 21 SSR-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.136 | 1.088 |  | 1 | 1.088
W-504C | Panel Bailey | 21 SSR-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 56 | 0.136 | 7.616 |  | 1 | 7.616
W-505 | Panel Bailey | KOMPONEN BAILEY | M20X140 | B/N/2WP - HDG (std) | 8.8 | 100 | 0.474 | 47.4 |  | 1 | 47.4 | 2023-02-06 | PANEL BAILEY 1X42 DSR2-EW
W-506A | Panel Bailey | 24 DSR2-EW | M24 x 90 | B/N/2WP - HDG (std) | F10T | 256 | 0.79 | 202.24 |  | 2 | 404.48
W-506A | Panel Bailey | 24 DSR2-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 136 | 0.46 | 62.56 |  | 2 | 125.12
W-506A | Panel Bailey | 24 DSR2-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 64 | 0.43 | 27.52 |  | 2 | 55.04
W-506A | Panel Bailey | 24 DSR2-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 40 | 0.41 | 16.4 |  | 2 | 32.8
W-506A | Panel Bailey | 24 DSR2-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 144 | 0.474 | 68.256 |  | 2 | 136.512
W-506A | Panel Bailey | 24 DSR2-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.294 | 7.056 |  | 2 | 14.112
W-506A | Panel Bailey | 24 DSR2-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.294 | 2.352 |  | 2 | 4.704
W-506A | Panel Bailey | 24 DSR2-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 128 | 0.244 | 31.232 |  | 2 | 62.464
W-506A | Panel Bailey | 24 DSR2-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.14 | 2.24 |  | 2 | 4.48
W-506A | Panel Bailey | 24 DSR2-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 64 | 0.136 | 8.704 |  | 2 | 17.408
W-506B | Panel Bailey | 21 DS-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 119 | 0.46 | 54.74 |  | 2 | 109.48
W-506B | Panel Bailey | 21 DS-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 56 | 0.43 | 24.08 |  | 2 | 48.16
W-506B | Panel Bailey | 21 DS-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 36 | 0.41 | 14.76 |  | 2 | 29.52
W-506B | Panel Bailey | 21 DS-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 128 | 0.474 | 60.672 |  | 2 | 121.344
W-506B | Panel Bailey | 21 DS-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.294 | 4.704 |  | 2 | 9.408
W-506B | Panel Bailey | 21 DS-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 7 | 0.294 | 2.058 |  | 2 | 4.116
W-506B | Panel Bailey | 21 DS-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 112 | 0.244 | 27.328 |  | 2 | 54.656
W-506B | Panel Bailey | 21 DS-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 56 | 0.136 | 7.616 |  | 2 | 15.232
W-506C | Panel Bailey | 18 DSR1-EW | M24 x 90 | B/N/2WP - HDG (std) | F10T | 96 | 0.53 | 50.88 |  | 1 | 50.88
W-506C | Panel Bailey | 18 DSR1-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 102 | 0.46 | 46.92 |  | 1 | 46.92
W-506C | Panel Bailey | 18 DSR1-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 48 | 0.43 | 20.64 |  | 1 | 20.64
W-506C | Panel Bailey | 18 DSR1-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 32 | 0.41 | 13.12 |  | 1 | 13.12
W-506C | Panel Bailey | 18 DSR1-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 112 | 0.474 | 53.088 |  | 1 | 53.088
W-506C | Panel Bailey | 18 DSR1-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 20 | 0.294 | 5.88 |  | 1 | 5.88
W-506C | Panel Bailey | 18 DSR1-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 6 | 0.294 | 1.764 |  | 1 | 1.764
W-506C | Panel Bailey | 18 DSR1-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 96 | 0.244 | 23.424 |  | 1 | 23.424
W-506C | Panel Bailey | 18 DSR1-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.14 | 1.12 |  | 1 | 1.12
W-506C | Panel Bailey | 18 DSR1-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 48 | 0.136 | 6.528 |  | 1 | 6.528
W-506D | Panel Bailey | 18 DSR2-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 102 | 0.46 | 46.92 |  | 1 | 46.92
W-506D | Panel Bailey | 18 DSR2-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 48 | 0.43 | 20.64 |  | 1 | 20.64
W-506D | Panel Bailey | 18 DSR2-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 32 | 0.41 | 13.12 |  | 1 | 13.12
W-506D | Panel Bailey | 18 DSR2-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 112 | 0.474 | 53.088 |  | 1 | 53.088
W-506D | Panel Bailey | 18 DSR2-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.294 | 4.704 |  | 1 | 4.704
W-506D | Panel Bailey | 18 DSR2-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 6 | 0.294 | 1.764 |  | 1 | 1.764
W-506D | Panel Bailey | 18 DSR2-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 96 | 0.244 | 23.424 |  | 1 | 23.424
W-506D | Panel Bailey | 18 DSR2-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 48 | 0.136 | 6.528 |  | 1 | 6.528
W-506E | Panel Bailey | 33 DSR2H*-EW (U120) | M24X130 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.67 | 10.72 |  | 1 | 10.72
W-506E | Panel Bailey | 33 DSR2H*-EW (U120) | M24 x 90 | B/N/2WP - HDG (std) | F10T | 336 | 0.53 | 178.08 |  | 1 | 178.08
W-506E | Panel Bailey | 33 DSR2H*-EW (U120) | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 154 | 0.46 | 70.84 |  | 1 | 70.84
W-506E | Panel Bailey | 33 DSR2H*-EW (U120) | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 88 | 0.43 | 37.84 |  | 1 | 37.84
W-506E | Panel Bailey | 33 DSR2H*-EW (U120) | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 56 | 0.41 | 22.96 |  | 1 | 22.96
W-506E | Panel Bailey | 33 DSR2H*-EW (U120) | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 208 | 0.474 | 98.592 |  | 1 | 98.592
W-506E | Panel Bailey | 33 DSR2H*-EW (U120) | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 148 | 0.294 | 43.512 |  | 1 | 43.512
W-506E | Panel Bailey | 33 DSR2H*-EW (U120) | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 18 | 0.294 | 5.292 |  | 1 | 5.292
W-506E | Panel Bailey | 33 DSR2H*-EW (U120) | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 168 | 0.244 | 40.992 |  | 1 | 40.992
W-506E | Panel Bailey | 33 DSR2H*-EW (U120) | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.136 | 2.176 |  | 1 | 2.176
W-506E | Panel Bailey | 33 DSR2H*-EW (U120) | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 88 | 0.136 | 11.968 |  | 1 | 11.968
W-507 | Panel Bailey | 30 DSR2-EW | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 320 | 0.53 | 169.6 |  | 3 | 508.8
W-507 | Panel Bailey | 30 DSR2-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 170 | 0.46 | 78.2 |  | 3 | 234.6
W-507 | Panel Bailey | 30 DSR2-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.43 | 34.4 |  | 3 | 103.2
W-507 | Panel Bailey | 30 DSR2-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 48 | 0.41 | 19.68 |  | 3 | 59.04
W-507 | Panel Bailey | 30 DSR2-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 176 | 0.474 | 83.424 |  | 3 | 250.272
W-507 | Panel Bailey | 30 DSR2-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.294 | 7.056 |  | 3 | 21.168
W-507 | Panel Bailey | 30 DSR2-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 10 | 0.294 | 2.94 |  | 3 | 8.82
W-507 | Panel Bailey | 30 DSR2-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 160 | 0.244 | 39.04 |  | 3 | 117.12
W-507 | Panel Bailey | 30 DSR2-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.14 | 2.24 |  | 3 | 6.72
W-507 | Panel Bailey | 30 DSR2-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.136 | 10.88 |  | 3 | 32.64
W-573 | Truss Modullar | RB40 | M20X90 | B/N/2WP - HDG (std) | 8.8 | 124 | 0.407 | 50.468 |  | 1 | 50.468
W-573 | Truss Modullar | RB40 | M20X80 | B/N/2WP - HDG (std) | 8.8 | 141 | 0.387 | 54.567 |  | 1 | 54.567
W-573 | Truss Modullar | RB40 | M20X75 | B/N/2WP - HDG (std) | 8.8 | 231 | 0.367 | 84.777 |  | 1 | 84.777
W-573 | Truss Modullar | RB40 | M20X70 | B/N/2WP - HDG (std) | 8.8 | 1838 | 0.357 | 656.166 |  | 1 | 656.166
W-573 | Truss Modullar | RB40 | M20X65 | B/N/2WP - HDG (std) | 8.8 | 872 | 0.347 | 302.584 |  | 1 | 302.584
W-573 | Truss Modullar | RB40 | M20X60 | B/N/2WP - HDG (std) | 8.8 | 1978 | 0.327 | 646.806 |  | 1 | 646.806
W-573 | Truss Modullar | RB40 | M20X55 | B/N/2WP - HDG (std) | 8.8 | 1434 | 0.317 | 454.578 |  | 1 | 454.578
W-573 | Truss Modullar | RB40 | M20X50 | B/N/2WP - HDG (std) | 8.8 | 153 | 0.307 | 46.971 |  | 1 | 46.971
W-573 | Truss Modullar | RB40 | M12X60 | B/N/2WP - HDG (std) | 8.8 | 25 | 0.086 | 2.15 |  | 1 | 2.15
W-573 | Truss Modullar | RB40 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 425 | 0.068 | 28.9 |  | 1 | 28.9
W-573 | Truss Modullar | RB40 | M12X35 | B/N/2WP - HDG (std) | 8.8 | 112 | 0.063 | 7.056 |  | 1 | 7.056
W-573 | Truss Modullar | RB40 | M12X30 | B/N/2WP - HDG (std) | 8.8 | 1158 | 0.059 | 68.322 |  | 1 | 68.322
W-511 | Girder | BG22 | M20X80 | B/N/2WP - HDG (F35) | 8.8 | 701 | 0.387 | 271.287 |  | 1 | 271.287
W-511 | Girder | BG22 | M20X70 | B/N/2WP - HDG (F35) | 8.8 | 495 | 0.357 | 176.715 |  | 1 | 176.715
W-511 | Girder | BG22 | M16X55 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.154 | 2.618 |  | 1 | 2.618
W-511 | Girder | BG22 | M16X50 | B/N/2WP - HDG (std) | 8.8 | 297 | 0.136 | 40.392 |  | 1 | 40.392
W-511 | Girder | BG22 | M12X55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729
W-511 | Girder | BG22 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 433 | 0.081 | 35.073 |  | 1 | 35.073
W-512A | Panel Bailey | 42 DSR2-EW (U120) | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 448 | 0.53 | 237.44 |  | 1 | 237.44
W-512A | Panel Bailey | 42 DSR2-EW (U120) | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 196 | 0.46 | 90.16 |  | 1 | 90.16
W-512A | Panel Bailey | 42 DSR2-EW (U120) | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 112 | 0.43 | 48.16 |  | 1 | 48.16
W-512A | Panel Bailey | 42 DSR2-EW (U120) | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 68 | 0.41 | 27.88 |  | 1 | 27.88
W-512A | Panel Bailey | 42 DSR2-EW (U120) | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 256 | 0.474 | 121.344 |  | 1 | 121.344
W-512A | Panel Bailey | 42 DSR2-EW (U120) | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 184 | 0.294 | 54.096 |  | 1 | 54.096
W-512A | Panel Bailey | 42 DSR2-EW (U120) | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 28 | 0.294 | 8.232 |  | 1 | 8.232
W-512A | Panel Bailey | 42 DSR2-EW (U120) | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 216 | 0.244 | 52.704 |  | 1 | 52.704
W-512A | Panel Bailey | 42 DSR2-EW (U120) | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.136 | 2.176 |  | 1 | 2.176
W-512A | Panel Bailey | 42 DSR2-EW (U120) | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 112 | 0.136 | 15.232 |  | 1 | 15.232
W-512B | Panel Bailey | 45 DSR2H**-EW (U120) | M24X130 | B/N/2WP - HDG (std) | 8.8 | 64 | 0.67 | 42.88 |  | 2 | 85.76
W-512B | Panel Bailey | 45 DSR2H**-EW (U120) | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 480 | 0.53 | 254.4 |  | 2 | 508.8
W-512B | Panel Bailey | 45 DSR2H**-EW (U120) | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 210 | 0.46 | 96.6 |  | 2 | 193.2
W-512B | Panel Bailey | 45 DSR2H**-EW (U120) | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 120 | 0.43 | 51.6 |  | 2 | 103.2
W-512B | Panel Bailey | 45 DSR2H**-EW (U120) | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 72 | 0.41 | 29.52 |  | 2 | 59.04
W-512B | Panel Bailey | 45 DSR2H**-EW (U120) | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 272 | 0.474 | 128.928 |  | 2 | 257.856
W-512B | Panel Bailey | 45 DSR2H**-EW (U120) | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 196 | 0.294 | 57.624 |  | 2 | 115.248
W-512B | Panel Bailey | 45 DSR2H**-EW (U120) | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 22 | 0.294 | 6.468 |  | 2 | 12.936
W-512B | Panel Bailey | 45 DSR2H**-EW (U120) | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 232 | 0.244 | 56.608 |  | 2 | 113.216
W-512B | Panel Bailey | 45 DSR2H**-EW (U120) | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.136 | 2.176 |  | 2 | 4.352
W-512B | Panel Bailey | 45 DSR2H**-EW (U120) | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 120 | 0.136 | 16.32 |  | 2 | 32.64
W-512C | BEAM TRESTLE | TRESTLE BEAM | M20X50 | B/N/2WP - HDG (std) | 8.8 | 75 | 0.254 | 19.05 |  | 1 | 19.05
W-512C | BEAM TRESTLE | TRESTLE BEAM | M10X40 | B/N/2WP - HDG (std) | 8.8 | 99 | 0.136 | 13.464 |  | 1 | 13.464
W-513 | Panel Bailey | 30 DSR2-EW | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 320 | 0.53 | 169.6 |  | 1 | 169.6
W-513 | Panel Bailey | 30 DSR2-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 170 | 0.46 | 78.2 |  | 1 | 78.2
W-513 | Panel Bailey | 30 DSR2-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.43 | 34.4 |  | 1 | 34.4
W-513 | Panel Bailey | 30 DSR2-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 48 | 0.41 | 19.68 |  | 1 | 19.68
W-513 | Panel Bailey | 30 DSR2-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 176 | 0.474 | 83.424 |  | 1 | 83.424
W-513 | Panel Bailey | 30 DSR2-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.294 | 7.056 |  | 1 | 7.056
W-513 | Panel Bailey | 30 DSR2-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 10 | 0.294 | 2.94 |  | 1 | 2.94
W-513 | Panel Bailey | 30 DSR2-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 160 | 0.244 | 39.04 |  | 1 | 39.04
W-513 | Panel Bailey | 30 DSR2-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.14 | 2.24 |  | 1 | 2.24
W-513 | Panel Bailey | 30 DSR2-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.136 | 10.88 |  | 1 | 10.88
W-514 | Girder | CG30 | M24X100 | B/N/2WP - HDG (std) | 8.8 | 231 | 0.407 | 94.017 |  | 1 | 94.017
W-514 | Girder | CG30 | M24X90 | B/N/2WP - HDG (std) | 8.8 | 165 | 0.387 | 63.855 |  | 1 | 63.855
W-514 | Girder | CG30 | M24X75 | B/N/2WP - HDG (std) | 8.8 | 462 | 0.347 | 160.314 |  | 1 | 160.314
W-514 | Girder | CG30 | M20X60 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.154 | 2.618 |  | 1 | 2.618
W-514 | Girder | CG30 | M20X55 | B/N/2WP - HDG (std) | 8.8 | 50 | 0.149 | 7.45 |  | 1 | 7.45
W-514 | Girder | CG30 | M20X50 | B/N/2WP - HDG (std) | 8.8 | 124 | 0.136 | 16.864 |  | 1 | 16.864
W-514 | Girder | CG30 | M12X55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729
W-516A | Panel Bailey | 36 DSR2-EW | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 384 | 0.53 | 203.52 |  | 1 | 203.52
W-516A | Panel Bailey | 36 DSR2-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 204 | 0.46 | 93.84 |  | 1 | 93.84
W-516A | Panel Bailey | 36 DSR2-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 96 | 0.43 | 41.28 |  | 1 | 41.28
W-516A | Panel Bailey | 36 DSR2-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 56 | 0.41 | 22.96 |  | 1 | 22.96
W-516A | Panel Bailey | 36 DSR2-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 208 | 0.474 | 98.592 |  | 1 | 98.592
W-516A | Panel Bailey | 36 DSR2-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.294 | 7.056 |  | 1 | 7.056
W-516A | Panel Bailey | 36 DSR2-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 12 | 0.294 | 3.528 |  | 1 | 3.528
W-516A | Panel Bailey | 36 DSR2-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 192 | 0.244 | 46.848 |  | 1 | 46.848
W-516A | Panel Bailey | 36 DSR2-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.14 | 2.24 |  | 1 | 2.24
W-516A | Panel Bailey | 36 DSR2-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 96 | 0.136 | 13.056 |  | 1 | 13.056
W-516B | Panel Bailey | 30 DSR2-EW | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 320 | 0.53 | 169.6 |  | 2 | 339.2
W-516B | Panel Bailey | 30 DSR2-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 170 | 0.46 | 78.2 |  | 2 | 156.4
W-516B | Panel Bailey | 30 DSR2-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.43 | 34.4 |  | 2 | 68.8
W-516B | Panel Bailey | 30 DSR2-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 48 | 0.41 | 19.68 |  | 2 | 39.36
W-516B | Panel Bailey | 30 DSR2-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 176 | 0.474 | 83.424 |  | 2 | 166.848
W-516B | Panel Bailey | 30 DSR2-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.294 | 7.056 |  | 2 | 14.112
W-516B | Panel Bailey | 30 DSR2-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 10 | 0.294 | 2.94 |  | 2 | 5.88
W-516B | Panel Bailey | 30 DSR2-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 160 | 0.244 | 39.04 |  | 2 | 78.08
W-516B | Panel Bailey | 30 DSR2-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.14 | 2.24 |  | 2 | 4.48
W-516B | Panel Bailey | 30 DSR2-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.136 | 10.88 |  | 2 | 21.76
W-516C | Panel Bailey | 45 TSR2 - EW | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 1080 | 0.53 | 572.4 |  | 1 | 572.4
W-516C | Panel Bailey | 45 TSR2 - EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 210 | 0.46 | 96.6 |  | 1 | 96.6
W-516C | Panel Bailey | 45 TSR2 - EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 120 | 0.43 | 51.6 |  | 1 | 51.6
W-516C | Panel Bailey | 45 TSR2 - EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 104 | 0.41 | 42.64 |  | 1 | 42.64
W-516C | Panel Bailey | 45 TSR2 - EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 272 | 0.474 | 128.928 |  | 1 | 128.928
W-516C | Panel Bailey | 45 TSR2 - EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 144 | 0.294 | 42.336 |  | 1 | 42.336
W-516C | Panel Bailey | 45 TSR2 - EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 45 | 0.294 | 13.23 |  | 1 | 13.23
W-516C | Panel Bailey | 45 TSR2 - EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 288 | 0.244 | 70.272 |  | 1 | 70.272
W-516C | Panel Bailey | 45 TSR2 - EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 48 | 0.14 | 6.72 |  | 1 | 6.72
W-516C | Panel Bailey | 45 TSR2 - EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 120 | 0.136 | 16.32 |  | 1 | 16.32
W-516D | RAMP Panel Bailey | RAMP PANEL BAILEY | M20X50 | B/N/2WP - HDG (std) | 8.8 | 66 | 0.254 | 16.764 |  | 6 | 100.584
W-516D | RAMP Panel Bailey | RAMP PANEL BAILEY | M20X45 | B/N/2WP - HDG (std) | 8.8 | 50 | 0.244 | 12.2 |  | 6 | 73.2
W-517 | Panel Bailey | 30 DSR2-EW | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 320 | 0.53 | 169.6 |  | 1 | 169.6
W-517 | Panel Bailey | 30 DSR2-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 170 | 0.46 | 78.2 |  | 1 | 78.2
W-517 | Panel Bailey | 30 DSR2-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.43 | 34.4 |  | 1 | 34.4
W-517 | Panel Bailey | 30 DSR2-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 48 | 0.41 | 19.68 |  | 1 | 19.68
W-517 | Panel Bailey | 30 DSR2-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 176 | 0.474 | 83.424 |  | 1 | 83.424
W-517 | Panel Bailey | 30 DSR2-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.294 | 7.056 |  | 1 | 7.056
W-517 | Panel Bailey | 30 DSR2-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 10 | 0.294 | 2.94 |  | 1 | 2.94
W-517 | Panel Bailey | 30 DSR2-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 160 | 0.244 | 39.04 |  | 1 | 39.04
W-517 | Panel Bailey | 30 DSR2-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.14 | 2.24 |  | 1 | 2.24
W-517 | Panel Bailey | 30 DSR2-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.136 | 10.88 |  | 1 | 10.88
W-518A | Panel Bailey | 21 SSR-EW | M24 x 90 | B/N/2WP - HDG (std) | F10T | 112 | 0.79 | 88.48 |  | 2 | 176.96
W-518A | Panel Bailey | 21 SSR-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 7 | 0.46 | 3.22 |  | 2 | 6.44
W-518A | Panel Bailey | 21 SSR-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 56 | 0.43 | 24.08 |  | 2 | 48.16
W-518A | Panel Bailey | 21 SSR-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 36 | 0.41 | 14.76 |  | 2 | 29.52
W-518A | Panel Bailey | 21 SSR-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 128 | 0.474 | 60.672 |  | 2 | 121.344
W-518A | Panel Bailey | 21 SSR-EW | M20 x 90 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.354 | 5.664 |  | 2 | 11.328
W-518A | Panel Bailey | 21 SSR-EW | M20 x 80 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.334 | 5.344 |  | 2 | 10.688
W-518A | Panel Bailey | 21 SSR-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.294 | 4.704 |  | 2 | 9.408
W-518A | Panel Bailey | 21 SSR-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 7 | 0.294 | 2.058 |  | 2 | 4.116
W-518A | Panel Bailey | 21 SSR-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 56 | 0.244 | 13.664 |  | 2 | 27.328
W-518A | Panel Bailey | 21 SSR-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.136 | 1.088 |  | 2 | 2.176
W-518A | Panel Bailey | 21 SSR-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 56 | 0.136 | 7.616 |  | 2 | 15.232
W-518B | Panel Bailey | 24 SSR-EW | M24 x 90 | B/N/2WP - HDG (F35) | F10T | 128 | 0.79 | 101.12 |  | 1 | 101.12
W-518B | Panel Bailey | 24 SSR-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.46 | 3.68 |  | 1 | 3.68
W-518B | Panel Bailey | 24 SSR-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 64 | 0.43 | 27.52 |  | 1 | 27.52
W-518B | Panel Bailey | 24 SSR-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 40 | 0.41 | 16.4 |  | 1 | 16.4
W-518B | Panel Bailey | 24 SSR-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 144 | 0.474 | 68.256 |  | 1 | 68.256
W-518B | Panel Bailey | 24 SSR-EW | M20 x 90 | B/N/2WP - HDG (std) | 8.8 | 18 | 0.354 | 6.372 |  | 1 | 6.372
W-518B | Panel Bailey | 24 SSR-EW | M20 x 80 | B/N/2WP - HDG (std) | 8.8 | 18 | 0.334 | 6.012 |  | 1 | 6.012
W-518B | Panel Bailey | 24 SSR-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.294 | 4.704 |  | 1 | 4.704
W-518B | Panel Bailey | 24 SSR-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.294 | 2.352 |  | 1 | 2.352
W-518B | Panel Bailey | 24 SSR-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 64 | 0.244 | 15.616 |  | 1 | 15.616
W-518B | Panel Bailey | 24 SSR-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.136 | 1.088 |  | 1 | 1.088
W-518B | Panel Bailey | 24 SSR-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 64 | 0.136 | 8.704 |  | 1 | 8.704
W-518C | Panel Bailey | 27 DSR2-EW | M24 x 90 | B/N/2WP - HDG (F35) | F10T | 288 | 0.53 | 152.64 |  | 1 | 152.64
W-518C | Panel Bailey | 27 DSR2-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 153 | 0.46 | 70.38 |  | 1 | 70.38
W-518C | Panel Bailey | 27 DSR2-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 72 | 0.43 | 30.96 |  | 1 | 30.96
W-518C | Panel Bailey | 27 DSR2-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 44 | 0.41 | 18.04 |  | 1 | 18.04
W-518C | Panel Bailey | 27 DSR2-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 160 | 0.474 | 75.84 |  | 1 | 75.84
W-518C | Panel Bailey | 27 DSR2-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.294 | 7.056 |  | 1 | 7.056
W-518C | Panel Bailey | 27 DSR2-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.294 | 2.646 |  | 1 | 2.646
W-518C | Panel Bailey | 27 DSR2-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 144 | 0.244 | 35.136 |  | 1 | 35.136
W-518C | Panel Bailey | 27 DSR2-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.14 | 2.24 |  | 1 | 2.24
W-518C | Panel Bailey | 27 DSR2-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 72 | 0.136 | 9.792 |  | 1 | 9.792
W-519 | Panel Bailey | 39 DSR2H**-EW | M24X130 | B/N/2WP - HDG (std) | 8.8 | 33 | 0.67 | 22.11 |  | 1 | 22.11
W-519 | Panel Bailey | 39 DSR2H**-EW | M24 x 90 | B/N/2WP - HDG (std) | F10T | 429 | 0.79 | 338.91 |  | 1 | 338.91
W-519 | Panel Bailey | 39 DSR2H**-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 228 | 0.46 | 104.88 |  | 1 | 104.88
W-519 | Panel Bailey | 39 DSR2H**-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 54 | 0.43 | 23.22 |  | 1 | 23.22
W-519 | Panel Bailey | 39 DSR2H**-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 83 | 0.41 | 34.03 |  | 1 | 34.03
W-519 | Panel Bailey | 39 DSR2H**-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 264 | 0.474 | 125.136 |  | 1 | 125.136
W-519 | Panel Bailey | 39 DSR2H**-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 25 | 0.294 | 7.35 |  | 1 | 7.35
W-519 | Panel Bailey | 39 DSR2H**-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 88 | 0.254 | 22.352 |  | 1 | 22.352
W-519 | Panel Bailey | 39 DSR2H**-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 54 | 0.244 | 13.176 |  | 1 | 13.176
W-519 | Panel Bailey | 39 DSR2H**-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.136 | 2.312 |  | 1 | 2.312
W-519 | Panel Bailey | 39 DSR2H**-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 108 | 0.136 | 14.688 |  | 1 | 14.688
W-519 | Panel Bailey | 39 DSR2H**-EW | M24X130 | B/N/2WP - HDG (std) | 8.8 | 32 | 0.67 | 21.44 |  | 1 | 21.44
W-519 | Panel Bailey | 39 DSR2H**-EW | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 416 | 0.53 | 220.48 |  | 1 | 220.48
W-519 | Panel Bailey | 39 DSR2H**-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 182 | 0.46 | 83.72 |  | 1 | 83.72
W-519 | Panel Bailey | 39 DSR2H**-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 104 | 0.43 | 44.72 |  | 1 | 44.72
W-519 | Panel Bailey | 39 DSR2H**-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 64 | 0.41 | 26.24 |  | 1 | 26.24
W-519 | Panel Bailey | 39 DSR2H**-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 240 | 0.474 | 113.76 |  | 1 | 113.76
W-519 | Panel Bailey | 39 DSR2H**-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 172 | 0.294 | 50.568 |  | 1 | 50.568
W-519 | Panel Bailey | 39 DSR2H**-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 18 | 0.294 | 5.292 |  | 1 | 5.292
W-519 | Panel Bailey | 39 DSR2H**-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 200 | 0.244 | 48.8 |  | 1 | 48.8
W-519 | Panel Bailey | 39 DSR2H**-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.136 | 2.176 |  | 1 | 2.176
W-519 | Panel Bailey | 39 DSR2H**-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 104 | 0.136 | 14.144 |  | 1 | 14.144
W-520A | Girder Spesial | GD14 | M19X76 | B/N/2WP - HDG (F436) | A325 | 99 | 0.394 | 39.006 |  | 1 | 39.006
W-520A | Girder Spesial | GD14 | M19X69 | B/N/2WP - HDG (F436) | A325 | 149 | 0.38 | 56.62 |  | 1 | 56.62
W-520A | Girder Spesial | GD14 | M15X63 | B/N/2WP - HDG (std) | A325 | 124 | 0.237 | 29.388 |  | 1 | 29.388
W-520A | Girder Spesial | GD14 | M15X57 | B/N/2WP - HDG (std) | A325 | 145 | 0.229 | 33.205 |  | 1 | 33.205
W-520A | Girder Spesial | GD14 | M12X50 | B/N/2WP - HDG (std) | 8.8 | 99 | 0.072 | 7.128 |  | 1 | 7.128
W-520A | Girder Spesial | GD14 | M12X45 | B/N/2WP - HDG (std) | 8.8 | 54 | 0.072 | 3.888 |  | 1 | 3.888
W-520B | Girder Spesial | GD16 | M19X76 | B/N/2WP - HDG (F436) | A325 | 99 | 0.394 | 39.006 |  | 5 | 195.03
W-520B | Girder Spesial | GD16 | M19X69 | B/N/2WP - HDG (F436) | A325 | 149 | 0.38 | 56.62 |  | 5 | 283.1
W-520B | Girder Spesial | GD16 | M15X63 | B/N/2WP - HDG (std) | A325 | 309 | 0.237 | 73.233 |  | 5 | 366.165
W-520B | Girder Spesial | GD16 | M12X50 | B/N/2WP - HDG (std) | A325 | 116 | 0.077 | 8.932 |  | 5 | 44.66
W-520B | Girder Spesial | GD16 | M12X45 | B/N/2WP - HDG (std) | 8.8 | 58 | 0.072 | 4.176 |  | 5 | 20.88
W-520B | Girder Spesial | GD16 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 198 | 0.068 | 13.464 |  | 5 | 67.32
W-520C | Girder Spesial | GD18 | M19X76 | B/N/2WP - HDG (F436) | A325 | 132 | 0.394 | 52.008 |  | 3 | 156.024
W-520C | Girder Spesial | GD18 | M19X69 | B/N/2WP - HDG (F436) | A325 | 231 | 0.38 | 87.78 |  | 3 | 263.34
W-520C | Girder Spesial | GD18 | M15X63 | B/N/2WP - HDG (std) | A325 | 351 | 0.237 | 83.187 |  | 3 | 249.561
W-520C | Girder Spesial | GD18 | M12X50 | B/N/2WP - HDG (std) | 8.8 | 165 | 0.229 | 37.785 |  | 3 | 113.355
W-520C | Girder Spesial | GD18 | M12X44 | B/N/2WP - HDG (std) | 8.8 | 71 | 0.133 | 9.443 |  | 3 | 28.329
W-520C | Girder Spesial | GD18 | M12X38 | B/N/2WP - HDG (std) | 8.8 | 223 | 0.127 | 28.321 |  | 3 | 84.963
W-520D | Girder Spesial | GD20 | M19X83 | B/N/2WP - HDG (F436) | A325 | 165 | 0.408 | 67.32 |  | 1 | 67.32
W-520D | Girder Spesial | GD20 | M19X70 | B/N/2WP - HDG (F436) | A325 | 289 | 0.38 | 109.82 |  | 1 | 109.82
W-520D | Girder Spesial | GD20 | M15X63 | B/N/2WP - HDG (std) | A325 | 392 | 0.237 | 92.904 |  | 1 | 92.904
W-520D | Girder Spesial | GD20 | M12X50 | B/N/2WP - HDG (std) | 8.8 | 149 | 0.077 | 11.473 |  | 1 | 11.473
W-520D | Girder Spesial | GD20 | M12X45 | B/N/2WP - HDG (std) | 8.8 | 75 | 0.072 | 5.4 |  | 1 | 5.4
W-521 | Girder | BG25 | M20X90 | B/N/2WP - HDG (F35) | 8.8 | 577 | 0.407 | 234.839 |  | 1 | 234.839
W-521 | Girder | BG25 | M20X80 | B/N/2WP - HDG (F35) | 8.8 | 289 | 0.387 | 111.843 |  | 1 | 111.843
W-521 | Girder | BG25 | M20X70 | B/N/2WP - HDG (F35) | 8.8 | 680 | 0.357 | 242.76 |  | 1 | 242.76
W-521 | Girder | BG25 | M20X50 | B/N/2WP - HDG (F35) | 8.8 | 17 | 0.307 | 5.219 |  | 1 | 5.219
W-521 | Girder | BG25 | M16X55 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.154 | 2.618 |  | 1 | 2.618
W-521 | Girder | BG25 | M16X45 | B/N/2WP - HDG (std) | 8.8 | 182 | 0.136 | 24.752 |  | 1 | 24.752
W-521 | Girder | BG25 | M12X55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729
W-521 | Girder | BG25 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 495 | 0.068 | 33.66 |  | 1 | 33.66
W-523 | Girder | BG25 | M20X80 | B/N/2WP - HDG (F35) | 8.8 | 433 | 0.334 | 144.622 |  | 1 | 144.622
W-523 | Girder | BG25 | M20X70 | B/N/2WP - HDG (F35) | 8.8 | 433 | 0.304 | 131.632 |  | 1 | 131.632
W-523 | Girder | BG25 | M20X65 | B/N/2WP - HDG (F35) | 8.8 | 454 | 0.294 | 133.476 |  | 1 | 133.476
W-523 | Girder | BG25 | M16X55 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.154 | 2.618 |  | 1 | 2.618
W-523 | Girder | BG25 | M16X50 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.149 | 1.341 |  | 1 | 1.341
W-523 | Girder | BG25 | M16X45 | B/N/2WP - HDG (std) | 8.8 | 190 | 0.136 | 25.84 |  | 1 | 25.84
W-523 | Girder | BG25 | M12X55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729
W-523 | Girder | BG25 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 515 | 0.068 | 35.02 |  | 1 | 35.02
W-525 | Girder | BG30 | M24X120 | B/N/2WP - HDG (F35) | 8.8 | 1236 | 0.792 | 978.912 |  | 1 | 978.912
W-525 | Girder | BG30 | M24X100 | B/N/2WP - HDG (F35) | 8.8 | 742 | 0.722 | 535.724 |  | 1 | 535.724
W-525 | Girder | BG30 | M24X90 | B/N/2WP - HDG (F35) | 8.8 | 1236 | 0.682 | 842.952 |  | 1 | 842.952
W-525 | Girder | BG30 | M20X60 | B/N/2WP - HDG (std) | 8.8 | 338 | 0.274 | 92.612 |  | 1 | 92.612
W-525 | Girder | BG30 | M12X55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729
W-526 | Girder | CG30 | M24x90 | B/N/2WP - HDG (F35) | 8.8 | 528 | 0.53 | 279.84 |  | 1 | 279.84
W-526 | Girder | CG30 | M24x70 | B/N/2WP - HDG (F35) | 8.8 | 429 | 0.46 | 197.34 |  | 1 | 197.34
W-526 | Girder | CG30 | M20x60 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.274 | 4.658 |  | 1 | 4.658
W-526 | Girder | CG30 | M20x55 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.264 | 4.488 |  | 1 | 4.488
W-526 | Girder | CG30 | M20x50 | B/N/2WP - HDG (std) | 8.8 | 157 | 0.254 | 39.878 |  | 1 | 39.878
W-526 | Girder | CG30 | M12X55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729
W-526 | Girder | CG30 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 478 | 0.06 | 28.68 |  | 1 | 28.68
W-527 | Girder | BG35 | M25X101 | B/N/2WP - HDG (F436) | A325 | 1319 | 0.867 | 1143.573 |  | 1 | 1143.573
W-527 | Girder | BG35 | M25X88 | B/N/2WP - HDG (F436) | A325 | 1154 | 0.817 | 942.818 |  | 1 | 942.818
W-527 | Girder | BG35 | M19X69 | B/N/2WP - HDG (std) | A325 | 17 | 0.38 | 6.46 |  | 1 | 6.46
W-527 | Girder | BG35 | M19X57 | B/N/2WP - HDG (std) | A325 | 264 | 0.351 | 92.664 |  | 1 | 92.664
W-527 | Girder | BG35 | M12X55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729
W-527 | Girder | BG35 | M12X45 | B/N/2WP - HDG (std) | 8.8 | 660 | 0.072 | 47.52 |  | 1 | 47.52
W-528 | Girder | BG20 | M20X100 | B/N/2WP - HDG (F35) | 8.8 | 371 | 0.427 | 158.417 |  | 1 | 158.417
W-528 | Girder | BG20 | M20X90 | B/N/2WP - HDG (F35) | 8.8 | 206 | 0.407 | 83.842 |  | 1 | 83.842
W-528 | Girder | BG20 | M20X70 | B/N/2WP - HDG (F35) | 8.8 | 412 | 0.357 | 147.084 |  | 1 | 147.084
W-528 | Girder | BG20 | M16X60 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.159 | 2.703 |  | 1 | 2.703
W-528 | Girder | BG20 | M16X50 | B/N/2WP - HDG (std) | 8.8 | 297 | 0.149 | 44.253 |  | 1 | 44.253
W-528 | Girder | BG20 | M12X55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729
W-528 | Girder | BG20 | M12X45 | B/N/2WP - HDG (std) | 8.8 | 412 | 0.072 | 29.664 |  | 1 | 29.664
W-529 | Truss Modullar | RB50 | M20X90 | B/N/2WP - HDG (F35) | 8.8 | 252 | 0.407 | 102.564 |  | 2 | 205.128
W-529 | Truss Modullar | RB50 | M20X80 | B/N/2WP - HDG (F35) | 8.8 | 421 | 0.387 | 162.927 |  | 2 | 325.854
W-529 | Truss Modullar | RB50 | M20X75 | B/N/2WP - HDG (F35) | 8.8 | 2320 | 0.367 | 851.44 |  | 2 | 1702.88
W-529 | Truss Modullar | RB50 | M20X70 | B/N/2WP - HDG (F35) | 8.8 | 1459 | 0.357 | 520.863 |  | 2 | 1041.726
W-529 | Truss Modullar | RB50 | M20X65 | B/N/2WP - HDG (F35) | 8.8 | 882 | 0.347 | 306.054 |  | 2 | 612.108
W-529 | Truss Modullar | RB50 | M20X60 | B/N/2WP - HDG (F35) | 8.8 | 4059 | 0.327 | 1327.293 |  | 2 | 2654.586
W-529 | Truss Modullar | RB50 | M20X55 | B/N/2WP - HDG (F35) | 8.8 | 182 | 0.317 | 57.694 |  | 2 | 115.388
W-529 | Truss Modullar | RB50 | M12X60 | B/N/2WP - HDG (std) | 8.8 | 25 | 0.307 | 7.675 |  | 2 | 15.35
W-529 | Truss Modullar | RB50 | M12X45 | B/N/2WP - HDG (std) | 8.8 | 33 | 0.086 | 2.838 |  | 2 | 5.676
W-529 | Truss Modullar | RB50 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 557 | 0.072 | 40.104 |  | 2 | 80.208
W-529 | Truss Modullar | RB50 | M12X35 | B/N/2WP - HDG (std) | 8.8 | 95 | 0.068 | 6.46 |  | 2 | 12.92
W-529 | Truss Modullar | RB50 | M12X30 | B/N/2WP - HDG (std) | 8.8 | 1447 | 0.063 | 91.161 |  | 2 | 182.322
W-531 | Girder | CG15_6 Line | M20X80 | B/N/2WP - HDG (F35) | 8.8 | 693 | 0.387 | 268.191 |  | 1 | 268.191
W-531 | Girder | CG15_6 Line | M20X75 | B/N/2WP - HDG (F35) | 8.8 | 396 | 0.367 | 145.332 |  | 1 | 145.332
W-531 | Girder | CG15_6 Line | M20X50 | B/N/2WP - HDG (F35) | 8.8 | 198 | 0.307 | 60.786 |  | 1 | 60.786
W-532 | Girder | BG30 | M24X90 | B/N/2WP - HDG (F35) | 8.8 | 330 | 0.682 | 225.06 |  | 1 | 225.06
W-532 | Girder | BG30 | M24X75 | B/N/2WP - HDG (F35) | 8.8 | 866 | 0.632 | 547.312 |  | 1 | 547.312
W-532 | Girder | BG30 | M20X60 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.274 | 4.658 |  | 1 | 4.658
W-532 | Girder | BG30 | M20X55 | B/N/2WP - HDG (std) | 8.8 | 33 | 0.264 | 8.712 |  | 1 | 8.712
W-532 | Girder | BG30 | M20X50 | B/N/2WP - HDG (std) | 8.8 | 165 | 0.254 | 41.91 |  | 1 | 41.91
W-532 | Girder | BG30 | M12X55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729
W-532 | Girder | BG30 | M12X35 | B/N/2WP - HDG (std) | 8.8 | 598 | 0.063 | 37.674 |  | 1 | 37.674
W-532A | ORNAMEN PIPA | GB30-ARCH | M20X55 | B/N/2WP - HDG (std) | 8.8 | 198 | 0.264 | 52.272 |  | 1 | 52.272
W-532A | ORNAMEN PIPA | GB30-ARCH | M20X45 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.244 | 4.148 |  | 1 | 4.148
W-532A | ORNAMEN PIPA | GB30-ARCH | M16X55 | B/N/2WP - HDG (std) | 8.8 | 112 | 0.154 | 17.248 |  | 1 | 17.248
W-532A | ORNAMEN PIPA | GB30-ARCH | M12X35 | B/N/2WP - HDG (std) | 8.8 | 99 | 0.063 | 6.237 |  | 1 | 6.237
W-535 | Jembatan Gantung | JG80 | M24X85 | B/N/2WP - HDG (+F35) | F10T | 17 | 0.652 | 11.084 |  | 1 | 11.084
W-535 | Jembatan Gantung | JG80 | M20X70 | B/N/2WP - HDG (std) | 8.8 | 581 | 0.304 | 176.624 |  | 1 | 176.624
W-535 | Jembatan Gantung | JG80 | M16X70 | B/N/2WP - HDG (std) | 8.8 | 242 | 0.179 | 43.318 |  | 1 | 43.318
W-535 | Jembatan Gantung | JG80 | M16X65 | B/N/2WP - HDG (std) | 8.8 | 81 | 0.169 | 13.689 |  | 1 | 13.689
W-535 | Jembatan Gantung | JG80 | M12X45 | B/N/2WP - HDG (std) | 8.8 | 890 | 0.072 | 64.08 |  | 1 | 64.08
W-535 | Jembatan Gantung | JG80 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 660 | 0.068 | 44.88 |  | 1 | 44.88
W-535 | Jembatan Gantung | JG80 | M10X30 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.05 | 0.85 |  | 1 | 0.85
W-535 | Jembatan Gantung | JG80 | M6X20 | B/N/2WP - HDG (std) | 8.8 | 33 | 0.03 | 0.99 |  | 1 | 0.99
W-536 | Girder | CG30 | M24x90 | B/N/2WP - HDG (F35) | 8.8 | 528 | 0.53 | 279.84 |  | 1 | 279.84
W-536 | Girder | CG30 | M24x70 | B/N/2WP - HDG (F35) | 8.8 | 429 | 0.46 | 197.34 |  | 1 | 197.34
W-536 | Girder | CG30 | M20x60 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.274 | 4.658 |  | 1 | 4.658
W-536 | Girder | CG30 | M20x55 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.264 | 4.488 |  | 1 | 4.488
W-536 | Girder | CG30 | M20x50 | B/N/2WP - HDG (std) | 8.8 | 157 | 0.254 | 39.878 |  | 1 | 39.878
W-536 | Girder | CG30 | M12X55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729
W-536 | Girder | CG30 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 478 | 0.06 | 28.68 |  | 1 | 28.68
W-537 | Panel Bailey | 30 SSR-EW | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 160 | 0.53 | 84.8 |  | 3 | 254.4
W-537 | Panel Bailey | 30 SSR-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 10 | 0.46 | 4.6 |  | 3 | 13.8
W-537 | Panel Bailey | 30 SSR-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.43 | 34.4 |  | 3 | 103.2
W-537 | Panel Bailey | 30 SSR-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 48 | 0.41 | 19.68 |  | 3 | 59.04
W-537 | Panel Bailey | 30 SSR-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 176 | 0.474 | 83.424 |  | 3 | 250.272
W-537 | Panel Bailey | 30 SSR-EW | M20 x 90 | B/N/2WP - HDG (std) | 8.8 | 22 | 0.354 | 7.788 |  | 3 | 23.364
W-537 | Panel Bailey | 30 SSR-EW | M20 x 80 | B/N/2WP - HDG (std) | 8.8 | 22 | 0.334 | 7.348 |  | 3 | 22.044
W-537 | Panel Bailey | 30 SSR-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.294 | 4.704 |  | 3 | 14.112
W-537 | Panel Bailey | 30 SSR-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 10 | 0.294 | 2.94 |  | 3 | 8.82
W-537 | Panel Bailey | 30 SSR-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.244 | 19.52 |  | 3 | 58.56
W-537 | Panel Bailey | 30 SSR-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.136 | 1.088 |  | 3 | 3.264
W-537 | Panel Bailey | 30 SSR-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.136 | 10.88 |  | 3 | 32.64
W-538 | Truss Modullar | RB60 | M20X100 | B/N/2WP - HDG (F35) | 8.8 | 347 | 0.427 | 148.169 |  | 1 | 148.169
W-538 | Truss Modullar | RB60 | M20X90 | B/N/2WP - HDG (F35) | 8.8 | 1558 | 0.407 | 634.106 |  | 1 | 634.106
W-538 | Truss Modullar | RB60 | M20X80 | B/N/2WP - HDG (F35) | 8.8 | 2794 | 0.387 | 1081.278 |  | 1 | 1081.278
W-538 | Truss Modullar | RB60 | M20X75 | B/N/2WP - HDG (F35) | 8.8 | 2522 | 0.367 | 925.574 |  | 1 | 925.574
W-538 | Truss Modullar | RB60 | M20X70 | B/N/2WP - HDG (F35) | 8.8 | 1138 | 0.357 | 406.266 |  | 1 | 406.266
W-538 | Truss Modullar | RB60 | M20X65 | B/N/2WP - HDG (F35) | 8.8 | 956 | 0.347 | 331.732 |  | 1 | 331.732
W-538 | Truss Modullar | RB60 | M20X60 | B/N/2WP - HDG (F35) | 8.8 | 4963 | 0.327 | 1622.901 |  | 1 | 1622.901
W-538 | Truss Modullar | RB60 | M20X55 | B/N/2WP - HDG (F35) | 8.8 | 132 | 0.317 | 41.844 |  | 1 | 41.844
W-538 | Truss Modullar | RB60 | M20X50 | B/N/2WP - HDG (F35) | 8.8 | 112 | 0.307 | 34.384 |  | 1 | 34.384
W-538 | Truss Modullar | RB60 | M12X60 | B/N/2WP - HDG (std) | 8.8 | 25 | 0.086 | 2.15 |  | 1 | 2.15
W-538 | Truss Modullar | RB60 | M12X45 | B/N/2WP - HDG (std) | 8.8 | 544 | 0.072 | 39.168 |  | 1 | 39.168
W-538 | Truss Modullar | RB60 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 540 | 0.068 | 36.72 |  | 1 | 36.72
W-538 | Truss Modullar | RB60 | M12X35 | B/N/2WP - HDG (std) | 8.8 | 1805 | 0.063 | 113.715 |  | 1 | 113.715
W-540 | SUPPORT BEAM | SB35 | 1"x5-1/2" | B/N/2WP - HDG (F436) | A325 | 50 | 1.017 | 50.85 |  | 1 | 50.85
W-540 | SUPPORT BEAM | SB35 | 1"x4-1/2" | B/N/2WP - HDG (F436) | A325 | 248 | 0.917 | 227.416 |  | 1 | 227.416
W-540 | SUPPORT BEAM | SB35 | 1"x3-3/4" | B/N/2WP - HDG (F436) | A325 | 557 | 0.844 | 470.108 |  | 1 | 470.108
W-540 | SUPPORT BEAM | SB35 | 7/8"x2-3/4" | B/N/2WP - HDG (std) | A325 | 25 | 0.552 | 13.8 |  | 1 | 13.8
W-541 | Girder | CG12 | M20X75 | B/N/2WP - HDG (F35) | 8.8 | 396 | 0.367 | 145.332 |  | 1 | 145.332
W-541 | Girder | CG12 | M20X70 | B/N/2WP - HDG (F35) | 8.8 | 198 | 0.357 | 70.686 |  | 1 | 70.686
W-541 | Girder | CG12 | M16X50 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.149 | 2.533 |  | 1 | 2.533
W-541 | Girder | CG12 | M16X45 | B/N/2WP - HDG (std) | 8.8 | 124 | 0.136 | 16.864 |  | 1 | 16.864
W-541 | Girder | CG12 | M12X55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729
W-541 | Girder | CG12 | M12X45 | B/N/2WP - HDG (std) | 8.8 | 182 | 0.063 | 11.466 |  | 1 | 11.466
W-542 | Jembatan Gantung | JG360_TAHAP I | M30X120 | B/N/2WP - HDG (F35) | 8.8 | 116 | 1.38 | 160.08 |  | 1 | 160.08
W-542 | Jembatan Gantung | JG360_TAHAP I | M24X110 | B/N/2WP - HDG (F35) | 8.8 | 3560 | 0.762 | 2712.72 |  | 1 | 2712.72
W-542 | Jembatan Gantung | JG360_TAHAP I | M24X100 | B/N/2WP - HDG (F35) | 8.8 | 1978 | 0.722 | 1428.116 |  | 1 | 1428.116
W-542 | Jembatan Gantung | JG360_TAHAP I | M20X55 | B/N/2WP - HDG (std) | 8.8 | 1978 | 0.264 | 522.192 |  | 1 | 522.192
W-542 | Jembatan Gantung | JG360_TAHAP I | M20X50 | B/N/2WP - HDG (std) | 8.8 | 6592 | 0.254 | 1674.368 |  | 1 | 1674.368
W-543 | Girder | GB30 | M24X90 | B/N/2WP - HDG (+F35) | 8.8 | 330 | 0.53 | 174.9 |  | 1 | 174.9
W-543 | Girder | GB30 | M24X80 | B/N/2WP - HDG (+F35) | 8.8 | 330 | 0.5 | 165 |  | 1 | 165
W-543 | Girder | GB30 | M24X70 | B/N/2WP - HDG (+F35) | 8.8 | 577 | 0.46 | 265.42 |  | 1 | 265.42
W-543 | Girder | GB30 | M20X60 | B/N/2WP - HDG (std) | 8.8 | 66 | 0.274 | 18.084 |  | 1 | 18.084
W-543 | Girder | GB30 | M20X55 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.264 | 4.488 |  | 1 | 4.488
W-543 | Girder | GB30 | M20X50 | B/N/2WP - HDG (std) | 8.8 | 165 | 0.254 | 41.91 |  | 1 | 41.91
W-543 | Girder | GB30 | M12X55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729
W-543 | Girder | GB30 | M12X35 | B/N/2WP - HDG (std) | 8.8 | 598 | 0.068 | 40.664 |  | 1 | 40.664
W-544 | Panel Bailey | 9 SSR-EW | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 48 | 0.53 | 25.44 |  | 2 | 50.88
W-544 | Panel Bailey | 9 SSR-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 3 | 0.46 | 1.38 |  | 2 | 2.76
W-544 | Panel Bailey | 9 SSR-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.43 | 10.32 |  | 2 | 20.64
W-544 | Panel Bailey | 9 SSR-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 20 | 0.41 | 8.2 |  | 2 | 16.4
W-544 | Panel Bailey | 9 SSR-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 64 | 0.474 | 30.336 |  | 2 | 60.672
W-544 | Panel Bailey | 9 SSR-EW | M20 x 90 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.354 | 2.832 |  | 2 | 5.664
W-544 | Panel Bailey | 9 SSR-EW | M20 x 80 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.334 | 2.672 |  | 2 | 5.344
W-544 | Panel Bailey | 9 SSR-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.294 | 4.704 |  | 2 | 9.408
W-544 | Panel Bailey | 9 SSR-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 3 | 0.294 | 0.882 |  | 2 | 1.764
W-544 | Panel Bailey | 9 SSR-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.244 | 5.856 |  | 2 | 11.712
W-544 | Panel Bailey | 9 SSR-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.136 | 1.088 |  | 2 | 2.176
W-544 | Panel Bailey | 9 SSR-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.136 | 3.264 |  | 2 | 6.528
W-545 | Jembatan Gantung | JG150 | M24X90 | B/N/2WP - HDG (+F35) | 8.8 | 488 | 0.53 | 258.64 |  | 1 | 258.64
W-545 | Jembatan Gantung | JG150 | M20X70 | B/N/2WP - HDG (+F35) | 8.8 | 1044 | 0.304 | 317.376 |  | 1 | 317.376
W-545 | Jembatan Gantung | JG150 | M20X65 | B/N/2WP - HDG (+F35) | 8.8 | 2964 | 0.274 | 812.136 |  | 1 | 812.136
W-545 | Jembatan Gantung | JG150 | M20X60 | B/N/2WP - HDG (+F35) | 8.8 | 16 | 0.274 | 4.384 |  | 1 | 4.384
W-545 | Jembatan Gantung | JG150 | M20X55 | B/N/2WP - HDG (+F35) | 8.8 | 640 | 0.274 | 175.36 |  | 1 | 175.36
W-545 | Jembatan Gantung | JG150 | M16X65 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.169 | 2.704 |  | 1 | 2.704
W-545 | Jembatan Gantung | JG150 | M16X50 | B/N/2WP - HDG (std) | 8.8 | 2100 | 0.149 | 312.9 |  | 1 | 312.9
W-545 | Jembatan Gantung | JG150 | M16X45 | B/N/2WP - HDG (std) | 8.8 | 600 | 0.136 | 81.6 |  | 1 | 81.6
W-545 | Jembatan Gantung | JG150 | M16X40 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.129 | 1.032 |  | 1 | 1.032
W-545 | Jembatan Gantung | JG150 | M12X45 | B/N/2WP - HDG (std) | 8.8 | 2368 | 0.072 | 170.496 |  | 1 | 170.496
W-545 | Jembatan Gantung | JG150 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 976 | 0.068 | 66.368 |  | 1 | 66.368
W-546 | Panel Bailey | 39 DSR2H**-EW | M24X130 | B/N/2WP - HDG (std) | 8.8 | 33 | 0.67 | 22.11 |  | 1 | 22.11
W-546 | Panel Bailey | 39 DSR2H**-EW | M24 x 90 | B/N/2WP - HDG (std) | F10T | 429 | 0.79 | 338.91 |  | 1 | 338.91
W-546 | Panel Bailey | 39 DSR2H**-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 228 | 0.46 | 104.88 |  | 1 | 104.88
W-546 | Panel Bailey | 39 DSR2H**-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 54 | 0.43 | 23.22 |  | 1 | 23.22
W-546 | Panel Bailey | 39 DSR2H**-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 83 | 0.41 | 34.03 |  | 1 | 34.03
W-546 | Panel Bailey | 39 DSR2H**-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 264 | 0.474 | 125.136 |  | 1 | 125.136
W-546 | Panel Bailey | 39 DSR2H**-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 25 | 0.294 | 7.35 |  | 1 | 7.35
W-546 | Panel Bailey | 39 DSR2H**-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 88 | 0.254 | 22.352 |  | 1 | 22.352
W-546 | Panel Bailey | 39 DSR2H**-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 54 | 0.244 | 13.176 |  | 1 | 13.176
W-546 | Panel Bailey | 39 DSR2H**-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.136 | 2.312 |  | 1 | 2.312
W-546 | Panel Bailey | 39 DSR2H**-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 108 | 0.136 | 14.688 |  | 1 | 14.688
W-549 | Truss Modullar | RB40 | M20X90 | B/N/2WP - HDG (std) | 8.8 | 124 | 0.407 | 50.468 |  | 1 | 50.468
W-549 | Truss Modullar | RB40 | M20X80 | B/N/2WP - HDG (std) | 8.8 | 141 | 0.387 | 54.567 |  | 1 | 54.567
W-549 | Truss Modullar | RB40 | M20X75 | B/N/2WP - HDG (std) | 8.8 | 231 | 0.367 | 84.777 |  | 1 | 84.777
W-549 | Truss Modullar | RB40 | M20X70 | B/N/2WP - HDG (std) | 8.8 | 1838 | 0.357 | 656.166 |  | 1 | 656.166
W-549 | Truss Modullar | RB40 | M20X65 | B/N/2WP - HDG (std) | 8.8 | 872 | 0.347 | 302.584 |  | 1 | 302.584
W-549 | Truss Modullar | RB40 | M20X60 | B/N/2WP - HDG (std) | 8.8 | 1978 | 0.327 | 646.806 |  | 1 | 646.806
W-549 | Truss Modullar | RB40 | M20X55 | B/N/2WP - HDG (std) | 8.8 | 1434 | 0.317 | 454.578 |  | 1 | 454.578
W-549 | Truss Modullar | RB40 | M20X50 | B/N/2WP - HDG (std) | 8.8 | 153 | 0.307 | 46.971 |  | 1 | 46.971
W-549 | Truss Modullar | RB40 | M12X60 | B/N/2WP - HDG (std) | 8.8 | 25 | 0.086 | 2.15 |  | 1 | 2.15
W-549 | Truss Modullar | RB40 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 425 | 0.068 | 28.9 |  | 1 | 28.9
W-549 | Truss Modullar | RB40 | M12X35 | B/N/2WP - HDG (std) | 8.8 | 112 | 0.063 | 7.056 |  | 1 | 7.056
W-549 | Truss Modullar | RB40 | M12X30 | B/N/2WP - HDG (std) | 8.8 | 1158 | 0.059 | 68.322 |  | 1 | 68.322
W-550 | Panel Bailey | 30 DSR2-EW | M24 x 90 | B/N/2WP - HDG (std) | F10T | 320 | 0.53 | 169.6 |  | 1 | 169.6
W-550 | Panel Bailey | 30 DSR2-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 170 | 0.46 | 78.2 |  | 1 | 78.2
W-550 | Panel Bailey | 30 DSR2-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.43 | 34.4 |  | 1 | 34.4
W-550 | Panel Bailey | 30 DSR2-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 48 | 0.41 | 19.68 |  | 1 | 19.68
W-550 | Panel Bailey | 30 DSR2-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 176 | 0.474 | 83.424 |  | 1 | 83.424
W-550 | Panel Bailey | 30 DSR2-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.294 | 7.056 |  | 1 | 7.056
W-550 | Panel Bailey | 30 DSR2-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 10 | 0.294 | 2.94 |  | 1 | 2.94
W-550 | Panel Bailey | 30 DSR2-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 160 | 0.244 | 39.04 |  | 1 | 39.04
W-550 | Panel Bailey | 30 DSR2-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.14 | 2.24 |  | 1 | 2.24
W-550 | Panel Bailey | 30 DSR2-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.136 | 10.88 |  | 1 | 10.88
W-551 | Girder | AG40 | M24X110 | B/N/2WP - HDG (+F35) | 8.8 | 1681 | 0.762 | 1280.922 |  | 1 | 1280.922
W-551 | Girder | AG40 | M24X90 | B/N/2WP - HDG (+F35) | 8.8 | 989 | 0.682 | 674.498 |  | 1 | 674.498
W-551 | Girder | AG40 | M24X75 | B/N/2WP - HDG (+F35) | 8.8 | 2670 | 0.632 | 1687.44 |  | 1 | 1687.44
W-551 | Girder | AG40 | M20X60 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.327 | 5.559 |  | 1 | 5.559
W-551 | Girder | AG40 | M20X55 | B/N/2WP - HDG (std) | 8.8 | 437 | 0.317 | 138.529 |  | 1 | 138.529
W-551 | Girder | AG40 | M16X50 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.149 | 2.533 |  | 1 | 2.533
W-551 | Girder | AG40 | M12X55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729
W-551 | Girder | AG40 | M12X35 | B/N/2WP - HDG (std) | 8.8 | 890 | 0.063 | 56.07 |  | 1 | 56.07
W-552 | JPO | JPO-48 | M20X90 | B/N/2WP - HDG (std) | 8.8 | 396 | 0.354 | 140.184 |  | 1 | 140.184
W-552 | JPO | JPO-48 | M20X75 | B/N/2WP - HDG (std) | 8.8 | 445 | 0.314 | 139.73 |  | 1 | 139.73
W-552 | JPO | JPO-48 | M16X50 | B/N/2WP - HDG (std) | 8.8 | 285 | 0.149 | 42.465 |  | 1 | 42.465
W-552 | JPO | JPO-48 | M16X45 | B/N/2WP - HDG (std) | 8.8 | 112 | 0.136 | 15.232 |  | 1 | 15.232
W-552 | JPO | JPO-48 | M10X65 | B/N/2WP - HDG (std) | 8.8 | 668 | 0.063 | 42.084 |  | 1 | 42.084
W-553 | Panel Bailey | 12 SSR-EW | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 64 | 0.53 | 33.92 |  | 3 | 101.76
W-553 | Panel Bailey | 12 SSR-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 4 | 0.46 | 1.84 |  | 3 | 5.52
W-553 | Panel Bailey | 12 SSR-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 32 | 0.43 | 13.76 |  | 3 | 41.28
W-553 | Panel Bailey | 12 SSR-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.41 | 9.84 |  | 3 | 29.52
W-553 | Panel Bailey | 12 SSR-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 64 | 0.474 | 30.336 |  | 3 | 91.008
W-553 | Panel Bailey | 12 SSR-EW | M20 x 90 | B/N/2WP - HDG (std) | 8.8 | 10 | 0.354 | 3.54 |  | 3 | 10.62
W-553 | Panel Bailey | 12 SSR-EW | M20 x 80 | B/N/2WP - HDG (std) | 8.8 | 10 | 0.334 | 3.34 |  | 3 | 10.02
W-553 | Panel Bailey | 12 SSR-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.294 | 4.704 |  | 3 | 14.112
W-553 | Panel Bailey | 12 SSR-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 4 | 0.294 | 1.176 |  | 3 | 3.528
W-553 | Panel Bailey | 12 SSR-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 32 | 0.244 | 7.808 |  | 3 | 23.424
W-553 | Panel Bailey | 12 SSR-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.136 | 1.088 |  | 3 | 3.264
W-553 | Panel Bailey | 12 SSR-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 32 | 0.136 | 4.352 |  | 3 | 13.056
W-554 | STRUKTUR PERKUATAN | PERKUATAN | M24X70 | B/N/2WP - HDG (+F35) | 8.8 | 50 | 0.612 | 30.6 |  | 1 | 30.6
W-554 | STRUKTUR PERKUATAN | PERKUATAN | M24X50 | B/N/2WP - HDG (+F35) | 8.8 | 25 | 0.552 | 13.8 |  | 1 | 13.8
W-554 | STRUKTUR PERKUATAN | PERKUATAN | M12X35 | B/N/2WP - HDG (std) | 8.8 | 297 | 0.063 | 18.711 |  | 1 | 18.711
W-555 | Jembatan Gantung | JG40_ASIMETRIS | M20X70 | B/N/2WP - HDG (std) | F10T | 13 | 0.41 | 5.33 |  | 1 | 5.33
W-555 | Jembatan Gantung | JG40_ASIMETRIS | M20X70 | B/N/2WP - HDG (std) | 8.8 | 198 | 0.357 | 70.686 |  | 1 | 70.686
W-555 | Jembatan Gantung | JG40_ASIMETRIS | M20X65 | B/N/2WP - HDG (std) | 8.8 | 87 | 0.347 | 30.189 |  | 1 | 30.189
W-555 | Jembatan Gantung | JG40_ASIMETRIS | M20X60 | B/N/2WP - HDG (std) | 8.8 | 83 | 0.327 | 27.141 |  | 1 | 27.141
W-555 | Jembatan Gantung | JG40_ASIMETRIS | M20X50 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.307 | 5.219 |  | 1 | 5.219
W-555 | Jembatan Gantung | JG40_ASIMETRIS | M16X60 | B/N/2WP - HDG (std) | 8.8 | 87 | 0.159 | 13.833 |  | 1 | 13.833
W-555 | Jembatan Gantung | JG40_ASIMETRIS | M16X50 | B/N/2WP - HDG (std) | 8.8 | 122 | 0.149 | 18.178 |  | 1 | 18.178
W-555 | Jembatan Gantung | JG40_ASIMETRIS | M16X45 | B/N/2WP - HDG (std) | 8.8 | 174 | 0.136 | 23.664 |  | 1 | 23.664
W-555 | Jembatan Gantung | JG40_ASIMETRIS | M16X40 | B/N/2WP - HDG (std) | 8.8 | 495 | 0.129 | 63.855 |  | 1 | 63.855
W-555 | Jembatan Gantung | JG40_ASIMETRIS | M12X40 | B/N/2WP - HDG (std) | 8.8 | 363 | 0.068 | 24.684 |  | 1 | 24.684
W-555 | Jembatan Gantung | JG40_ASIMETRIS | M12X35 | B/N/2WP - HDG (std) | 8.8 | 606 | 0.063 | 38.178 |  | 1 | 38.178
W-555 | Jembatan Gantung | JG40_ASIMETRIS | M10X30 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.003 | 0.027 |  | 1 | 0.027
W-555 | Jembatan Gantung | JG40_ASIMETRIS | M6X20 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.01 | 0.17 |  | 1 | 0.17
W-556 | Girder | CG12 | M20X70 | B/N/2WP - HDG (+F35) | 8.8 | 297 | 0.357 | 106.029 |  | 1 | 106.029
W-556 | Girder | CG12 | M20X65 | B/N/2WP - HDG (+F35) | 8.8 | 297 | 0.347 | 103.059 |  | 1 | 103.059
W-556 | Girder | CG12 | M16X50 | B/N/2WP - HDG (std) | 8.8 | 25 | 0.149 | 3.725 |  | 1 | 3.725
W-556 | Girder | CG12 | M16X45 | B/N/2WP - HDG (std) | 8.8 | 91 | 0.136 | 12.376 |  | 1 | 12.376
W-556 | Girder | CG12 | M12X55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729
W-556 | Girder | CG12 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 182 | 0.068 | 12.376 |  | 1 | 12.376
W-558 | Truss Modullar | RB30 | M20X80 | B/N/2WP - HDG (+F35) | 8.8 | 136 | 0.387 | 52.632 |  | 1 | 52.632
W-558 | Truss Modullar | RB30 | M20X75 | B/N/2WP - HDG (+F35) | 8.8 | 211 | 0.367 | 77.437 |  | 1 | 77.437
W-558 | Truss Modullar | RB30 | M20X70 | B/N/2WP - HDG (+F35) | 8.8 | 198 | 0.357 | 70.686 |  | 1 | 70.686
W-558 | Truss Modullar | RB30 | M20X65 | B/N/2WP - HDG (+F35) | 8.8 | 1154 | 0.347 | 400.438 |  | 1 | 400.438
W-558 | Truss Modullar | RB30 | M20X60 | B/N/2WP - HDG (+F35) | 8.8 | 1424 | 0.327 | 465.648 |  | 1 | 465.648
W-558 | Truss Modullar | RB30 | M20X55 | B/N/2WP - HDG (+F35) | 8.8 | 1220 | 0.317 | 386.74 |  | 1 | 386.74
W-558 | Truss Modullar | RB30 | M20X50 | B/N/2WP - HDG (+F35) | 8.8 | 145 | 0.307 | 44.515 |  | 1 | 44.515
W-558 | Truss Modullar | RB30 | M12X60 | B/N/2WP - HDG (std) | 8.8 | 25 | 0.086 | 2.15 |  | 1 | 2.15
W-558 | Truss Modullar | RB30 | M12X45 | B/N/2WP - HDG (std) | 8.8 | 433 | 0.072 | 31.176 |  | 1 | 31.176
W-558 | Truss Modullar | RB30 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.068 | 1.156 |  | 1 | 1.156
W-558 | Truss Modullar | RB30 | M12X35 | B/N/2WP - HDG (std) | 8.8 | 948 | 0.063 | 59.724 |  | 1 | 59.724
W-558 | Truss Modullar | RB30 | M12X30 | B/N/2WP - HDG (std) | 8.8 | 5 | 0.059 | 0.295 |  | 1 | 0.295
W-559 | Jembatan Gantung | JG100P | M24X80 | B/N/2WP - HDG (+F35) | 8.8 | 17 | 0.652 | 11.084 |  | 1 | 11.084
W-559 | Jembatan Gantung | JG100P | M24X60 | B/N/2WP - HDG (+F35) | 8.8 | 5 | 0.582 | 2.91 |  | 1 | 2.91
W-559 | Jembatan Gantung | JG100P | M20X70 | B/N/2WP - HDG (std) | 8.8 | 792 | 0.357 | 282.744 |  | 1 | 282.744
W-559 | Jembatan Gantung | JG100P | M20X65 | B/N/2WP - HDG (std) | 8.8 | 277 | 0.347 | 96.119 |  | 1 | 96.119
W-559 | Jembatan Gantung | JG100P | M20X60 | B/N/2WP - HDG (std) | 8.8 | 544 | 0.327 | 177.888 |  | 1 | 177.888
W-559 | Jembatan Gantung | JG100P | M20X55 | B/N/2WP - HDG (std) | 8.8 | 83 | 0.317 | 26.311 |  | 1 | 26.311
W-559 | Jembatan Gantung | JG100P | M20X50 | B/N/2WP - HDG (std) | 8.8 | 478 | 0.307 | 146.746 |  | 1 | 146.746
W-559 | Jembatan Gantung | JG100P | M20X45 | B/N/2WP - HDG (std) | 8.8 | 50 | 0.297 | 14.85 |  | 1 | 14.85
W-559 | Jembatan Gantung | JG100P | M16X90 | B/N/2WP - HDG (std) | 8.8 | 85 | 0.209 | 17.765 |  | 1 | 17.765
W-559 | Jembatan Gantung | JG100P | M16X65 | B/N/2WP - HDG (std) | 8.8 | 161 | 0.169 | 27.209 |  | 1 | 27.209
W-559 | Jembatan Gantung | JG100P | M16X60 | B/N/2WP - HDG (std) | 8.8 | 42 | 0.159 | 6.678 |  | 1 | 6.678
W-559 | Jembatan Gantung | JG100P | M16X55 | B/N/2WP - HDG (std) | 8.8 | 161 | 0.154 | 24.794 |  | 1 | 24.794
W-559 | Jembatan Gantung | JG100P | M16X45 | B/N/2WP - HDG (std) | 8.8 | 2967 | 0.136 | 403.512 |  | 1 | 403.512
W-559 | Jembatan Gantung | JG100P | M12X50 | B/N/2WP - HDG (std) | 8.8 | 25 | 0.077 | 1.925 |  | 1 | 1.925
W-559 | Jembatan Gantung | JG100P | M12X40 | B/N/2WP - HDG (std) | 8.8 | 1319 | 0.068 | 89.692 |  | 1 | 89.692
W-559 | Jembatan Gantung | JG100P | M12X30 | B/N/2WP - HDG (std) | 8.8 | 380 | 0.059 | 22.42 |  | 1 | 22.42
W-559 | Jembatan Gantung | JG100P | M10X30 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.03 | 0.51 |  | 1 | 0.51
W-559 | Jembatan Gantung | JG100P | M6X20 | B/N/2WP - HDG (std) | 8.8 | 33 | 0.02 | 0.66 |  | 1 | 0.66
W-561 | TOWER | TWR-H36 | M20X70 | B/N/2WP - HDG (std) | 8.8 | 124 | 0.304 | 37.696 |  | 1 | 37.696
W-561 | TOWER | TWR-H36 | M20X50 | B/N/2WP - HDG (std) | 8.8 | 606 | 0.254 | 153.924 |  | 1 | 153.924
W-561 | TOWER | TWR-H36 | M20X45 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.244 | 2.196 |  | 1 | 2.196
W-561 | TOWER | TWR-H36 | M16X45 | B/N/2WP - HDG (std) | 8.8 | 31 | 0.136 | 4.216 |  | 1 | 4.216
W-561 | TOWER | TWR-H36 | M16X40 | B/N/2WP - HDG (std) | 8.8 | 50 | 0.129 | 6.45 |  | 1 | 6.45
W-561 | TOWER | TWR-H36 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 21 | 0.068 | 1.428 |  | 1 | 1.428
W-561 | TOWER | TWR-H36 | M12X35 | B/N/2WP - HDG (std) | 8.8 | 130 | 0.063 | 8.19 |  | 1 | 8.19
W-561 | TOWER | TWR-H36 | M12X30 | B/N/2WP - HDG (std) | 8.8 | 13 | 0.059 | 0.767 |  | 1 | 0.767
W-561 | TOWER | TWR-H36 | M10X30 | B/N/2WP - HDG (std) | 4.6 | 112 | 0.29 | 32.48 |  | 1 | 32.48
W-561 | TOWER | TWR-H36 | M10X30 | B/N/2WP - HDG (std) | 4.6 | 13 | 0.2 | 2.6 |  | 1 | 2.6
W-561 | TOWER | TWR-H36 | M6X19 | B/N/2WP - HDG (std) | 4.6 | 50 | 0.091 | 4.55 |  | 1 | 4.55
W-561 | TOWER | TWR-H36 | M6X18 | B/N/2WP - HDG (std) | 4.6 | 6 | 0.091 | 0.546 |  | 1 | 0.546
W-561 | TOWER | TWR-H36 | M6X18 | B/N/2WP - HDG (std) | 4.6 | 6 | 0.091 | 0.546 |  | 1 | 0.546
W-562 | Panel Bailey | 24 DSR2-EW | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 269 | 0.53 | 142.57 |  | 1 | 142.57
W-562 | Panel Bailey | 24 DSR2-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 143 | 0.46 | 65.78 |  | 1 | 65.78
W-562 | Panel Bailey | 24 DSR2-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 68 | 0.43 | 29.24 |  | 1 | 29.24
W-562 | Panel Bailey | 24 DSR2-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 42 | 0.41 | 17.22 |  | 1 | 17.22
W-562 | Panel Bailey | 24 DSR2-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 152 | 0.474 | 72.048 |  | 1 | 72.048
W-562 | Panel Bailey | 24 DSR2-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 26 | 0.294 | 7.644 |  | 1 | 7.644
W-562 | Panel Bailey | 24 DSR2-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.294 | 2.646 |  | 1 | 2.646
W-562 | Panel Bailey | 24 DSR2-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 135 | 0.244 | 32.94 |  | 1 | 32.94
W-562 | Panel Bailey | 24 DSR2-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.136 | 2.312 |  | 1 | 2.312
W-562 | Panel Bailey | 24 DSR2-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 68 | 0.136 | 9.248 |  | 1 | 9.248
W-563 | Girder | CG12 | M20X75 | B/N/2WP - HDG (+F35) | 8.8 | 363 | 0.367 | 133.221 |  | 1 | 133.221
W-563 | Girder | CG12 | M20X55 | B/N/2WP - HDG (+F35) | 8.8 | 264 | 0.317 | 83.688 |  | 1 | 83.688
W-563 | Girder | CG12 | M16X50 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.149 | 2.533 |  | 1 | 2.533
W-563 | Girder | CG12 | M16X45 | B/N/2WP - HDG (std) | 8.8 | 99 | 0.136 | 13.464 |  | 1 | 13.464
W-563 | Girder | CG12 | M12X55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729
W-563 | Girder | CG12 | M12X45 | B/N/2WP - HDG (std) | 8.8 | 83 | 0.072 | 5.976 |  | 1 | 5.976
W-563 | Girder | CG12 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 132 | 0.068 | 8.976 |  | 1 | 8.976
W-564 | Truss Modullar | RB50 | M20X100 | B/N/2WP - HDG (+F35) | 8.8 | 109 | 0.427 | 46.543 |  | 1 | 46.543
W-564 | Truss Modullar | RB50 | M20X90 | B/N/2WP - HDG (+F35) | 8.8 | 289 | 0.407 | 117.623 |  | 1 | 117.623
W-564 | Truss Modullar | RB50 | M20X80 | B/N/2WP - HDG (+F35) | 8.8 | 421 | 0.387 | 162.927 |  | 1 | 162.927
W-564 | Truss Modullar | RB50 | M20X75 | B/N/2WP - HDG (+F35) | 8.8 | 2448 | 0.367 | 898.416 |  | 1 | 898.416
W-564 | Truss Modullar | RB50 | M20X70 | B/N/2WP - HDG (+F35) | 8.8 | 1030 | 0.357 | 367.71 |  | 1 | 367.71
W-564 | Truss Modullar | RB50 | M20X65 | B/N/2WP - HDG (+F35) | 8.8 | 1591 | 0.347 | 552.077 |  | 1 | 552.077
W-564 | Truss Modullar | RB50 | M20X60 | B/N/2WP - HDG (+F35) | 8.8 | 2717 | 0.327 | 888.459 |  | 1 | 888.459
W-564 | Truss Modullar | RB50 | M20X55 | B/N/2WP - HDG (+F35) | 8.8 | 1162 | 0.317 | 368.354 |  | 1 | 368.354
W-564 | Truss Modullar | RB50 | M20X50 | B/N/2WP - HDG (+F35) | 8.8 | 153 | 0.307 | 46.971 |  | 1 | 46.971
W-564 | Truss Modullar | RB50 | M12X60 | B/N/2WP - HDG (std) | 8.8 | 25 | 0.086 | 2.15 |  | 1 | 2.15
W-564 | Truss Modullar | RB50 | M12X45 | B/N/2WP - HDG (std) | 8.8 | 149 | 0.072 | 10.728 |  | 1 | 10.728
W-564 | Truss Modullar | RB50 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 437 | 0.068 | 29.716 |  | 1 | 29.716
W-564 | Truss Modullar | RB50 | M12X35 | B/N/2WP - HDG (std) | 8.8 | 99 | 0.063 | 6.237 |  | 1 | 6.237
W-564 | Truss Modullar | RB50 | M12X30 | B/N/2WP - HDG (std) | 8.8 | 1447 | 0.059 | 85.373 |  | 1 | 85.373
W-565 | Panel Bailey | 36 DSR2-EW | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 384 | 0.53 | 203.52 |  | 1 | 203.52
W-565 | Panel Bailey | 36 DSR2-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 204 | 0.46 | 93.84 |  | 1 | 93.84
W-565 | Panel Bailey | 36 DSR2-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 96 | 0.43 | 41.28 |  | 1 | 41.28
W-565 | Panel Bailey | 36 DSR2-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 56 | 0.41 | 22.96 |  | 1 | 22.96
W-565 | Panel Bailey | 36 DSR2-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 208 | 0.474 | 98.592 |  | 1 | 98.592
W-565 | Panel Bailey | 36 DSR2-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.294 | 7.056 |  | 1 | 7.056
W-565 | Panel Bailey | 36 DSR2-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 12 | 0.294 | 3.528 |  | 1 | 3.528
W-565 | Panel Bailey | 36 DSR2-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 192 | 0.244 | 46.848 |  | 1 | 46.848
W-565 | Panel Bailey | 36 DSR2-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.14 | 2.24 |  | 1 | 2.24
W-565 | Panel Bailey | 36 DSR2-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 96 | 0.136 | 13.056 |  | 1 | 13.056
W-566 | Girder | AG18.8 | M24X120 | B/N/2WP - HDG (+F35) | 8.8 | 404 | 0.792 | 319.968 |  | 1 | 319.968
W-566 | Girder | AG18.8 | M24X110 | B/N/2WP - HDG (+F35) | 8.8 | 347 | 0.762 | 264.414 |  | 1 | 264.414
W-566 | Girder | AG18.8 | M24X100 | B/N/2WP - HDG (+F35) | 8.8 | 404 | 0.722 | 291.688 |  | 1 | 291.688
W-566 | Girder | AG18.8 | M24X75 | B/N/2WP - HDG (+F35) | 8.8 | 693 | 0.632 | 437.976 |  | 1 | 437.976
W-566 | Girder | AG18.8 | M20X55 | B/N/2WP - HDG (std) | 8.8 | 445 | 0.264 | 117.48 |  | 1 | 117.48
W-566 | Girder | AG18.8 | M16X55 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.154 | 2.618 |  | 1 | 2.618
W-566 | Girder | AG18.8 | M12X55 | B/N/2WP - HDG (std) | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729
W-566 | Girder | AG18.8 | M12X50 | B/N/2WP - HDG (std) | 8.8 | 520 | 0.068 | 35.36 |  | 1 | 35.36
W-566 | Girder | AG18.8 | M10X25 | B/N/2WP - HDG (std) | 8.8 | 124 | 0.04 | 4.96 |  | 1 | 4.96
W-569 | Truss Modullar | RB40 | M20X90 | B/N/2WP - HDG (+F35) | 8.8 | 58 | 0.407 | 23.606 |  | 1 | 23.606
W-569 | Truss Modullar | RB40 | M20X80 | B/N/2WP - HDG (+F35) | 8.8 | 206 | 0.387 | 79.722 |  | 1 | 79.722
W-569 | Truss Modullar | RB40 | M20X75 | B/N/2WP - HDG (+F35) | 8.8 | 231 | 0.367 | 84.777 |  | 1 | 84.777
W-569 | Truss Modullar | RB40 | M20X70 | B/N/2WP - HDG (+F35) | 8.8 | 1525 | 0.357 | 544.425 |  | 1 | 544.425
W-569 | Truss Modullar | RB40 | M20X65 | B/N/2WP - HDG (+F35) | 8.8 | 952 | 0.347 | 330.344 |  | 1 | 330.344
W-569 | Truss Modullar | RB40 | M20X60 | B/N/2WP - HDG (+F35) | 8.8 | 1747 | 0.327 | 571.269 |  | 1 | 571.269
W-569 | Truss Modullar | RB40 | M20X55 | B/N/2WP - HDG (+F35) | 8.8 | 1434 | 0.317 | 454.578 |  | 1 | 454.578
W-569 | Truss Modullar | RB40 | M20X50 | B/N/2WP - HDG (+F35) | 8.8 | 91 | 0.307 | 27.937 |  | 1 | 27.937
W-569 | Truss Modullar | RB40 | M12X60 | B/N/2WP - HDG (std) | 8.8 | 25 | 0.086 | 2.15 |  | 1 | 2.15
W-569 | Truss Modullar | RB40 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 425 | 0.068 | 28.9 |  | 1 | 28.9
W-569 | Truss Modullar | RB40 | M12X35 | B/N/2WP - HDG (std) | 8.8 | 112 | 0.063 | 7.056 |  | 1 | 7.056
W-569 | Truss Modullar | RB40 | M12X30 | B/N/2WP - HDG (std) | 8.8 | 1158 | 0.059 | 68.322 |  | 1 | 68.322
W-570 | Truss Modullar | RB30 | M20X80 | B/N/2WP - HDG (+F35) | 8.8 | 136 | 0.387 | 52.632 |  | 1 | 52.632
W-570 | Truss Modullar | RB30 | M20X75 | B/N/2WP - HDG (+F35) | 8.8 | 211 | 0.367 | 77.437 |  | 1 | 77.437
W-570 | Truss Modullar | RB30 | M20X70 | B/N/2WP - HDG (+F35) | 8.8 | 198 | 0.357 | 70.686 |  | 1 | 70.686
W-570 | Truss Modullar | RB30 | M20X65 | B/N/2WP - HDG (+F35) | 8.8 | 1154 | 0.347 | 400.438 |  | 1 | 400.438
W-570 | Truss Modullar | RB30 | M20X60 | B/N/2WP - HDG (+F35) | 8.8 | 1424 | 0.327 | 465.648 |  | 1 | 465.648
W-570 | Truss Modullar | RB30 | M20X55 | B/N/2WP - HDG (+F35) | 8.8 | 1220 | 0.317 | 386.74 |  | 1 | 386.74
W-570 | Truss Modullar | RB30 | M20X50 | B/N/2WP - HDG (+F35) | 8.8 | 145 | 0.307 | 44.515 |  | 1 | 44.515
W-570 | Truss Modullar | RB30 | M12X60 | B/N/2WP - HDG (std) | 8.8 | 25 | 0.086 | 2.15 |  | 1 | 2.15
W-570 | Truss Modullar | RB30 | M12X45 | B/N/2WP - HDG (std) | 8.8 | 433 | 0.072 | 31.176 |  | 1 | 31.176
W-570 | Truss Modullar | RB30 | M12X40 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.068 | 1.156 |  | 1 | 1.156
W-570 | Truss Modullar | RB30 | M12X35 | B/N/2WP - HDG (std) | 8.8 | 948 | 0.063 | 59.724 |  | 1 | 59.724
W-570 | Truss Modullar | RB30 | M12X30 | B/N/2WP - HDG (std) | 8.8 | 5 | 0.059 | 0.295 |  | 1 | 0.295
W-567 | STRUKTUR ATAP | ATAP ASRAMA HAJI | M16X55 | B/N/2WP - HDG (std) | 8.8 | 64 | 0.154 | 9.856 |  | 1 | 9.856
W-567 | STRUKTUR ATAP | ATAP ASRAMA HAJI | M20X55 | B/N/2WP - HDG (std) | 8.8 | 416 | 0.317 | 131.872 |  | 1 | 131.872
W-567 | STRUKTUR ATAP | ATAP ASRAMA HAJI | M12X35 | B/N/2WP - HDG (std) | 8.8 | 480 | 0.063 | 30.24 |  | 1 | 30.24
W-572 | Panel Bailey | 21 SSR-EW | M24 x 90 | B/N/2WP - HDG (std) | F10T | 112 | 0.79 | 88.48 |  | 1 | 88.48
W-572 | Panel Bailey | 21 SSR-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 7 | 0.46 | 3.22 |  | 1 | 3.22
W-572 | Panel Bailey | 21 SSR-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 56 | 0.43 | 24.08 |  | 1 | 24.08
W-572 | Panel Bailey | 21 SSR-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 36 | 0.41 | 14.76 |  | 1 | 14.76
W-572 | Panel Bailey | 21 SSR-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 128 | 0.474 | 60.672 |  | 1 | 60.672
W-572 | Panel Bailey | 21 SSR-EW | M20 x 90 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.354 | 5.664 |  | 1 | 5.664
W-572 | Panel Bailey | 21 SSR-EW | M20 x 80 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.334 | 5.344 |  | 1 | 5.344
W-572 | Panel Bailey | 21 SSR-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.294 | 4.704 |  | 1 | 4.704
W-572 | Panel Bailey | 21 SSR-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 7 | 0.294 | 2.058 |  | 1 | 2.058
W-572 | Panel Bailey | 21 SSR-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 56 | 0.244 | 13.664 |  | 1 | 13.664
W-572 | Panel Bailey | 21 SSR-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.136 | 1.088 |  | 1 | 1.088
W-572 | Panel Bailey | 21 SSR-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 56 | 0.136 | 7.616 |  | 1 | 7.616
W-571 | Panel Bailey | 30 DSR2-EW | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 320 | 0.53 | 169.6 |  | 1 | 169.6
W-571 | Panel Bailey | 30 DSR2-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 170 | 0.46 | 78.2 |  | 1 | 78.2
W-571 | Panel Bailey | 30 DSR2-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.43 | 34.4 |  | 1 | 34.4
W-571 | Panel Bailey | 30 DSR2-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 48 | 0.41 | 19.68 |  | 1 | 19.68
W-571 | Panel Bailey | 30 DSR2-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 176 | 0.474 | 83.424 |  | 1 | 83.424
W-571 | Panel Bailey | 30 DSR2-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.294 | 7.056 |  | 1 | 7.056
W-571 | Panel Bailey | 30 DSR2-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 10 | 0.294 | 2.94 |  | 1 | 2.94
W-571 | Panel Bailey | 30 DSR2-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 160 | 0.244 | 39.04 |  | 1 | 39.04
W-571 | Panel Bailey | 30 DSR2-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.14 | 2.24 |  | 1 | 2.24
W-571 | Panel Bailey | 30 DSR2-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.136 | 10.88 |  | 1 | 10.88
W-560C | Jembatan Pendekat | SPAN 22.82 M | M24X90 | B/N/2WP - HDG (std) | 8.8 | 347 | 0.53 | 183.91 |  | 1 | 183.91
W-560C | Jembatan Pendekat | SPAN 22.82 M | M24X75 | B/N/2WP - HDG (std) | 8.8 | 124 | 0.48 | 59.52 |  | 1 | 59.52
W-560C | Jembatan Pendekat | SPAN 22.82 M | M16X45 | B/N/2WP - HDG (std) | 8.8 | 396 | 0.136 | 53.856 |  | 1 | 53.856
W-560C | Jembatan Pendekat | SPAN 22.82 M | M16X40 | B/N/2WP - HDG (std) | 8.8 | 264 | 0.129 | 34.056 |  | 1 | 34.056
W-560C | Jembatan Pendekat | SPAN 22.82 M | M12X40 | B/N/2WP - HDG (std) | 8.8 | 50 | 0.068 | 3.4 |  | 1 | 3.4
W-560A | Jembatan Pendekat | SPAN 11.87 M | M16X100 | B/N/2WP - HDG (std) | 8.8 | 25 | 0.229 | 5.725 |  | 2 | 11.45
W-560A | Jembatan Pendekat | SPAN 11.87 M | M16X45 | B/N/2WP - HDG (std) | 8.8 | 25 | 0.136 | 3.4 |  | 2 | 6.8
W-560A | Jembatan Pendekat | SPAN 11.87 M | M16X40 | B/N/2WP - HDG (std) | 8.8 | 165 | 0.129 | 21.285 |  | 2 | 42.57
W-560A | Jembatan Pendekat | SPAN 11.87 M | M12X40 | B/N/2WP - HDG (std) | 8.8 | 21 | 0.068 | 1.428 |  | 2 | 2.856
W-560B | Jembatan Pendekat | SPAN 14.20 M | M16X65 | B/N/2WP - HDG (std) | 8.8 | 174 | 0.169 | 29.406 |  | 1 | 29.406
W-560B | Jembatan Pendekat | SPAN 14.20 M | M16X60 | B/N/2WP - HDG (std) | 8.8 | 112 | 0.159 | 17.808 |  | 1 | 17.808
W-560B | Jembatan Pendekat | SPAN 14.20 M | M16X45 | B/N/2WP - HDG (std) | 8.8 | 33 | 0.136 | 4.488 |  | 1 | 4.488
W-560B | Jembatan Pendekat | SPAN 14.20 M | M16X40 | B/N/2WP - HDG (std) | 8.8 | 141 | 0.129 | 18.189 |  | 1 | 18.189
W-576A | Panel Bailey | 18 SSR - EW | M24 x 90 | B/N/2WP - HDG (F35) | F10T | 96 | 0.53 | 50.88 |  | 1 | 50.88
W-576A | Panel Bailey | 18 SSR - EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 6 | 0.46 | 2.76 |  | 1 | 2.76
W-576A | Panel Bailey | 18 SSR - EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 48 | 0.43 | 20.64 |  | 1 | 20.64
W-576A | Panel Bailey | 18 SSR - EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 32 | 0.41 | 13.12 |  | 1 | 13.12
W-576A | Panel Bailey | 18 SSR - EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 112 | 0.474 | 53.088 |  | 1 | 53.088
W-576A | Panel Bailey | 18 SSR - EW | M20 x 90 | B/N/2WP - HDG (std) | 8.8 | 14 | 0.354 | 4.956 |  | 1 | 4.956
W-576A | Panel Bailey | 18 SSR - EW | M20 x 80 | B/N/2WP - HDG (std) | 8.8 | 14 | 0.334 | 4.676 |  | 1 | 4.676
W-576A | Panel Bailey | 18 SSR - EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.294 | 4.704 |  | 1 | 4.704
W-576A | Panel Bailey | 18 SSR - EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 6 | 0.294 | 1.764 |  | 1 | 1.764
W-576A | Panel Bailey | 18 SSR - EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 48 | 0.244 | 11.712 |  | 1 | 11.712
W-576A | Panel Bailey | 18 SSR - EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.136 | 1.088 |  | 1 | 1.088
W-576A | Panel Bailey | 18 SSR - EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 48 | 0.136 | 6.528 |  | 1 | 6.528
W-576B | Panel Bailey | 12 SSR-EW | M24 x 90 | B/N/2WP - HDG (F35) | F10T | 64 | 0.53 | 33.92 |  | 1 | 33.92
W-576B | Panel Bailey | 12 SSR-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 4 | 0.46 | 1.84 |  | 1 | 1.84
W-576B | Panel Bailey | 12 SSR-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 32 | 0.43 | 13.76 |  | 1 | 13.76
W-576B | Panel Bailey | 12 SSR-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.41 | 9.84 |  | 1 | 9.84
W-576B | Panel Bailey | 12 SSR-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.474 | 37.92 |  | 1 | 37.92
W-576B | Panel Bailey | 12 SSR-EW | M20 x 90 | B/N/2WP - HDG (std) | 8.8 | 10 | 0.354 | 3.54 |  | 1 | 3.54
W-576B | Panel Bailey | 12 SSR-EW | M20 x 80 | B/N/2WP - HDG (std) | 8.8 | 10 | 0.334 | 3.34 |  | 1 | 3.34
W-576B | Panel Bailey | 12 SSR-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.294 | 4.704 |  | 1 | 4.704
W-576B | Panel Bailey | 12 SSR-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 4 | 0.294 | 1.176 |  | 1 | 1.176
W-576B | Panel Bailey | 12 SSR-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 32 | 0.244 | 7.808 |  | 1 | 7.808
W-576B | Panel Bailey | 12 SSR-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 8 | 0.136 | 1.088 |  | 1 | 1.088
W-576B | Panel Bailey | 12 SSR-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 32 | 0.136 | 4.352 |  | 1 | 4.352
W-574 | Truss Modullar | RC45+15 | M20X70 | B/N/2WP - HDG (F35) | 8.8 | 23 | 0.347 | 7.981 |  | 1 | 7.981
W-574 | Truss Modullar | RC45+15 | M20X65 | B/N/2WP - HDG (F35) | 8.8 | 423 | 0.327 | 138.321 |  | 1 | 138.321
W-574 | Truss Modullar | RC45+15 | M20X60 | B/N/2WP - HDG (F35) | 8.8 | 610 | 0.209 | 127.49 |  | 1 | 127.49
W-574 | Truss Modullar | RC45+15 | M20X55 | B/N/2WP - HDG (F35) | 8.8 | 3247 | 0.149 | 483.803 |  | 1 | 483.803
W-574 | Truss Modullar | RC45+15 | M20X50 | B/N/2WP - HDG (F35) | 8.8 | 2283 | 0.136 | 310.488 |  | 1 | 310.488
W-574 | Truss Modullar | RC45+15 | M16X45 | B/N/2WP - HDG (std) | 8.8 | 83 | 0.129 | 10.707 |  | 1 | 10.707
W-574 | Truss Modullar | RC45+15 | M12X55 | B/N/2WP - HDG (std) | 8.8 | 29 | 0.081 | 2.349 |  | 1 | 2.349
W-574 | Truss Modullar | RC45+15 | M12X35 | B/N/2WP - HDG (std) | 8.8 | 248 | 0.063 | 15.624 |  | 1 | 15.624
W-574 | Truss Modullar | RC45+15 | M12X30 | B/N/2WP - HDG (std) | 8.8 | 927 | 0.04 | 37.08 |  | 1 | 37.08
W-574 | Truss Modullar | RC45+15 | M10X35 | B/N/2WP - HDG (std) | 8.8 | 866 | 0.04 | 34.64 |  | 1 | 34.64
W-577 | Girder | AG20 | M20X85 | B/N/2WP (F35) - HDG | 8.8 | 520 | 0.387 | 201.24 |  | 1 | 201.24
W-577 | Girder | AG20 | M20X75 | B/N/2WP (F35) - HDG | 8.8 | 186 | 0.367 | 68.262 |  | 1 | 68.262
W-577 | Girder | AG20 | M20X70 | B/N/2WP (F35) - HDG | 8.8 | 557 | 0.357 | 198.849 |  | 1 | 198.849
W-577 | Girder | AG20 | M16X50 | B/N/2WP (STD) - HDG | 8.8 | 17 | 0.149 | 2.533 |  | 1 | 2.533
W-577 | Girder | AG20 | M16X45 | B/N/2WP (STD) - HDG | 8.8 | 206 | 0.136 | 28.016 |  | 1 | 28.016
W-577 | Girder | AG20 | M12X55 | B/N/2WP (STD) - HDG | 8.8 | 9 | 0.081 | 0.729 |  | 1 | 0.729
W-577 | Girder | AG20 | M12X40 | B/N/2WP (STD) - HDG | 8.8 | 495 | 0.068 | 33.66 |  | 1 | 33.66
W-579 | Panel Bailey | 30 DSR2-EW | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 320 | 0.53 | 169.6 |  | 2 | 339.2
W-579 | Panel Bailey | 30 DSR2-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 170 | 0.46 | 78.2 |  | 2 | 156.4
W-579 | Panel Bailey | 30 DSR2-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.43 | 34.4 |  | 2 | 68.8
W-579 | Panel Bailey | 30 DSR2-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 48 | 0.41 | 19.68 |  | 2 | 39.36
W-579 | Panel Bailey | 30 DSR2-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 176 | 0.474 | 83.424 |  | 2 | 166.848
W-579 | Panel Bailey | 30 DSR2-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.294 | 7.056 |  | 2 | 14.112
W-579 | Panel Bailey | 30 DSR2-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 10 | 0.294 | 2.94 |  | 2 | 5.88
W-579 | Panel Bailey | 30 DSR2-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 160 | 0.244 | 39.04 |  | 2 | 78.08
W-579 | Panel Bailey | 30 DSR2-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.14 | 2.24 |  | 2 | 4.48
W-579 | Panel Bailey | 30 DSR2-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 80 | 0.136 | 10.88 |  | 2 | 21.76
W-579A | Panel Bailey | 36 DSR2-EW | M24 x 90 | B/N/2WP - HDG (std) | 8.8 | 384 | 0.53 | 203.52 |  | 2 | 407.04
W-579A | Panel Bailey | 36 DSR2-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 204 | 0.46 | 93.84 |  | 2 | 187.68
W-579A | Panel Bailey | 36 DSR2-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 96 | 0.43 | 41.28 |  | 2 | 82.56
W-579A | Panel Bailey | 36 DSR2-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 56 | 0.41 | 22.96 |  | 2 | 45.92
W-579A | Panel Bailey | 36 DSR2-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 208 | 0.474 | 98.592 |  | 2 | 197.184
W-579A | Panel Bailey | 36 DSR2-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 24 | 0.294 | 7.056 |  | 2 | 14.112
W-579A | Panel Bailey | 36 DSR2-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 12 | 0.294 | 3.528 |  | 2 | 7.056
W-579A | Panel Bailey | 36 DSR2-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 192 | 0.244 | 46.848 |  | 2 | 93.696
W-579A | Panel Bailey | 36 DSR2-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 16 | 0.14 | 2.24 |  | 2 | 4.48
W-579A | Panel Bailey | 36 DSR2-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 96 | 0.136 | 13.056 |  | 2 | 26.112
W-580 | Panel Bailey | 39 DSR2H**-EW | M24X130 | B/N/2WP - HDG (std) | 8.8 | 33 | 0.67 | 22.11 |  | 2 | 44.22
W-580 | Panel Bailey | 39 DSR2H**-EW | M24 x 90 | B/N/2WP - HDG (std) | F10T | 429 | 0.79 | 338.91 |  | 2 | 677.82
W-580 | Panel Bailey | 39 DSR2H**-EW | M24 x 70 | B/N/2WP - HDG (std) | 8.8 | 228 | 0.46 | 104.88 |  | 2 | 209.76
W-580 | Panel Bailey | 39 DSR2H**-EW | M24 x 60 | B/N/2WP - HDG (std) | 8.8 | 54 | 0.43 | 23.22 |  | 2 | 46.44
W-580 | Panel Bailey | 39 DSR2H**-EW | M24 x 55 | B/N/2WP - HDG (std) | 8.8 | 83 | 0.41 | 34.03 |  | 2 | 68.06
W-580 | Panel Bailey | 39 DSR2H**-EW | M20 x 140 | B/N/2WP - HDG (std) | 8.8 | 264 | 0.474 | 125.136 |  | 2 | 250.272
W-580 | Panel Bailey | 39 DSR2H**-EW | M20 x 65 | B/N/2WP - HDG (std) | 8.8 | 25 | 0.294 | 7.35 |  | 2 | 14.7
W-580 | Panel Bailey | 39 DSR2H**-EW | M20 x 55 | B/N/2WP - HDG (std) | 8.8 | 88 | 0.254 | 22.352 |  | 2 | 44.704
W-580 | Panel Bailey | 39 DSR2H**-EW | M20 x 45 | B/N/2WP - HDG (std) | 8.8 | 54 | 0.244 | 13.176 |  | 2 | 26.352
W-580 | Panel Bailey | 39 DSR2H**-EW | M16 x 45 | B/N/2WP - HDG (std) | 8.8 | 17 | 0.136 | 2.312 |  | 2 | 4.624
W-580 | Panel Bailey | 39 DSR2H**-EW | M16 x 40 | B/N/2WP - HDG (std) | 8.8 | 108 | 0.136 | 14.688 |  | 2 | 29.376
W-581 | Komponen Jembatan | WB BEAM | M24X75 | B/N/2WP - HDG (F35) | F10T | 675 | 0.42 | 283.5 |  | 1 | 283.5
[8 empty] | 71832.871 |  |  | 82866.748

## DATA PACKING
UPDATE | 2024-12-14
No.PON | Type Struktur | Marking Struktur | Berat Packing | Harga Satuan (Rp) | Harga Satuan (Rp) WGJ | Total Tagihan WGJ | Total Tagihan (Rp) | Tanggal Penagihan ke P. AGUS | STATUS | KETERANGAN | Tanggal Penagihan ke WGJ | STATUS PENAGIHAN | Date Finish Aktual | Keterangan2
W-489A | PLATE LRB | BASEPLATE FOR LRB | 79206.4578 | 70 | 200 | 15841291.5642 | 5544452.0475
W-489B | PLATE LRB | BASEPLATE FOR LRB | 48589.616 | 70 | 200 | 9717923.2 | 3401273.12
W-494 | FENCING SHELTER & STAIRCASES | FENCING | 3450.457 | 70 | 200 | 690091.3944 | 241531.988
W-495A-02 | PLATE LRB | BASEPLATE FOR LRB | 875.3339 | 70 | 200 | 175066.7769 | BY DHJ
W-496-A | PLATE LRB | BASEPLATE FOR LRB | 3090.48 | 70 | 200 | 618096 | BY DHJ
W-498 | Jembatan Gantung | JG105 - PIPA | 11634.56 | 70 | 200 | 2326912 | BY DHJ
W-499 | Girder | AG30 | 45554.55 | 70 | 200 | 9110910 | 3188818.5 | 2023-02-07 | LUNAS
W-500 | Panel Bailey | 33M DSR2 - SS400 | 33073.36 | 70 | 200 | 6614672 | 2315135.2 | 2023-03-30 | LUNAS |  | 2023-03-30
W-501 | Girder | AG20 | 23643.79 | 70 | 200 | 4728758 | 1655065.3 | 2023-02-08 | LUNAS
W-502 | Girder | AG8 | 16323.93 | 70 | 200 | 3264786 | 1142675.1 | 2023-02-28 | LUNAS
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | 60630.99 | 70 | 200 | 12126198 | 4244169.3 | 2023-03-07 | LUNAS
W-503 | Panel Bailey | 42 DSR2-EW + TRESTLE | 4838.64 | 70 | 200 | 967728 | 338704.8 | 2023-03-30 | LUNAS | TRESTLE | 2023-03-30
W-504A | Panel Bailey | 12 SSR-EW | 13217.91 | 70 | 200 | 2643582 | 925253.7 | 2023-03-20 | LUNAS | UNIT I
W-504A | Panel Bailey | 12 SSR-EW | 13217.91 | 70 | 200 | 2643582 | 925253.7 | 2023-03-30 | LUNAS | UNIT II | 2023-03-30
W-504B | Panel Bailey | 15 SSR-EW | 16207.22 | 70 | 200 | 3241444 | 1134505.4 | 2023-03-24 | LUNAS | UNIT I
W-504B | Panel Bailey | 15 SSR-EW | 16207.22 | 70 | 200 | 3241444 | 1134505.4 | 2023-03-24 | LUNAS | UNIT II
W-504B | Panel Bailey | 15 SSR-EW | 16207.22 | 70 | 200 | 3241444 | 1134505.4 | 2023-03-30 | LUNAS | UNIT III | 2023-03-30
W-504C | Panel Bailey | 21 SSR-EW | 22185.84 | 70 | 200 | 4437168 | 1553008.8 | 2023-03-07 | LUNAS
W-505 | Panel Bailey | KOMPONEN BAILEY | 1406.4612 | 70 | 200 | 281292.24 | 98452.284 |  | LUNAS
W-506A | Panel Bailey | 24 DSR2-EW | 35448.49 | 70 | 200 | 7089698 | 2481394.3 | 2023-05-09 | LUNAS | PERUBAHAN TYPE DAN BENTANG
W-506A | Panel Bailey | 24 DSR2-EW | 35448.49 | 70 | 200 | 7089698 | 2481394.3 | 2023-05-10 | LUNAS | PERUBAHAN TYPE DAN BENTANG
W-506B | Panel Bailey | 21 DS-EW | 26070.5 | 70 | 200 | 5214100 | 1824935 | 2023-05-19 | LUNAS | PERUBAHAN TYPE DAN BENTANG
W-506B | Panel Bailey | 21 DS-EW | 26070.5 | 70 | 200 | 5214100 | 1824935 |  | LUNAS | PERUBAHAN TYPE DAN BENTANG
W-506C | Panel Bailey | 18 DSR1-EW | 23943.91 | 70 | 200 | 4788782 | 1676073.7 | 2023-05-16 | LUNAS | PERUBAHAN TYPE DAN BENTANG
W-506D | Panel Bailey | 18 DSR2-EW | 50719.9345 | 70 | 200 | 10143986.9016 | 3550395.4156 | 2023-05-16 | LUNAS | PERUBAHAN TYPE DAN BENTANG
W-506E | Panel Bailey | 33 DSR2H*-EW (U120) | 51191.9 | 70 | 200 | 10238380 | 3583433 | 2023-05-22 | LUNAS | PERUBAHAN TYPE DAN BENTANG
W-507 | Panel Bailey | 30 DSR2-EW | 43842.15 | 70 | 200 | 8768430 | 3068950.5 | 2023-02-22 | LUNAS | UNIT I
W-507 | Panel Bailey | 30 DSR2-EW | 43842.15 | 70 | 200 | 8768430 | 3068950.5 | 2023-03-14 | LUNAS | UNIT II
W-507 | Panel Bailey | 30 DSR2-EW | 43842.15 | 70 | 200 | 8768430 | 3068950.5 | 2023-03-18 | LUNAS | UNIT III
W-509 |  |  | 70216.06 | 70 | 200 | 14043212 | 4915124.2 | 2023-04-03 | LUNAS
W-511 | Girder | BG22 | 45399.27 | 70 | 200 | 9079854 | 3177948.9 | 2023-06-10 | LUNAS
W-512A | Panel Bailey | 42 DSR2-EW (U120) | 62725.21 | 70 | 200 | 12545042 | 4390764.7 | 2023-04-12 | LUNAS |  | 2023-04-15
W-512B | Panel Bailey | 45 DSR2H**-EW (U120) | 69792.12 | 70 | 200 | 13958424 | 4885448.4 | 2023-06-05 | LUNAS | UNIT I
W-512B | Panel Bailey | 45 DSR2H**-EW (U120) | 69792.12 | 70 | 200 | 13958424 | 4885448.4 | 2023-06-13 | LUNAS | UNIT II
W-512C | BEAM TRESTLE | TRESTLE BEAM | 4028.04 | 70 | 200 | 805608 | 281962.8 |  |  | BEAM TRESTLE 1X42 & 1X45
W-513 | Panel Bailey | 30 DSR2-EW | 43842.15 | 70 | 200 | 8768430 | 3068950.5 | 2023-04-28 | LUNAS
W-514 | Girder | CG30 | 27306.98 | 70 | 200 | 5461396 | 1911488.6 | 2023-04-12 | LUNAS | PENGAMBILAN UNIT DARI W499 (A30) | 2023-04-15
W-516A | Panel Bailey | 36 DSR2-EW | 4002.8927 | 70 | 200 | 800578.5376 | 280202.4882 | 2023-05-26 | LUNAS
W-516B | Panel Bailey | 30 DSR2-EW | 43842.15 | 70 | 200 | 8768430 | 3068950.5 | 2023-05-31 | LUNAS | UNIT I
W-516B | Panel Bailey | 30 DSR2-EW | 43842.15 | 70 | 200 | 8768430 | 3068950.5 | 2023-06-22 | LUNAS | UNIT II
W-517 | Panel Bailey | 30 DSR2-EW | 43842.15 | 70 | 200 | 8768430 | 3068950.5 | 2023-07-06 | LUNAS
W-518A | Panel Bailey | 21 SSR-EW | 22185.84 | 70 | 200 | 4437168 | 1553008.8 | 2023-06-15 | LUNAS | UNIT I
W-518A | Panel Bailey | 21 SSR-EW | 22185.84 | 70 | 200 | 4437168 | 1553008.8 | 2023-06-24 | LUNAS | UNIT II
W-518B | Panel Bailey | 24 SSR-EW | 4354.28 | 70 | 200 | 870856 | 304799.6 | 2023-06-23 | LUNAS
W-518C | Panel Bailey | 27 DSR2-EW | 22500.72 | 70 | 200 | 4500144 | 1575050.4 | 2023-07-01 | LUNAS
W-521 | Girder | BG25 | 33480.93 | 70 | 200 | 6696186 | 2343665.1 | 2023-07-14 | LUNAS
W-522 | Truss Modullar | KOMPONEN STRINGGER | 11675.6 | 70 | 200 | 2335120 | 817292 | 2023-07-06 | LUNAS
W-523 | Girder | BG25 | 29059.86 | 70 | 200 | 5811972 | 2034190.2 | 2023-07-18 | LUNAS
W-524 | WELDED BEAM | WB BEAM |  |  | 200 | 0
W-525 | Girder | BG30 | 61826.9969 | 70 | 200 | 12365399.3716 | 4327889.7801 | 2023-08-14
W-526 | Girder | CG30 | 33623.1401 | 70 | 200 | 6724628.0208 | 2353619.8073 | 2023-08-11 | LUNAS
W-527 | Girder | BG35 | 66115.7112 | 70 | 200 | 13223142.2396 | 4628099.7839 | 2023-08-09 | LUNAS
W-528 | Girder | BG20 | 24992.5712 | 70 | 200 | 4998514.2396 | 1749479.9839 | 2023-08-09 | LUNAS
W-537 | Panel Bailey | 30 SSR-EW | 30820 | 70 | 200 | 6164000 | 2157400 | 2023-08-09 | LUNAS | UNIT I
W-537 | Panel Bailey | 30 SSR-EW | 30820 | 70 | 200 | 6164000 | 2157400 | 2023-08-09 | LUNAS | UNIT II
W-537 | Panel Bailey | 30 SSR-EW | 30820 | 70 | 200 | 6164000 | 2157400 | 2023-08-09 | LUNAS | UNIT III
W-370 | Truss Modullar | RB60-BU+LINKSET | 121083.5461 | 70 | 200 | 24216709.2288 | 8475848.2301 | 2023-07-20 | LUNAS | UNIT I
W-370 | Truss Modullar | RB60-BU+LINKSET | 121083.5461 | 70 | 200 | 24216709.2288 | 8475848.2301 | 2023-07-20 | LUNAS | UNIT II
W-370 | Truss Modullar | RB60-BU+LINKSET | 4299.39 | 70 | 200 | 859878 | 300957.3 | 2023-07-20 | LUNAS | LINKSET
W-516C | Panel Bailey | 45 TSR2 - EW | 80469.49 | 70 | 200 | 16093898 | 5632864.3 | 2023-07-27 | LUNAS
W-516D | RAMP Panel Bailey | RAMP PANEL BAILEY | 11387.76 | 70 | 200 | 2277552 | 797143.2 | 2023-07-27 | LUNAS
W-531 | Girder | CG15_6 Line | 19005.7196 | 70 | 200 | 3801143.92 | 1330400.372 | 2023-08-02 | LUNAS
W-550 | Panel Bailey | 30 DSR2-EW | 43842.15 | 70 | 200 | 8768430 | 3068950.5 | 2023-08-02 | LUNAS
W-520A | Girder Spesial | GD14 | 8906.3186 | 70 | 200 | 1781263.7216 | 623442.3026 | 2023-08-10 | LUNAS | 1 UNIT
W-520B | Girder Spesial | GD16 | 54006.743 | 70 | 200 | 10801348.608 | 3780472.0128 | 2023-08-10 | LUNAS | 5 UNIT
W-520C | Girder Spesial | GD18 | 37379.5158 | 70 | 200 | 7475903.1648 | 2616566.1077 | 2023-08-10 | LUNAS | 3 UNIT
W-520D | Girder Spesial | GD20 | 15170.0586 | 70 | 200 | 3034011.7216 | 1061904.1026 | 2023-08-10 | LUNAS | 1 UNIT
W-553 | Panel Bailey | 12 SSR-EW | 11375.46 | 70 | 200 | 2275092 | 796282.2 | 2023-08-12 | LUNAS
W-553 | Panel Bailey | 12 SSR-EW | 11375.46 | 70 | 200 | 2275092 | 796282.2 | 2023-08-12 | LUNAS
W-553 | Panel Bailey | 12 SSR-EW | 11375.46 | 70 | 200 | 2275092 | 796282.2 | 2023-08-12 | LUNAS
W-529 | Truss Modullar | RB50 | 92467.3054 | 70 | 200 | 18493461.0848 | 6472711.3797 | 2023-08-23 | LUNAS | UNIT I
W-519 | Panel Bailey | 39 DSR2H**-EW | 60675.7633 | 70 | 200 | 12135152.6564 | 4247303.4297 | 2023-08-24 | LUNAS
W-541 | Girder | CG12 | 23119.6656 | 70 | 200 | 4623933.1296 | 1618376.5954 | 2023-08-30 | LUNAS
W-544 | Panel Bailey | 9 SSR-EW | 4712.8468 | 70 | 200 | 942569.368 | 329899.2788 | 2023-08-30 | LUNAS
W-534 | Girder | AG20 | 33045.302 | 70 |  | 0 | 2313171.14 | 2023-09-04 | LUNAS
W-562 | Panel Bailey | 24 DSR2-EW | 11490.28 | 70 |  | 0 | 804319.6 | 2023-09-04 | LUNAS
W-545 | Jembatan Gantung | JG150 |  |  |  | 0
W-538 | Truss Modullar | RB60 | 136765.7768 |  |  | 0
W-551 | Girder | AG40 | #REF! |  |  | #REF!
W-558 | Truss Modullar | RB30 | 8392.3334 |  |  | 0
|  |  | #REF! |  |  | #REF! | 176662241.6796
|  |  | #REF! |  |  |  | 115462.6361
#REF!
115462.6361

## CONSUMABLE PACKING
CONSUMABLE PACKING
| No.PON | Type Struktur | Marking Struktur | Deskripsi Consumable | Harga Satuan (Rp) | Qty (pcs) | Total Belanja | Tanggal Pengajuan | KETERANGAN | Date Finish Aktual | Keterangan2
MARET | W-504A | Panel Bailey | 12 SSR-EW | Pembelian Pilox | 70000 | 1 | 70000 | 2023-03-25 | KEBUTUHAN UNIT II
| W-500 | Panel Bailey | 33M DSR2 - SS400 | Pembelian Drum | 150000 | 3 | 450000 | 2023-03-27
| W-509 |  |  | Pembelian Drum | 150000 | 3 | 450000 | 2023-03-31
| W-509 |  |  | Pembelian Balok | 12500 | 40 | 500000 | 2023-03-31
APRIL | W-512A | Panel Bailey | 42 DSR2-EW (U120) | Pembelian Drum | 150000 | 3 | 450000 | 2023-04-07
| W-512A | Panel Bailey | 42 DSR2-EW (U120) | Pembelian Pilox | 38000 | 2 | 76000 | 2023-04-07
| STKJ20 | Panel Bailey STOCK | KOMPONEN BAILEY | Pembelian Drum | 135000 | 10 | 1350000 | 2023-04-11
MEI | W-513 | Panel Bailey | 30 DSR2-EW | Pembelian Pilox | 38000 | 2 | 76000 | 2023-05-12
| W-506A | Panel Bailey | 24 DSR2-EW | Pembelian Pylox | 38000 | 3 | 114000 | 2023-05-12
| W-506D | Panel Bailey | 18 DSR2-EW | Pembelian Pilox | 380000 | 1 | 380000 | 2023-05-12
| W-506D | Panel Bailey | 18 DSR2-EW | Pembelian Drum | 150000 | 1 | 150000 | 2023-05-17
| W-506C | Panel Bailey | 18 DSR1-EW | Pembelian Drum | 150000 | 1 | 150000 | 2023-05-17
| W-506B | Panel Bailey | 21 DS-EW | Pembelian Drum | 150000 | 2 | 300000 | 2023-05-17
| W-506E | Panel Bailey | 33 DSR2H*-EW (U120) | Pembelian Drum | 150000 | 3 | 450000 | 2023-05-17
| W-516A | Panel Bailey | 36 DSR2-EW | Pembelian Drum | 150000 | 4 | 600000 | 2023-05-25
JUNI | W-516B | Panel Bailey | 30 DSR2-EW | Pembelian Drum | 150000 | 2 | 300000 | 2023-06-02 | UNIT I
| W-512B | Panel Bailey | 45 DSR2H**-EW (U120) | Pembelian Drum | 150000 | 3 | 450000 | 2023-06-02 | UNIT I
| W-520A | Girder Spesial | GD14 | Pembelian Drum | 150000 | 2 | 300000 | 2023-06-14
| W-520B | Girder Spesial | GD16 | Pembelian Drum | 150000 | 4 | 600000 | 2023-06-14
| W-520C | Girder Spesial | GD18 | Pembelian Drum | 150000 | 2 | 300000 | 2023-06-14
| W-520D | Girder Spesial | GD20 | Pembelian Drum | 150000 | 2 | 300000 | 2023-06-14
| W-521 | Girder | BG25 | Pembelian Drum | 150000 | 2 | 300000 | 2023-06-14
| W-522 | Truss Modullar | KOMPONEN STRINGGER | Pembelian Drum | 150000 | 1 | 150000 | 2023-06-14
| W-523 | Girder | BG25 | Pembelian Drum | 150000 | 2 | 300000 | 2023-06-14
| W-525 | Girder | BG30 | Pembelian Drum | 150000 | 3 | 450000 | 2023-06-14
| W-526 | Girder | CG30 | Pembelian Drum | 150000 | 3 | 450000 | 2023-06-14
| W-527 | Girder | BG35 | Pembelian Drum | 150000 | 3 | 450000 | 2023-06-14
JULI | W-522 | Truss Modullar | KOMPONEN STRINGGER | Pembelian Pilox | 38000 | 3 | 114000 | 2023-07-06
| W-370 | Truss Modullar | RB60-BU+LINKSET | Pembelian Peti | 250000 | 6 | 1500000 | 2023-07-16
| W-370 | Truss Modullar | RB60-BU+LINKSET | Pembelian Balok | 12500 | 40 | 500000 | 2023-07-16
| W-370 | Truss Modullar | RB60-BU+LINKSET | Pembelian Pilox | 38000 | 4 | 152000 | 2023-07-16
| W-370 | Truss Modullar | RB60-BU+LINKSET | Pembelian Balok | 12500 | 80 | 1000000 | 2023-07-19
| W-517 | Panel Bailey | 30 DSR2-EW | Pembelian Pilox | 38000 | 2 | 76000 | 2023-07-19 | Untuk Ramp
| W-370 | Truss Modullar | RB60-BU+LINKSET | Pembelian Porstex | 100000 | 1 | 100000 | 2023-07-19
| W-370 | Truss Modullar | RB60-BU+LINKSET | Pembelian Plate Strapping | 2000000 | 4 | 8000000
AGUSTUS | W-529 | Truss Modullar | RB50 | Pembelian Balok | 12500 | 80 | 1000000 | 2023-08-22
| W-529 | Truss Modullar | RB50 | Pembelian Peti | 250000 | 4 | 1000000 | 2023-08-21
| W-529 | Truss Modullar | RB50 | Pembelian Pilox | 38000 | 4 | 152000 | 2023-08-21
| W-525 | Girder | BG30
| W-541 | Girder | CG12
| W-537 | Panel Bailey | 30 SSR-EW
23510000
|  |  |  | 250 | 38000
12.5
135

## DATA TRIAL BAILEY
REKAP TRIAL PANEL BAILEY 2023
No. | Type | Harga ke Tim Trial (Rp) | Harga ke DHJ | Berat (Kg) | Total Harga (Rp) | Total Harga DHJ (Rp) | No.PON | Tanggal Pencairan | Tanggal Pengiriman Data ke Soleh | Tanggal Pengiriman Invoice | No. Invoice | Status Ke DHJ | Status Ke Tim Trial
1 | 30 DSR2-EW | 200 | 500 | 43245.47 | 8649094 | 21622735 | W507 | 2023-03-02 | 2023-03-02 | 2023-03-07 |  | OK | LUNAS
2 | 21 SSR-EW | 200 | 500 | 21962.04 | 4392408 | 10981020 | W504 | 2023-03-06 | 2023-03-06 | 2023-03-07 |  | OK | LUNAS
3 | 30 DSR2-EW | 200 | 500 | 43245.47 | 8649094 | 21622735 | W507 | 2023-03-14 | 2023-03-15 | 2023-03-16 |  | OK | LUNAS
4 | 12 SSR-EW | 200 | 500 | 13068.51 | 2613702 | 6534255 | W504 | 2023-03-15 | 2023-03-15 | 2023-03-16 |  | OK | LUNAS
5 | 12 DSR2-EW | 200 | 500 | 18263.61 | 3652722 | 9131805 | W503 | 2023-03-23 | 2023-03-23 | 2023-03-24 |  | OK | LUNAS
6 | 33 SSR_SS400 | 200 | 500 | 32746.12 | 6549224 | 16373060 | W500 | 2023-03-23 | 2023-03-23 | 2023-03-24 |  | OK | LUNAS
7 | 15 SSR-EW | 200 | 500 | 16033.02 | 3206604 | 8016510 | W504 | 2023-03-23 | 2023-03-23 | 2023-03-30 |  | OK | LUNAS
8 | 15 SSR-EW | 200 | 500 | 16075.37 | 3215074 | 8037685 | W504 | 2023-03-28 | 2023-03-28 | 2023-04-10 |  | OK | LUNAS
9 | 1X42 DSR2 | 200 | 500 | 56096.67 | 11219334 | 28048335 | W512 | 2023-04-05 | 2023-04-05 | 2023-04-10 |  | OK | LUNAS
10 | 1x18 SSR-EW | 200 | 500 | 18997.53 | 3799506 | 9498765 | W506 | 2023-04-10 | 2023-04-10 | 2023-04-11 |  | OK | LUNAS
11 | 30 DSR2-EW | 200 | 500 | 43245.47 | 8649094 | 21622735 | W513 | 2023-04-17 | 2023-04-18 | 2023-05-04 |  | OK | LUNAS
12 | 1x18 SSR | 200 |  | 18997.53 | 3799506 | 0 | W506 | 2023-05-03 | 2023-05-08 | 2023-05-10 |  | OK | LUNAS
13 | 1x24 DSR2-EW | 200 |  | 34984.3833 | 6996876.6564 | 0 | W506 | 2023-05-05 | 2023-05-08 | 2023-05-10 |  | OK | LUNAS
14 | 1x24 DSR2-EW | 200 |  | 34984.3833 | 6996876.6564 | 0 | W506 | 2023-05-10 | 2023-05-11 | 2023-05-16 |  | OK | LUNAS
15 | 1x18 DS-EW (TL) | 200 |  | 16570.9671 | 3314193.4236 | 0 | W506 | 2023-05-10 | 2023-05-11 | 2023-05-16 |  | OK | LUNAS
16 | 1x21 DS-EW | 200 |  | 24561.7781 | 4912355.6236 | 0 | W506 | 2023-05-10 | 2023-05-11 | 2023-05-16 |  | OK | LUNAS
17 | 1x33 DSR2H*-EW | 200 |  | 47802.9201 | 9560584.0236 | 0 | W506 | 2023-05-15 | 2023-05-15 | 2023-05-19 |  | OK | LUNAS
18 | 1X36 DSR2-EW | 200 |  | 49008.5841 | 9801716.8236 | 0 | W516 | 2023-05-25 | 2023-05-25 | 2023-05-31 |  | OK | LUNAS
19 | 1x45 DSR2H*-EW | 200 |  | 64945.0621 | 12989012.4236 | 0 | W512 | 2023-06-03 |  |  |  | OK | LUNAS
614834.8882
0

## Total
No | PON | Berat JO | Trial Data | Type Jembatan | Berat Jembatan (Kg) | Tanggal Pengambilan Invoice | No Invoice | Berat Invoice Total (Kg) | Total Invoice | Sisa Invoice | Total Sudah di Trial | Check
1 | STKJ 17 |  | W-507 - 02/03/2023 |  |  | 2023-03-07 | 02163/AGUSWAN/INVOICE/III/2023 | 12110.42 | 12110.42 | 12110.42 |  |  | 6055210
| STKJ 18 | 189231.53 | W-507 - 02/03/2023 |  | 43245.47 | 2023-03-07 | 02164/AGUSWAN/INVOICE/III/2023 | 31135.05 | 31135.05 | -158096.48 | 189071.45 | 160.08 | 15567525
2 |  |  | W-504 - 06/03/2023 |  | 21962.04 | 2023-03-07 | 02165/AGUSWAN/INVOICE/III/2023 | 21962.04 | 53097.09 | -136134.44 |  |  | 10981020
3 |  |  | W-507 - 14/03/2023 |  | 43245.47 | 2023-03-16 | 02166/AGUSWAN/INVOICE/III/2023 | 43245.47 | 96342.56 | -92888.97 |  |  | 21622735
4 |  |  | W-504 - 15/03/2023 |  | 13068.51 | 2023-03-16 | 02167/AGUSWAN/INVOICE/III/2023 | 13068.51 | 109411.07 | -79820.46 |  |  | 6534255
5 |  |  | W-503 - 23/03/2023 |  | 18263.61 | 2023-03-24 | 02168/AGUSWAN/INVOICE/III/2023 | 18263.61 | 127674.68 | -61556.85 |  |  | 9131805
6 |  |  | W-504 - 23/03/2023 |  | 16033.02 | 2023-03-23 | 02169/AGUSWAN/INVOICE/III/2023 | 16033.02 | 143707.7 | -45523.83 |  |  | 8016510
7 |  |  | W-504 - 28/03/2023 |  | 16075.37 | 2023-03-30 | 02170/AGUSWAN/INVOICE/III/2023 | 16075.37 | 159783.07 | -29448.46 |  |  | 8037685
8 |  |  | W-512 - 05/04/2023 |  | 56096.67 | 2023-04-10 | 02171/AGUSWAN/INVOICE/III/2023 | 29288.38 | 189071.45 | -160.08 |  |  | 14644190
| STKJ 19 | 155985 | W-512 - 05/04/2023 |  |  | 2023-04-10 | 02172/AGUSWAN/INVOICE/III/2023 | 26808.29 | 26808.29 | -129176.71 | 155885.33 | 99.67 | 13404145
9 |  |  | W-506 - 10/04/2023 |  | 18997.53 | 2023-04-11 | 02173/AGUSWAN/INVOICE/III/2023 | 18997.53 | 45805.82 | -110179.18 |  |  | 9498765
10 |  |  | W-513 - 18/04/2023 |  | 43245.47 | 2023-05-04 | 02174/AGUSWAN/INVOICE/III/2023 | 43245.47 | 89051.29 | -66933.71 |  |  | 21622735
11 |  |  | W-506 - 08/05/2023 |  | 18997.53 | 2023-05-10 | 02175/AGUSWAN/INVOICE/III/2023 | 18997.53 | 108048.82 | -47936.18 |  |  | 9498765
12 |  |  | W-506 - 08/05/2023 |  | 35639.36 | 2023-05-10 | 02176/AGUSWAN/INVOICE/III/2023 | 35639.36 | 143688.18 | -12296.82 |  |  | 17819680
13 |  |  | W-506 - 11/05/2023 | 1x24 DSR2-EW_UNIT II | 35465.94 |  | 02177/AGUSWAN/INVOICE/V/2023 | 12197.15 | 155885.33 | -99.67 |  |  | 6098575
14 | STKJ20 | 285621 | W-506 - 11/05/2023 | 1x24 DSR2-EW_UNIT II |  |  | 02177/AGUSWAN/INVOICE/V/2023 | 23268.79 | 23268.79 | -262352.21 | 285621 | 0 | 11634395
15 |  |  | W-506 - 11/05/2023 | 1X18 DS (TANPA LANTAI) | 17764.68 |  | 02178/AGUSWAN/INVOICE/V/2023 | 17764.68 | 41033.47 | -244587.53 |  |  | 8882340
16 |  |  | W-506 - 15/05/2023 | 1X21 DS-EW | 25958.93 |  | 02180/AGUSWAN/INVOICE/V/2023 | 25958.93 | 66992.4 | -218628.6 |  |  | 12979465
17 |  |  | W-506 - 19/05/2023 | 1X33 DSR2H*-EW | 50142.92 |  | 02181/AGUSWAN/INVOICE/V/2023 | 50142.92 | 117135.32 | -168485.68 |  |  | 25071460
18 |  |  | W-516 - 25/05/2023 | 1X36 DSR2 - EW | 51592.24 |  | 02182/AGUSWAN/INVOICE/V/2023 | 51592.24 | 168727.56 | -116893.44 |  |  | 25796120
|  |  | W- 518 - 30/05/2023 | 1X21 SSR-EW | 21962.04 |  | 02183/AGUSWAN/INVOICE/V/2023 | 21962.04 | 190689.6 | -94931.4 |  |  | 10981020
|  |  | W-512 - 05/06/2023 | 1X45 DSR2H*EW | 68299.44 |  | 02186/AGUSWAN/INVOICE/V/2023 | 68299.44 | 258989.04 | -26631.96
|  |  | W - 518 - 08/06/2023 | 1X21 SSR-EW | 21962.04 |  | 02187/AGUSWAN/INVOICE/V/2023 | 21962.04 | 280951.08 | -4669.92
|  |  | W - 516 - 20/06/2023 | 1X30 DSR2-EW | 43274.03 |  | 02188/AGUSWAN/INVOICE/V/2023 | 4669.92 | 285621 | 0
19 | STKJ21 | 174798.16 | W - 516 - 20/06/2023 | 1X30 DSR2-EW | 38604.11 |  | 02189/AGUSWAN/INVOICE/VI/2023 | 38604.11 | 38604.11 | -136194.05 | 146078.02 | 28720.14
|  |  | W - 518 - 23/06/2023 | 1X24 SSR-EW | 24926.55 |  | 02190/AGUSWAN/INVOICE/VI/2023 | 24926.55 | 63530.66 | -111267.5
|  |  | W - 518 - 30/06/2023 | 1X27 DSR2-EW | 39121.76 |  | 02191/AGUSWAN/INVOICE/VII/2023 | 39121.76 | 102652.42 | -72145.74
|  |  | W - 516 - 06/07/2023 | 1X30 DSR2-EW | 43425.6 |  |  | 43425.6 | 146078.02 | -28720.14
| STKJ22 | 313254.66 | [9 empty] | 313254.66
|  | 1118890.35 | [8 empty] | 776655.8 | KG | 273878400
|  |  | STKJ18-22 |  |  |  |  | 35465.94 | 1118890.35 | Kg
|  |  | MATERIAL YANG SUDAH DI TRIAL | [5 empty] | 776655.8 | Kg
|  |  | SISA YANG BELUM DI TRIAL STKJ18-22 | [5 empty] | 342234.55 | Kg | Update | 2024-12-14
171117275
68446910

## Sheet2
Year | Category | Product | Sales | Rating
2017 | Components | Chains | 20000 | 75%
2015 | Clothing | Socks | 3700 | 22%
2017 | Clothing | Bib-Shorts | 4000 | 22%
2015 | Clothing | Shorts | 13300 | 56%
2017 | Clothing | Tights | 36000 | 100%
2015 | Components | Handlebars | 2300 | 35%
2016 | Clothing | Socks | 2300 | 28%
2016 | Components | Brakes | 3400 | 36%
2016 | Bikes | Mountain Bikes | 6300 | 40%
2017 | Components | Brakes | 5400 | 38%
2016 | Accessories | Helmets | 17000 | 90%
2016 | Accessories | Lights | 21600 | 90%
2016 | Accessories | Locks | 29800 | 90%
2016 | Components | Bottom Brackets | 1000 | 23%
2015 | Clothing | Jerseys | 6700 | 5%
2017 | Components | Bottom Brackets | 600 | 27%
2015 | Bikes | Road Bikes | 3500 | 50%
2017 | Clothing | Jerseys | 7500 | 40%
2017 | Accessories | Tires and Tubes | 63700 | 90%
2017 | Bikes | Cargo Bike | 9300 | 60%
2017 | Bikes | Mountain Bikes | 8500 | 46%
2017 | Accessories | Bike Racks | 33700 | 92%
2017 | Clothing | Caps | 600 | 15%
2015 | Bikes | Mountain Bikes | 3100 | 35%
2017 | Accessories | Pumps | 30700 | 95%
2016 | Accessories | Pumps | 16400 | 80%
2016 | Accessories | Bike Racks | 22100 | 90%
2017 | Accessories | Helmets | 34000 | 95%
2015 | Accessories | Pumps | 700 | 10%
2015 | Clothing | Tights | 3300 | 30%
2017 | Bikes | Road Bikes | 16900 | 65%
2017 | Accessories | Lights | 36700 | 90%
2015 | Accessories | Helmets | 8300 | 99%
2016 | Clothing | Bib-Shorts | 2900 | 36%
2015 | Accessories | Tires and Tubes | 8700 | 90%
2017 | Accessories | Locks | 35000 | 100%
2016 | Bikes | Road Bikes | 8300 | 46%
2016 | Components | Wheels | 16700 | 75%
2016 | Bikes | Touring Bikes | 1800 | 15%
2017 | Clothing | Socks | 3700 | 48%
2016 | Clothing | Shorts | 12000 | 66%
2015 | Accessories | Locks | 10000 | 85%
2015 | Components | Bottom Brackets | 500 | 35%
2017 | Components | Wheels | 21800 | 96%
2016 | Components | Chains | 16400 | 70%
2016 | Clothing | Caps | 400 | 20%
2015 | Clothing | Vests | 3300 | 36%
2017 | Components | Handlebars | 5000 | 35%
2016 | Components | Handlebars | 3300 | 38%
2015 | Components | Pedals | 800 | 36%
2016 | Clothing | Gloves | 15600 | 65%
2016 | Components | Pedals | 1500 | 17%
2017 | Components | Pedals | 6200 | 38%
2017 | Clothing | Gloves | 27000 | 88%
2016 | Components | Saddles | 2800 | 38%
2016 | Bikes | Cargo Bike | 6700 | 46%
2015 | Clothing | Gloves | 13300 | 50%
2016 | Accessories | Tires and Tubes | 13800 | 85%
2017 | Clothing | Vests | 2400 | 35%
2015 | Accessories | Bike Racks | 300 | 5%
2015 | Components | Saddles | 2100 | 49%
2015 | Components | Brakes | 2300 | 34%
2015 | Components | Wheels | 10000 | 66%
2015 | Bikes | Touring Bikes | 500 | 22%
2016 | Clothing | Jerseys | 3800 | 48%
2015 | Bikes | Cargo Bike | 3200 | 48%
2017 | Clothing | Shorts | 23000 | 100%
2015 | Clothing | Bib-Shorts | 700 | 28%
2015 | Accessories | Lights | 1300 | 90%
2016 | Clothing | Vests | 1300 | 25%
2016 | Clothing | Tights | 22100 | 99%
2017 | Components | Saddles | 3100 | 42%
2015 | Clothing | Caps | 500 | 50%
2017 | Bikes | Touring Bikes | 3100 | 22%
2015 | Components | Chains | 8700 | 92%